Reporting Format-B

Introduction

- Background of Project and Organization:

Sulochana Education and Memoral Trust is is an NGO located in Ahmedabad of the Gujarat. The organization is working for NELP (National Leprosy Eradication Project, ICDS programme, Matru Mandal (for nuitrition), and HIV/AIDS prevention & Control.

The organization is headed by Dr. H V Kamdar and implementing 2 Trget Interventio projets in Ahmedaba under Ahmedabad Municipal Corporation AIDS Control Society (AMC ACS) under National AIDS Control Programme (NACP).

The present Destination Migrant Project Unit -2, at Bapunagar,  Ahmedabad is is started in the year March 2013.

- Name and address of the Organization:

Sulochana Education and Memoral Trust Unit -2

Head Office :

31, yogeshwarnagar Society,

Opp. Dharnidhar Derasar,

Bhatha, Paldi,

Ahmedabad – 380007

Project Office :

A/13, Matrushakti Society,

Opp. Sales India,

India Colony, Bapunagar,

Ahmedabad

- Chief Functionary: Dr. H. V Kamdar

- Year of establishment: 1984

- Year and month of project initiation: March  2013

- Evaluation team:

Mr. Dinesh Prajapati		                                : Program Evaluator I (Team Leader)

Dr. Rakesh Shah                                                        : Program Evaluator II

Ms. Shalvi Shah                                                         : Finance Evaluator

- Time frame: June 01, 2013 to March 30, 2015

Profile of TI

- Target Population Profile: MIGRANTS

Ahmedabad is an important manufacturing and trading hub. A variety of products like pesticides, chemicals, fertilizers, toys, electronics, dyes, printing ink, windmills, plastics, etc. are manufactured here inAhmedabad.

The project location Bapunagar is famous for its diamond, ambroidary and foundry industries. Most of the migrants are from UP and Rajasthan and in diamond industries most of the workers are from Saurashtra and North Gujarat areas of the state.

- Type of Project:  Destination Migrant  population

- Size of Target Groups: 15,000 Migrants.

- Target Area:  The TI project outreach migrant population from 10 target areas.

- Thakkarnagar

- MEMCO

- Uttamnagar

- Lala bahadur Shastri Marg

- Anil Starch Road,

- Nikol Road

- Approach road

- Viratnagar

- Khodiyarnagar

- BhidBhanjan

Key Findings and recommendations on Various Project Components

- Organizational support to the program

The evaluation team interacted with Mr. Chandrakant Barot (NGO appointed Project director) and Dr H V Kamdar (Chief Functionary). The NGO has been involved in various awareness activity related to health, Children, women issues. The organization implementing programme on Leprosy, TB, various training and IEC programme of ICDS, and HIV AIDS Prevention Programme The organization has appointed paid Project Diretor for the overall monitoring of the proramme. Time to time, they organize blood donation camps, awareness activities, etc. The organization with the support of the chief functionary and officer bearers has conducted various advocacy initiatives in the past for effective implementation of TI project.

- Organizational Capacity

- Human resources:

All the staff positions are in place. The Project staff comprise of the Project Director, Project Manager (male), Counselor,  M&E Officer cum Account Assistant, 8 ORWs and in the field 15 PL. No heavy staff turnover seen, but due to AMC ACS’s letter to curtail staff 25% ORWs from July 2014, 2 were not present on the day of evaluation. As reported 2 post of ORW were removed from 1st July 2015.

Staff has been appointed as per NACO norms and qualification criteria set by ACS – NACO except the post of  Monitoring & Evaluation Assistant cum Accountant. Project Director herself is post graduate and with 10 years experience in development sector but his involvement for monitoring TI activities seen minimal.  Appointment letters are given to staff having clear cut job descriptions and role and responsibility. The office bearers and PD have positive attitudes towards the target population by large.

- Ritesh Amin – PM

- Pramod Solanki – Counselor

- Jigna Sojitra – M&E cum Accountant

- Hitesh Patmar – ORW

- Ashok Datt - ORW

- Nitin Makwana - ORW

- Bhaumik Makwana - ORW

- Hansa Patel – ORW

- Vasant Dhabarde – ORW

- Jyotsana Amin – ORW

- Chirag Joshi - ORW

The evaluation team does not notice any turnover in staff and most of staff is one year old. However, team is old and stable but there is high turn over in PE specially in project period 2-13-2014. The project staff, in general, is enthusiastic, hardworking and committed and have good rapport with stake holders and migrant population.

- Capacity building:

The evaluation team observed that various trainings have been provided to the staffs of the present TI-project. Despite huge turnover of the PE, present staff has make efforts to train new PE but still 50% PEs are untrained not even given induction training. PE needs induction training to continue their work in good manner. Further, the project team requires specific training on documentation, IPC, outreach and advocacy.

- Infrastructure of the organization:

The project has one program office and two DICs (Its claimed to have free DIC). Office cum DIC is set up near by target areas. The infrastructure of the organization was found to be adequate and spacious. All necessary facilities like electricity, computer, printer, furniture were available and coded. The present Project Office cum DIC is like on room / hall and no provision of separate meeting/Counseling space. All assets purchased are codified and marked properly.

- Documentation and Reporting:

Documents are maintained according to the SACS protocols. Most of the documents are in Gujarati and English. DIC level meeting were initiated in last month only i.e. in March 2015 and records are also available for one month only i.e. March 2015.

No record was found for ORW field visit and IPC from March 2013 to December 2014. In January-March 2015 average 30% sessions are attended by ORW as observed from ORW records. ORW maintained field diary which is like register and not contain much details of field activities. There are many registers and ACS provided printed formats. Counselor is not maintaining dailly dairy and Daily dairy of PM is also not updated regularly.

The documentation system of the TI project was not good and adequate. Some Documents were not understood by the project team and not maintained as per the NACO guideline specially ORW Dairy, Counseling register, Condom Stock register, drug register and IPC format. Unique Identification Number was mentioned in the Master Sheet of ORW and in referral slip. The project has also maintained training register and training related activities are captured.

TI has developed and updated master register but analysis of various services was not assessed or not tracked i.e. referred V/s tested to ICTC, no. of migrants who had STI & had done their testing at ICTC, no of person avail various types of services, number of migrants not followed / traced etc.

The project needs to establish adequate documentation and record keeping system. The project team requires training on documentation and record leeping as per NACO provided formats.

Specially M&E Cum accountant needs to build her capacity in her tasks. Finance related documents both manual and Tally was not present at TI office and was kept at some other place. During evaluation it was presented by PD during 2nd day after due request.

- Program Deliverables

Outreach

- Line listing of the HRG by category.

The TI NGO has maintained Master Register for their currently identified HRGs. Line listing of registered migrant population was available for the review. In the line-list, each member was provided the Unique Identification Number (UID) and the same list was updated but not verifie, traced or analised. The TI team has registered 12533 migrants against target of 15000 in last reporting year up to March 2015.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

Total 12533 migrants were registered through three service sources i.e. counseling, STI health camps and two DICs. The project has provisioned two DIC in two areas. As claimed by TI staff daily 15-20 migrants visits DIC but it was not justified with documents or by field / PE interactions. The office cum DIC is like one room and does not have any specific provision for meeting, rest or Counseling. Its at residential society and not fit and ideal for migrant TI.

Total 4378 migrants benefitted with Counseling service, 5955 attended clinic, and 3728 migrant received 3 services from the project.

- Micro planning

Micro planning was not in place and initiated since Janaury 2015 after technical support of TSU PO.  The team has put an effort to illustrate the HRGs and their geographical locations on maps, the same is reflected in their work and documentation. Good Site maps are developed. More importantly PEs involvement in the TI as whole is yet not started.

Further to note, the TI staff has not maintained daily diary in good manner. It looks like format / register. The project team, as mentioned during an interaction with them, maintained daily diary but  which was not linked with monthly activity plan such as PE supervision or health camp, or ICTC camp or IPC session or FGDs or congregation events, counseling session, follow up and so.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

12533 Migrants are covered. Team has line listed the contacted but not classified in sub groups nor traced for various service links. While working with migrants TI team has developed good rapport with stake holders and do not feel difficulty to enter in industries and factories. TI NGO has put efforts to contact factory owners, managers and watch man gate keepers and has done advocacy meeting with them.

The TI project has a target population of 15,000 which has to be covered from 10 identified high risk areas. Out of 15,000, the TI project has registered 12533 HRB migrants till March 2015.

- Outreach planning

Planning was done for out reach after January 2015, movement register was maintained as per need. Monthly planning was done by team in presence of PM and PD and weekly meeting of staff members are also carried out by Project manager for planning, review and feed back.

ORWs have their area map. However the day to day plan should also reflect the activity they are going to perform i.e. organizing event, 1-1 interaction, 1-group interaction, health camps, street play etc. This would help in better planning & further focusing on the activity to be performed in the field.

- PE: Migrants

PE: Migrant ratio is: 1:835. The project has at present 15 PEs against the coverage of 12533.

- Regular contacts

While interaction with migrants, stakeholders & PEs, it was noted that the ORWs are visiting their respective outreach area on a regular basis for providing different services like condoms, 1-1 interaction, congregation events, follow up of the STI patients.  However, the contacts made by ORW and PEs were not reflected in the service uptake. The service component such as STI, ICTC, Follow up of STI/DOT/PLHIV and RPR was weak in terms of their overall achievement.

- Documentation of the peer education

PE has been identified and the project has just in process way for developing filed level documents and formats so PEs are not able to maintain any formats and records for data collection.

- Quality of peer education

The project has witnessed hug turn over, and 50% PEs are untrained, Additionally due to grant delay they have not paid PE incentives since couple of quarters; therefore, the quality and skills of PEs was not reflected in sustainable service uptake and PEs documentation. Present PEs had basic knowledge on the issues of HIV/AIDS i.e. route of transmission, importance of testing. However,

While conducting Focused Group Discussion with migrants, it was known that migrants were aware of the basic HIV issues; however, they were not aware of confidentiality norms. It was also reflects during interaction with some stake holders that confidentiality and privacy are not maintained at many levels.

- Supervision

The project has not laid out supervision mechanisms and systems. Evaluators observed that the project director shown minimal interest in project monitoring and thier presence is witnessed once in a two months in the project. Presence of PD has been reflected in field also. TSU PO has visited TI as per his plan and provided supportive technical support to the TI. Additionally PM has also done regular field visit.

From M & E part, field visit, or data monitoring is totally absence and needs immediate actions to plan monitoring & Evaluation activities as per ToR.

- Services

- Availability of STI services

Dr Hiren Sanghvi (BAMS) is providing his services for health camp; he is not MBBS and BAMS but has received syndromic management training for 5-6 times. He is client friendly and takes keen interest in project activities. Beside STI services, TI also has developed linkages with Urban Health Centers (UHCs) for RPR testing, Referral system is established by the TI NGO for STI, HIV testing and RPR testing.

However, TI has established health camp approach and linkages, TI has conducted only average 11 health camps per month which is almost 50% less than the indicator.  Health camps are organized at various congregation points. 2 DIC (Claimed to have rent free DICs) and 1 Project Office cum DIC are in place.

- Quality of treatment in the service provisioning

Doctor interacted by Evaluation team have up to date knowledge about NACO STI Guideline and TI approach and strategies. He takes keen interest and involves himself in project activities and client satisfaction. The Empanelled Doctor is equally trained with syndromic management guideline. But provision for drugs and social marketing of STI treatment is not evidence based and cost of the drugs are not generated from beneficiaries.

Total 543 STI patients identified and treated under the TI project, 119 HRGs took services from government health facilities, 163 are tested for RPR from which none is reactive for RPR. However, out of 543 STI treated, 375 were tested for HIV at ICTC but STI follow up seems very poor and in random verification of register of 3 months (Oct 14, Dec 14 and March 15) it was observed that non of STI or HIV tested person was followed.

Pre HIV, Post HIV and Follow up of STI/PLHIV was totally missing at TI level.

- Documentation

Registers and records are maintained as per SACS guideline; Referral slips are developed and maintained. Referral slips was also found at the ICTC centre and also the same was maintained at the TI level. Stock register for condom and drugs are being maintained but not updated in right way. Peer profile developed is not adequate and needs to update with more information.

Register of Counsleor, needs to update with right and accurate information. In many formats and registers, some column were not filled up and left blank (information was not captured). The organization is at initial stage of maintain MSDS formats.

- Availability of Condoms

Condoms were found to be not adequately available for the TI project.  However, Peer Educators & migrants reported during an interaction with them that they receive adequate condoms regularly. Stock out was found though out the year during the project period.

- No. of condoms distributed

A total 27500 condoms were distributed by the TI project in a period of 12 months against target of 60000. TI NGO has established 39 outlets against target of 50 and mainly promoted  DElux brand of  NIRODH. It was noticed that rolling fund for condom were not fully used and funds were not generated from condom beneficiaries but cost of condom were contributed by NGO itself. This makes Social Marketing approach and concept weak and become barriers for sustainability. There is no mechanism of tracking of condom distribution and record income generated from condom distribution.

- Information on linkages for ICTC, DOT, ART,STI clinics

NGO also has developed linkages with 1 ICTC, 2 FICTC and Mobil Van ICTC of AMC. Referral service has been started but need strong coordination, planning and follow up system. TI NGO has claimed to have ICTC referral of 2556 against target of 3000 i.e. 85%. 8 PLHA were identified and out of this, 4 were linked to ART, no referral was done at DOT center for TB.

The TI project has established linkages with ICTC, Coordination sheet signed by both IT NGO staff and ITC staff are found and verified at both the centres. STI screening is being done through health camps at various congregation points of TI area. The linkages with other services found to be weak for instance, out of 12533 migrants covered 2556 referred to ICTC and only 2028 were tested for HIV. Similarly, DOT and ART linkages were also found week.

- Referrals and follows up

Referrals of migrants to ICTC centre are being done on a regular basis. Until March 2015, 2556 migrants were referred for ICTC testing but only 2028 reached ICTC and underwent HIV screening. Total 600 migrants referred to STI clinic and out of 543 treated as STI, 375 were tested for HIV.

During random sampling and verification, it was found that in 3 months not a single STI, or PLHIV was followed or traced.

- Community participation

- Community participation in project activities

Community participation in congregation activities was found suitable and equal compare to age of TI. However, after January 2015, ACS / NACO has restricted expenses in area of community mobilization activities. 40 advocacy meetings in 2013-14, 18 advocacy meetings in 2014-2015 were conducted. Only list is available. TI Team is not clear about concept and importance of PMC in migrant project as per NACO guideline and thus, PMC is not formed at TI level. Team has identified 37 stake holders. 2 demand generation activities were conducted.

Community participation should be increased. It is suggested to increase migrants’ participation in planning and conducting advocacy, events and mid-media activities.

- Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages were established with various services providers like STI and ICTC.  Good linkages have been developed for STI Doctor and ESH. Due to good documentation, linkages could be verified with existing documentation and office keeping. The same was also verified during field visit and interaction with ICTC counselor, peers, stakeholders & community member.

- Percentages of HRGS tested in ICTC and gap between referred and tested.

2556 migrants were referred for ICTC testing but only 2028 reached ICTC and underwent HIV screening. There is gap of 20% found between referral to ICTC and actual tested for HIV.

It is recommended to the TI project team to strengthen follow ups of HRGs for ICTC services.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

During the field visit and interaction with various stakeholders in Viratnagar and Memco, it was found that stakeholders were aware about the project and involved in the project planning and monitoring. They provide spaces for organizing the health camps. Advocacy meetings were also held by the TI project to develop the support system. In total 18 advocacy meetings were held during the project period. Register and attendance sheet was available for the inspection and the team feels that the same should be continued.

It is recommended that advocacy meeting with the big industry owner/manager/HR person, doctors of Government Municipal Hospital and Policemen should also be attempted.

VII. Financial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

They have followed the approval basis and expenses are done as per the planned budget and as approved in the budget

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments

Payment is done as per the approval and vouchers, registers, bill book everything is checked with that of the registers maintained and vouchers are also machine printed and serial number wise.

- Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

Quotations are obtained from the parties regarding the purchase of furniture, electrical and purchase of drugs. Quotations from minimum three parties are obtained.

- Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

Documents are maintained for Cash book and bank books and audit reports and related SOEs and related documents are properly maintained.

- Competency of the project staff

VIIIa. Project Manager

The present Project Manager is recruited as per the norm and he is Post Graduate in Social Work and has promoted from Counselor to PM and is one of the oldest team members. He has good knowledge about HIV and project indicators. As per the records, PM has conducted review meetings with staff but quality of meeting need to be increased. The PM is able to delegate work to the team and able to provide good leadership to the TI.

PM should review the progress of each indicator and suggests the team to take necessary action and extend support on need basis. PM needs to develop strategies for community participation in the project.

VIIIb. ANM/Counselor

The project has recruited counselor is working with this TI since July 2014.  He has basic understanding regarding Counseling and TI components. Performance of counselor in-terms of achievement of clinic related targets is good. Documentation of counseling activities needs to be strengthened.

It is suggested to counselor to track each client who is accessing project services, develop a list of clients require specific services, and develop list of clients require follow-up services. Counselors also need to prioritize clients based on high-risk behaviors of migrants.

VIIId. ORWs

The project has 8 ORWs as on June 2015, All ORWs are senior, trained and seen matured for TI level tasks. ORWs were aware on the issues of outreach activities, STI, importance of ICTC testing. ORWs lack understanding of hotspot analysis and importance of DIC.

VIIIg. Peer educators in Migrant Projects

The present TI project has 15 Peer Educators. 53% were from Source state. 8 were from Gujarat, 1 from Maharasgtra, 3 from UP, 2 Rajasthan and 1 from Maharashtra. PE needs to be sustained and trained on basics of HIV and conducting various IPC sessions.

VIII i. M&E Officer cum Account Assistant

The present M&E Officer cum Account Assistant is working with this TI since March 2013. It is claimed by her that she has completed BA (Economics) but from more his educational certificate it was found that she has done BA (Sanskrit) and PGDCA. He is not qualified, not fit and capable to handle tasks of the Account, finance as well as M&E. Presently, external person from NGO maintained account and finance related records and documentation. In M&E part, Analytical information on various aspects like gaps in services, nature of migrants, drop-out migrants needs to make available for monthly / Quarterly review.

Capacity building in M&E tasks, Finance Management and Tally would certainly provide the direction & strength to the project.  M&E spends considerable time for entering field data than analyzing it to support the field activities or It is suggested to replaced capable, competent and qualified person for the post.

IXb. Outreach activity in Migrant Project

Outreach activity is performed by the ORWs & PEs both. PEs mainly performs the IPC sessions with the migrants and as per report ORWs monitored it. ORWs were found to be aware of various IPC tools & the same was being carried out at the field level but PEs seen unable to perform good IPC at filed.

638 sessions by 15 PE in 3 months (January-March 2015) Average 14 sessions per month. Records of earlier (Before January 2015) were not avialeble at TI level.

X.	      Services

Overall service uptake in the project is Average.  The project needs to ensure quality service uptake despite the intimidating working conditions that exist in migrant area. At present the evaluation team feels that the TI project is mainly involved in awareness generation activities, but the same should be shifted and linked to different services components.

The uptake of  DIC services is very poor and need to be strengthen. Further, there was no mechanism to track migrants visited DIC. Further, activities at DIC are not adequately documented. Evidence based documentation of DIC footfall needs to be developed

- Community involvement

Community involvement is minimal. At present community is involved in the form of PEs and stake holders only. It is suggested to increase community involvement in project planning. Community is required to involve in planning, implementation, monitoring or advocacy of the TI project.

- Commodities

TI has 39 active outlets including 25 non-traditional and 10 nontraditional outlets. Total 27500 socially marketed condoms were distributed which is merely 45% of total need / indicators.  Documentation of amount received from the selling of condoms was not available.

- Enabling environment

The present TI project has not formed a formal Project Management Committee to uptake the advocacy meeting. Advocacy meetings are conducted as per project’s monthly plan at different levels. The project team has conducted advocacy meetings each month with presence of Project Director with Chawl Owners, political leaders, Local leaders, Pan Walas, HR Manager, Directors of companies, Contractors,  etc.

The evaluation team has observed that the project team does not have any clarity on Project Management Committee (PMC). It is recommended to form PMC and make in functional involving industry, contractors and other leaders and stake holders. The TI programme can be linked with CSR and activities of the GIDC association.

- Social protection schemes/innovation at project level HRG availed welfare schemes, social entitlements etc.

At present the TI project has not yet commenced any such scheme or entitlements especially focusing on the migrants.

- Best Practices if any

None to report

Annexure C

Confidential

Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Dinesh Prajapati | 721-722, Kanan Society, Rajan Nagar, Valsad Pardi Road, Abrama, Valsad – 396145, Gujarat – India M : +91 9408333476 Email: dinesh_bsw@yahoo.com |
| Dr. Rakesh Shah | 6, Sushilnagar Society Part – 1, Nr Gwalia Sweet Mart, Gurukul Road, Memnagar, Ahmedabad- 380052, Gujarat – India M : +91 9925113609 Email: rrshahad1@yahoo.co.in |
| Ms. Shalvi Shah | Dhirubhai & Company, Ahmedanad M : +91 9510263467 Email : shalvi@dbsgroup.in |
| SACS representative | Mr. Rakesh Patel / Mr Rajan (AMC ACS) M: +91-8469969760 |

| Name of the NGO: | Sulochana Memorial Health and Education Trust unit -2 |
| --- | --- |
| Typology of the target population: | Destination Migrants |
| Total population being covered against target: | 12533/15000 |
| Dates of Visit: | July 03, 2015 to July 05, 2015 |
| Place of Visit: | Bapunagar, Ahmedabad (Gujarat) |

Overall Rating:

| Total Score Obtained (in %) | Rating | Recommendations |
| --- | --- | --- |
| 61.7% | Good | Recommended for continuation with specific recomendation |
| Specific Recommendations: - Incentives to PEs must be transferred by bank account. - Present M&E Assistant com Accountant is not qualified and also not able to maintain account and financial reports. In present system, person from NGO maintained and do account and finance related work, TI based M&E Com Account assistant is seen not qualified, capable and fit for finance related reporting. It is strongly recommended that Account and finance related work must be done by TI based M&E Com Account assistant and not to by any other persons. - Finance related SOE, Bank passbook and other records should be strictly made available at TI office only and NOT at any other office / place outside the TI office. TI NGO needs to adhere to NACO’s guideline for financial management. - In Social Marketing of Condom and Medicine, fund is not generated from benificiaries but is claimed to be contributed by NGO itself. It is suggested to roll out the funds through social marketing only. - TI team does not have clarity of PMC (Project Management Committee, its role and its importance. It is suggested to provide technical support regarding this and PMC needs to develop and in function within next quarter of the project period. - Needs to increase DIC utilization by migrants with ensured qualitative services. - Follow up of STI, DOT and PLHIV needs to ensure at Counselor level. - TI needs to develop analysis mechanism. M&E Officer should conduct TI Data analysis regularly. This will provide specific inputs on outreach activities that will strengthen the effective implementation of TI. - Office cum DIC can be changed and can ne replaced within target areas, should have separate arrangement for DIC and office and near to migrant work place. - The TI NGO requires establishing internal project monitoring and review mechanism. Monthly PD review meeting must be ensured. - Financial related queries related to DIC, and Office rent must be seen at AMC ACS level and necessary action should be taken by AMC ACS according NACO financial guideline. |  |  |

Name of the evaluators				Signature

| Mr. Dinesh Prajapati |  |
| --- | --- |
| Dr Rakesh Shah |  |
| Ms Shalvi Shah |  |