Annexure: B

Reporting Format -B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluation)

Introduction

- Background of Project of Organization

REWA NETWORK OF PLWHA is formed by Dharmendra Divedi, Dayaram Swami, Shyambati Verma and Sushila Saket in 2008 and registered under Society registration act 1860 in the year 2008. The NGO is working in the field especially for PLWHA. The Organization is played a cataract role among the PLHA in the REWA district since last two year because of the President one of the PLWHA.

- Name and address of the Organization

REWA NETWORK OF PLWHA

Address of TI Project – SAF Chowk, Bichhiya, Vairo Marg, REWA, MP

- Chief Functionary :-

Dharmendra Divedi , President

- Year of establishment : 2008

Year and month of project initiation : 7th February 2013

- Evaluation team :

- Mr. Pitambar Panda (TL)

- Nand Kishore Sinha (Program Expert)

- Mr. Sabbir Ansari ( finance expert)

- Mr. Rajeev Pandey(Observer/SACS )

- Time  Frame :

Date – 23rd and 24th March-2015

Profile of TI

(Information to be captured)

- Target Population Profile :  IDU

- Type of Project : Core

- Size of  target group :- 500

- Target Area – REWA gurh and Govindgarh Block of REWA

Key Findings and recommendation on Various Project Components

- Organizational support to the program

No office bearer was present for interaction during evaluation period. According to the PM & meeting minutes the PD of the TI project visit for review of program periodically. No such action taken after meeting conducted. No related record of PD’s presence and minutes of the meeting are  found in the register during our visit.

Organizational Capacity

- Human Resources: The staffing pattern is on hierarchical basis. The Project Director is part timer for TI project. The Project Manager is the sole responsible of the TI project activities. The Doctor, Accountant, ORW work under him and responsible to him .PE s worked under ORW. ANM post laying vacant from the contact period of this year.

The supervision  system in the TI Project is in descending order and reporting system reporting is in ascending order the commitment level of staff is good and they have positive outlook towards their service. There was no staff turnover since initiation of the project

- Capacity building :

The Staff of TI project is trained and aware about their job responsibility

- The Project Director & Project Manager was received training by SACS.

- Lady ORW- The post of counselor was also trained on subject matter like Harm reduction & Abscess Management.

- Accountant – He was not received any training

- ORW – 3 ORWs  have been trained on BCC, Outreach and harm reduction from SACS and they  has been working since last year

- Peer Educator was trained by NGO and SACS.

Training to the staff was given by lectures, demonstration, audio –visuals and Participatory methods the training of the staff was documented and PM, Counselor. ORW & Accountant were acquainted about their nature of jobs.

- Infrastructure of the Organization ;

The Infrastructure is sufficient for running of TI project. Many items were purchased in TI project. List of assets is enclosed with report separately.

- Documentation and Reporting :

Documentation and reporting system adhered to SACS norms. The documents were available for evaluation weekly and   monthly review meeting were held and reports were disseminated & shared.

Program Deliverables

Outreach

- Line listing of the HRG by category.

Line listing with codification is available at TI of IDU- 506 against 500 active as on date.

Sub-Groups and their Size – IDU- 500

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

NA

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

NA

- Micro planning in place and the same is reflected in Quality and documentation.

Micro planning has been done by the project & it is provided to PE through  project on the printed format on form B. Hot spot analysis, gap analysis, condom, N/S demand and Distribution, ICTC, STI, VDRL etc have been planned during weekly review meeting and the documentation is reflected in prescribed format provided by SACS.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

Contact – Individual contact 84% and Regular contact almost 29 % coverage.

- Outreach planning – quality, documentation and reflection in implementation

Outreach planning is available which is verified at the hot spot level. Gap analysis has been done on condom & N/S distribution hotspots wise as per demand of the HRGs.

- PE: HRG ratio- Ratio is 1: 40 almost maintained as per NACO guideline.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

Peers meet to HRGs on weekly basis twice a month and providing services such as condoms, N/S and other referral services.  The understanding level of the project staff were reflected in impact among the community members.

- Documentation of the peer education

Peers are maintaining Peer dairy which is verified by ORW in review meeting, it is found that planning process and writing of the plan has been done centrally at project office. Micro Plans are not prepared for project services & regular contact, STI treatment through STI Clinic, ICTC referrals and other services Peers are prepared N/S & condom requirement of their individual HRGs.

- Quality of peer education- messages, skills and reflection in the community

Peers have knowledge on programs like TI components, outreach and service delivery through Induction training provided by NGO and by SACS, but their knowledge is limited, required ORW support regularly. PEs is in regular contact with the HRGs of their sites. The peers documentation and programme knowledge skills are reflected in their working pattern. However, some time it is reflected the systems have sensitivity towards risk & vulnerability of the HRGs .

Supervision- mechanism, process, follow-up in action taken etc

ORW are regularly supervised the project activities which is found during record verification. Micro planning was not prepared by staff for the follow up and implementation.  It is designed by ORW as fill up B and B1 format basis for the target population in weekly review meeting. The movement register, referral register are regularly monitored for the supervision. PM should monitor each & every services of the TI project for covering individual HRGs.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

One Static clinic is set up at project office for providing STI services to HRGs. The doctor comes two days in a week It is been found that the HRG for providing services and it was limit on abscess management only. There is stock out of kits for STI treatments.  HRGs are going to the Govt. hospital for STI treatment, but only one doctor in charge of the STI clinic/ ICTC and Nodal officer(TB & AIDS) who have no time for providing service to HRG like STI checkups & treatment. It has been found through the records during verification that 131 STI cases are taking treatment during year 2014-15. It is required to display of doctor’s timing board in the project sites for betterment of the HRGs.

Dr. Anurag sharma (RMO)-selected as doctor and not trained on SCM through SACS. It has been provided services to HRGs since December -2013 and have been gone through the Symptomatic Treatment protocol. He gets15000/month from TI project. The doctor comes 2pm to 4 pm in 2days in a week i.e. Mon, Wed. As per the interaction with the doctor it is been found that maximum of the HRGs are comes for abscess management which comes through referral time to time from TI and he sends them to Govt. hospital for syphilis screening, ICTC & STI treatment.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Static clinic have adequate place & equipments like BP instrument, Stethoscope, weighing scale, hand gloves & examination table are not provided through TI project as per NACO guideline. No STI cases treatment found due to lack of STI kits in this year.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds. -        NA

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

One RMO doctor named Dr.Anurag Sharma has been selected for provisioning treatment service & trained on syndromic treatment protocol. Referral to ICTC, Surakshya clinic is recorded. Record of Static clinic is not properly maintained and follow mechanism is also needed.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

Treatment registers, referral, slips, stock register for medicine is available in the TI. The NGO is not received any STI Kits from SACS for TI. As the kits are supplied from SACS there is no system of procurement of STI medicine. Since last six month there is no STI KIT supply from the SACS. Patient referral register are maintained by ANM in the TI project.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

The condom distribution is done through ORW & PEs.  Outlet supply /distribution are not practice. Record of condom stock & distribution not maintained separately and the supply chains need to be upgraded. Since last 3 months condoms was out of stock found at project level.

- No. of condoms distributed - No. of condoms distributed through different channels/regular contacts.

Condoms are distributed through the Peer educator & ORW. Against the demand of condom-46800/Supply-53500 in year 2013-14, Demand- 49950 distribution- 28790 out of which is only 22000 received from SACS and 4000pcs from ICTC. Received records are available with TI.

- No. of Needles / Syringes distributed through outreach / DIC.

N/S was distributed through ORW, DIC & PEs. 190992 pcs syringes were distributed against 209902 demand for FY 2014-15and 96641 syringes were distributed against 194618 demand for year 2013-14.

- Information on linkages for ICTC, DOT, ART, STI clinics.

The ORWs & PEs are regularly provided information to HRG on linkages. NGO have been established contact with ART, ICTC & STI clinic. HRGs are referred to ICTC and STI clinic at Dist Head quarter Hospital.

- Referrals and follows up

Total referred 940 and 940 tested for ICTC. Referred-131 & treated 131 for STI   at Govt. STI clinic as per TI record). Syphilis screening referral- 0 & tested-0 done through local testing center & Govt.STI clinic at DHH,

- Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

No SHGs/CBOs were formed by the project from Community.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Regular DIC level meetings, Hotspot meetings held in monthly basis and advocacy committee formed with the community participation & stake holders, Follow up of the advocacy meeting is not maintained. Observation of events like WAD-2013,WAD-2014 in this project period where 75 HRGs were participates.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Established linkages with the various service providers like ICTC, STI, ART and STI clinic verified referrals slip. As per interaction with the ICTC counselor, Lab. technician and STI counselor at the Dist HQ hospitals, TI is in regular contact with the Service providers.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

Average 86% tested among referral & average 14% gap between the referral & tested among HRGs.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

Stake holders have been identified but they are not actively engaged in activities like distribution of condoms, advocacy, crisis management meeting and regular orientation meeting by TI at different level.

VII. Financial Systems and Procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication:

Form the perusal of records, it was observed that the guidelines issued by the SACS/ NACO have generally been followed by the NGO. Following discrepancies were noticed by us:-

- Recommendations specified in Audit Report have to maintain double column cash book, but NGO maintained in tally, so compilation is not needed by the NGO till the date of evaluation.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of  using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of  settling of advances before making further payments.

Examination of records on test check basis reveals that the payments are being generally made in accordance with the laid down system, i.e.,

- NGO is using printed serialized vouchers

- Most of the payments has been paid by way of cheque

- Separate bank account has been opened for project

- All payments are made in accordance with the approved action plan

- All payments are approved by the Project Director

- Some payments vouchers (6 No's.) of various heads, i.e., Travel to PM/ Counsellor/ Out Reach Worker were not supported by the Bills.

- Systems of  procurement - Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

During evaluation, it has been observed that no procurement of drugs has been done by the NGO. After discussion, it has been observed that there was not required of such system due to STI drugs supplied from SACS.

- Systems of documentation- Availability of bank accounts (maintained jointly, reconciliation made monthly basis), audit reports.

- Bank Reconciliation Statements (BRS) have not prepared till 31th March 2015.

- NGO has maintained a separate & jointly operated at local bank account for TI Project

- SOE has been submitted on time specified format provided by the SACS.

VIII. Competency of the project staff

VIII a. Project Manager

Program Manager Mr. Sankarlal Soni joined TI in 4th June 2013. He is MA.(sociology.) He is old to TI project & acquired knowledge from Induction, orientation & other training through STRC, SACS in Aug’13 onwards. As a PM his knowledge level is up to  mark about Program Management, financial management, computerization and management of data. Knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, monitoring and field visit & advocacy initiatives etc. Interaction and Interpersonal skill are satisfactory among HRG’s

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.

ANM/Counselor post is lying vacant since last one year. No quality candidate are not interested to join TI in this post as stated by both PM and PD. The allocation budget are utilizedd in other field without prior permission of SACS. There is no surplus fund in this particular head.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc. Support plan needed for weak performance Peer.

There is 3 male and one female ORW were appointed by the project with having required qualification & joined for outreach activities. ORW are well aware and trained in the subject and having good rapport with the HRGs, but need more training regarding the program and documentation. ORW have lack of knowledge on documentation and various aspects of the target indicators define for the outreach plan for the STI, RMC, ICTC, and BCC. ORWs are providing regular support to PEs for out reach. They set targets on various indicators of the TI project. One female ORW was joined just last two month before and act as counselor for family counseling. But there are no record found the work of lady ORW in the project.

VIII e. Peer educators

There are 12 peers appointed by the projects who are covering the registered 500 HRGs. PEs have good rapport with their HRGs. It was found during our filed visit. PEs is very familiar with the service delivery and they are not associated with the program planning with support of ORWs and had received information regarding program delivery and commodity distribution. They are reached to individual HRGs for outreach & distribution of commodities.

VIII f. Peer educators in IDU TI - PE ratio is 1:40

There are 12 peers appointed by the projects who are covering the registered 500 HRGs. PEs received information regarding program delivery and commodity distribution through TI and training. They are reached to individual HRGs for outreach & distribution of commodities.

VIII g. Peer Educators in Migrant Projects - NA

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.       NA

VIII i. M&E officer

Whether the M&E officer (FSW and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.   NA

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

As per interaction with all PEs the documentation which reflects the hot spot wise service and outreach plan is not available at TI and is only supply of form B and B1 for fill up. The ORWs and Peers are not properly clear about the format and  plan. Condom demand/supply and gaps analysis is not properly planned. Hotspot analysis are not in place. All the activity proves that is a gap between plan & outreach monitoring. But it is done for a practice manner.

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.  	NA

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

During FGD conducted with the HRG at Ranitalab, Hospital chowk and Bus stand hotspots it was found that the 40% HRGs were satisfied with service delivery provided by ORWs & PEs.   condom uses reflect among HRGs, is very less & it was proved that the occurrence of STI and HIV among HRGs is in a horrible manner Less awareness on incidence of STI & HIV infection. No HIV positive were reported in this year. The HRGs are taking OST for reduction of the risk of injecting. The HRGs are very satisfied the service of abscess management through the project doctor at Project office. It was suggested to the TI NGO to display board placed different project sites for the doctor timing.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

The community participation structures are not in place as per the project record there is no committee formed with community participation or there is no such type of meetings with HRGs held with support of HRGs & stakeholders. Hotspot meeting & DIC level meetings are held with HRGs participation, Except PEs they are not involved in planning, implementation of the project activities.

XII.    Commodities

Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

Planning is developed of each hotspot for condom, N/S demand /distribution, but there are no gap analysis calculation among demand and distribution. There is no condom social marketing program. Hot spot Analysis were not prepared at TI level. That so they are not able to practice the same in monthly & weekly demand/ distribution. They distributed as per availability. Outlet supply record is not in place.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

They have done advocacy with auto union at a regular basis. Monthly meeting were not organized with the stake holders along with the community members. Community members are mainly involved in the services which are provided by the TI. There is no Project Management committee formed with membership of local community/ stake holders.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

No social protection scheme are not adopted by TI for the shake of community.

XV. Best Practices if any,

The TI staff including PD has no knowledge about the best practices at TI level.

Annexure C

Confidential				Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of evaluator(S):

| Name of the evaluators | Contact Details with phone No. |
| --- | --- |
| Pitambar Panda | 09431705895 |
| Nand Kishore Sinha | 9470390196 |
| Sabbir Ansari | 8871906863 |
| Officials from SACS/TSU (as Facilitator) | Rajeev Pandey |

| Name of the NGO: | REWA NETWORK for PLHIV |
| --- | --- |
| Typology of the target population: | IDU |
| Total Population being covered against target: | 500 |
| Date of Visit: | 23rd & 24th Mar-2015 |
| Place of Visit: | REWA |

Overall Rating Based programme delivery score:

| Total Score Obtained (in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- PE diary should maintain properly, it is recommended for training on Diary maintain. - Advocacy should be carried out among the community. - More initiate should taken on STI treatment, syphilis screening & ICTC test - Static clinic doctor timing should be displayed in project sites for HRGs information and Doctors availabilities discussion during DIC level meeting & hotspot level meeting. - Focus given on Micro plan for each HRG covered in regular contact. The TI project management should prepare micro plan accordingly. - Ensure to formation of SHGs/CBOs among HRG. - Ensure ICTC test among every HRGs at least in each six month interval.

Name of the evaluators                                             Signature

| Nand Kishore Sinha |  |
| --- | --- |
| Pitambar panda |  |
| SABBIR ANSARI |  |