Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

O Background of Project and Organization:

Gram Sudhar Samiti is a non profit  NGO registered under Societies Registration Act 1860 & FCR Act 1979. It was established in year 1997 under the founder member of Shri Rajan Mishra and Brajen Mishra and Arun Tyagi with a purpose of Health, Education, Sanitation, Watershed & Women empowerment. The NGO starts their work from own means to improve the income of the poor people of Sidhi district. The NGO is working on development of   women & children with equal emphasis on livelihood opportunities. The NGO have been working in the field of HIV/AIDS in Sidhi district as a TI partner of MPSACS since October 2011.

Name and address of the Organization:

Gram Sudhar Samiti

TI office address:  MIG-3, Pt. Di Dayal Colony, Sidhi, MP

- Chief Functionary:  Mr. Arun Tyagi

- Year of establishment: 1997

- Year and month of project initiation:  2008

- Evaluation team:

Mr. Pitambar Panda, NK Sinha, Mr. Sabbir Ansari

- Time frame:  25th and 26th March -2015

Profile of TI

(Information to be captured)

- Target Population Profile: FSW, IDU

- Type of Project: Core Composite

- Size of Target Group(s) : FSW-150,  IDU-400

- Sub-Groups and their Size:  FSW-150(SB-74,HB-76) & IDU-400

- Target Area:   adjoining area of Sidhi District HQ township

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

Arun Tyagi, Secretary is working as Project Director in the TI project. He is one of the GB members. We came to know that he is always busy in different project work which runs through this NGO with support of Govt of MP. The chief functionary of the organization have busy in so many projects which is run directly because of this he have no time for TI visit during evaluation period. He is partly involved in the project activity and project monitoring. PD had attended TI review meeting conducted by MPSACS held at Bhopal

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

The staffing positions like PM-1, ORW-4, M& E cum Accountant-1 & Doctor-1 are filled as per MPSACS protocol. The posts are filled as per project proposal and staffing pattern as per guideline of NACO. One counselor  had been working from April to September in this project period and after sept she was promoted as female ORW of FSW and IDU both for family counseling purposes. ANM replace twice within last 4 months in this project period. Roles and responsibility has been defined in each of the appointment letter which clear the roles and commitment of the staff towards the project. The reporting and monitoring structure is in place, meetings are held regularly and meeting registers and minutes are available. The staff is not committed for the project activities and having good understanding of the community.

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

All staff of the TI is trained through induction, refresher, Project management, Accounts, record keeping, counseling, harm reduction etc conducted by MPSACS.

- Infrastructure of the organization

Infrastructure purchased through TI budget provided by MPSACS fund during change of the project in year 2012. Office is situated newly established township, office premises is rented building is at the ground floor with separate counseling room, separate PM/PD/Computer/accountant room. All the furniture’s are present at the office as purchased from MPSACS budget.  Furniture is available for running of TI project.  DIC is established in the Project office premises set up Colour TV with dish anteena.

- Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

TI is maintaining  Attendance register, Leave file, Accounts register, HRG line listing & registration register, Counseling, Condom stock register , STI,  Purchase & DIC meeting, referral register, N/S stock & distribution register etc. It was found that regularly send TI CMIS and STI CIMS to MPSACS as per SACS protocol.

- Program Deliverables

Outreach

- Line listing of the HRG by category.

592 HRGs Line listed till date as per Master register which is available at TI.

Sub-Groups and their Size

FSW- 147 & IDU-405 are active as on date.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

NA

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

NA

- Micro planning in place and the same is reflected in Quality and documentation.

The PM and other staff of the TI are not aware about the Hot spot wise micro plan which is required for TI project and which is reflected Condom demand, distribution, gap analysis, condom availability, supply analysis, referral to ICTC, RMC, VDRL etc have been planned  and documented. Form B and B1 available with TI which is not properly defined by the ORW.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

On an average contact 117 against target 150 among FSW,  contact- 183 target – 400 among IDU. Regular contacts done by the project with 2241 times among HRGs which is very less for twice in a month by PEs.

- Outreach planning – quality, documentation and reflection in implementation

Outreach planning is available which is verified at the hot spot level. Gap analysis has been found on condom distribution done as per the hotspots. Documentation is reflected in implementation. The TI staff is more focus in two specific activities like condom distribution and Needle syringe distribution.

- PE: HRG ratio,

Ratio is 1: 75 among FSW and 1: 40 among IDUas per NACO guideline.

Among IDU PE1:38, PE2:37, PE3:38, PE4:43, PE5:42, 37,45,44,and 41, FSW- PE1; 69, PE2; 78 HRG found as per record of TI which is less than 1:60 average. Among IDU the PE: HRG ratio is around 40.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

As data available at TI, peers are meet 86% HRG among  in a month and the peers are in contact with HRGs for condoms and other referral services, and it was found from their document like peers diary and tracking sheet. ORWs are meet HRGs as per PE requirement. ORW among FSW category visit weekly once to the field and she is previously work as PE.

- Documentation of the peer education

Peers are maintaining Peer dairy and present data in weekly review meeting, however it is found that planning process which is planned centrally at project office. STI, ICTC and other services are documented in B and B1 form which is printed at project office each PE wise.

- Quality of peer education- messages, skills and reflection in the community

FSW Peers are having knowledge on HIV  spread and condom is the solution for prevention of HIV.  The IDU PEs needs to be improve to provide services. Induction training / Harm reduction training to ORWs provided by MPSACS, but their knowledge is limited. In general PEs is in regular contact with the HRGs of their sites. The peers program knowledge skills are reflected in their working pattern. However, some time it is reflected the systems have become mechanical and sensitivity towards the finer points. They are able to motivate the HRGs for RMC, ICTC referrals and   condom use. But documentation is very poor.

- Supervision- mechanism, process, follow-up in action taken etc

Female ORW act as Counselor visit some times to field visit for family counseling and  the project service uptake.  PM planning & monitoring process is satisfactory for Advocacy, follow up and service delivery to target population. The referral register and OST register are regularly monitored by PM. PM is working in this project since 2014, that so he has no adequate knowledge on TI management. In supervision and monitoring point of view she is poor for visit site and advocacy with other stakeholder.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

STI clinic set up at project office for providing RMC and STI services to HRGs. HRGs are reached to Suraskhya clinic set up at DHH for RMC which is found during visit. It is found that the HRG’s are going to the Govt. hospital for HIV test and STI treatment. Due to non availability of Kits there were no treatment undergone timely. Dr.  Himesh Pathak joined as doctor, but he is regularly irregular in his job assigned by the TI.   It has been found through the records that no STI cases indentified in this project period.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

The basic medical equipment is available with the clinic. Networking clinic format & patient referral register maintained by ANM of TI in a regular interval. STI kits are not available within TI project as per record.

In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

NA

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

Referral slips, placed in a file typology wise at the TI. MPSACS provided STI Kits to TI . As all the medicinal kits are supplied from the SACS there is no system of procurement. Only system of procurement followed in N/S purchase. It is noticed that 3 party quotation purchase committee was formed l and process done in year 2012 & same agency supply N/S till date.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

45800  pcs condoms are available with TI as on date which was supplied recently by MPSACS. The condom distribution process is adopted by TI through ORW to PE to HRG and Outlet supply. Record of outlets stock not maintained separately and the distribution process needs to be updated. Distribution through DIC are not shows in the record, but there is no issue in the name of DIC from main condom stock register available with TI.

- No. of condoms distributed - No. of condoms distributed through different channels/regular contacts.

Condoms are distributed through the Peer educator through regular contact. Against the demand of 2013-14 D-98450 /S 96291 & 2014-15- D 55470/S 53200 condoms were distributed during period of 1st April to 23rd March-2015. It was noticed that approximately 90% distribution from the demand.

- No. of Needles / Syringes distributed through outreach / DIC.

No of needles Demand 120704 against Distribution- 99810 & syringes 52607 nos. demands, against Distribution of 43514 through outreach. 83559 needles & 42910 syringes returned by PEs in N/S exchange program.

- Information on linkages for ICTC, DOT, ART, STI clinics.

Establishing linkages with ICTC, STI  by NGO for referral & testing. As per the documents verified from referral slips at the ICTC and STI clinic at Dist Hospital  we came to know maximum general patients referral & accompanied for tested in the name of HRG.

- Referrals and follows up

Referrals cases mismatched when we verified referrals slips of ICTC & STD clinic records at Hospital.

Referred 310 &175 tested among FSW,  Referred 987 & 519 tested among IDU in 2013-14, Referred 175 and 175 tested among FSW,  Referred 554 and tested 483 among IDU at  ICTC and 6 and 8 among FSW,   5 & 6 among IDU received STI services.

- Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

There is no particular step undertaken by TI on Collectivization activities. There is no CBO/SHG formed since inception of the project..

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

,

As per TI record 160 DIC level meetings, 12 PMC meetings, 16 Crisis management meetings, 12 community events, 3 Health camps organized by TI during this project period for community participation.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

As per the interaction with the ICTC, & OST  at the Dist  hospitals the TI are regular contact with them. Counselors post are vacant at ICTC and only STI counselor are  cooperated to TI staff for tested cases with  documents.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

FSW-55 % & IDU- 61% tested at ICTC & STI. Minimum gap between referred & tested found as per record available with TI.

Support system developed with various stakeholders and involvement of various stakeholders in the project.

No Stake holders have been identified for support to project as per TI records.  It is suggested that system is developed with the stakeholders like police, Influential person and doctors for service linkages.

VII. Financial Systems and Procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication:

Form the perusal of records, it was observed that the guidelines issued by the SACS/ NACO have generally been followed by the NGO.

- Recommendations specified in Audit Report have to maintain double column cash book.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of  using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of  settling of advances before making further payments.

Examination of records on test check basis reveals that the payments are being generally made in accordance with the laid down system, i.e.

- Most of transactions have been made on credit due to insufficient fund in the account and entries made on journal vouchers after disbursed the fund by SACS then payment made.

- NGO is using printed serialized vouchers.

- Most of the payments has been paid by way of cheque.

- Separate bank account has been opened for project.

- All payments are made in accordance with the approved action plan

- All payments are approved by the Project Director.

- Fixed asset register is not maintained in proper manner but stock register maintained in properly.

- Systems of  procurement - Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

- During evaluation, . it is observed that purchase committee organized for purchases of needles and  syringes/drugs/fixed assets as well as quotation system followed but  L1,L2  system not followed by TI.

- Systems of documentation- Availability of bank accounts (maintained jointly),audit reports.

- Bank Reconciliation Statements (BRS) have been prepared both year.

- NGO has maintained a separate & jointly operated at local bank account for TI Project

- SOE has been submitted on time specified format provided by the SACS..

- Cheque register is  maintained for the year 2013-14 and 2014-15.

- All the payment made beyond of Rs. 250 by cheques accordance with the SACS guideline.

- Rent agreement not made for 2013-14 only verbally agreement.

- Balance Sheet and income & expenditure statement not made manually.

- Cheque no. 002105 issued but not cleared till date but also cheque return not physically shown on record.

- Fixed asset balance shown in the Balance Sheet as per Statutory audit report by Rs. 71066 but as per NGO fixed asset maintained on record by R. 68,168.

- Contract agreement with the vendor but TDS not deducted when the payment made of  (statutory compliance not done).

- Professional taxes are not deducted by the NGO.

VIII. Competency of the project staff

VIII a. Project Manager

Ms. Alka Dwivedi, has been working as Program Manager in the TI from   5th March 2014.  She is aware about TI project and acquired knowledge through the Induction, Refresher, Harm reduction & other Training through MPSACS. She has MSW in proffesionally. Knowledge level of the PM is poor in financial management, computerization and management of data. Knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, monitoring and field visit & advocacy initiatives etc.  Interpersonal skill is good, Very less command among the Staff , local influential person and HRGs.

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

Ms. Ranu Pandey joined as ANM from last 2nd February 2015. She has 10th standard  with ANM course which have no working knowledge on TI aspects.  She is aware of harm reduction and abscess mgmt. terminology and  knowledge on  STI and HIV. She was attending refresher training conducted by MPSACS just after joining. General medicine distribution register & Records maintained by her.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.

One ANM appointed for FSW,  IDU as per guideline.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc. Support plan needed for weak performance Peer.

There are two male ORWs and two female ORWs appointed as per budget allocation to the TI NGO. no recruitment process followed by the organization.  The ORWs are aware and trained in the subject and are having rapport with the HRG.. The Female ORW’s are not enough knowledge on job description and documentation and various aspects of the target indicators define for the outreach plan for the STI, RMC, ICTC, and BCC. PM are not support to ORWs for provide regular support to PEs in preparation of  micro plan as per weekly targets on project services.

VIII e. Peer educators

There are 12 peers selected for the project who are covering the registered 400 + 150 HRGs.( 2 for FSW & and  10 peers  for IDU community who are covering all HRG’s.

All peers are associated with the program. It is noticed that they are working around 3-5 KM distance from the project office at their own time period. It is difficult to monitoring by ORW & PM. There is no satisfactory monitoring strategy planned by TI. The ORWs are visited weekly once or as when required by PEs. Only five PEs received induction training regarding  program and HIV/ AIDS massage.

VIII f. Peer educators in IDU TI

Need improvement skill in information, testing, motivation, outreach and waste management among IDU peers regarding prioritization of hotspots. PEs is not aware about symptoms of STI, harm reduction and abscess management.

VIII g. Peer Educators in Migrant Projects

NA

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

NA

VIII i. M&E officer

Whether the M&E officer (FSW and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

There is one appointment post M & E cum accountant sanctioned from MPSACS for TI Project. The person was busy for accounts. He gives less priority in data management and update.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

During interaction with PEs & ORWs it was found that the Outreach activities is not reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff  is not found during interaction with PEs and ORWs at TI level.  All the activity proves the clarity of  plan, target and outreach monitoring.

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc. -	NA

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

During FGD with the HRG at different hotspots it was found that the HRGs were satisfied with the quality and delivery of the project services provided by the TI staff. It is further reflected by the TI as per their record more condoms distributed than demand.  No cases found on  STI and HIV in the target population. HIV positive were reported in the year among general population.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

The community participation is very low in project management such as various committees etc. which was not reflected in practice or meetings with HRGs. & stakeholders. DIC meetings are held with low frequencies HRGs. The community people are not participated in planning, implementation process.

XII.    Commodities

Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

Proper planning is not developed of each hotspot for condom, needle and syringes as per demand /distribution and gap analysis calculation. Method of calculation for needle & condom are followed by TI staff as per MPSACS guideline. There are not introduced Female condom and Social Marketing of condom in the TI program.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

Community members are mainly involved in the services which are provided by the TI.  Advocacy meeting organized by TI and it is not found in the monthly plan.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

No such evidence found during TI visit.

XV. Best Practices if any,

TI project engaged to the IDU HRGs in different cultural activities during local level Mela and festivals.

Annexure C

Confidential Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Pitambar Panda, TL | At/Po- Bhadrak Odisha, M- 9470390196 |
| Mr. N K Sinha, Program Expert | At/po-Ranchi, Jharkhand M-9431705895 |
| Mr. Sabbir Ansari, Financial expert | Ashoka garden, Bhopal M- 8871906863 |
| Mr. Rajeev Pandey Officials from SACS (as facilitator) |  |
| Name of the NGO: | Gram Sudhar Samiti |
| Typology of the target population: | FSW, IDU |
| Total population being covered against target: | FSW-150 & IDU-400 |
| Dates of Visit: | 25th& 26th March -2015 |
| Place of Visit: | Sidhi |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for continuation with specific input |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- Establish link between the micro plan and the outreach planning for proper execution. - Analysis of the existing information to make more comprehensive strategy to address the goal of the TI project - Keeping in view the performance of the organization, the target should be enhanced - The community members are required to be involved in planning, implementation and monitoring of the project. - PD involvement in TI project activities - More training to TI staff on project implementation - PO support needed on specific areas - Formation of SHGs /CBOs among the HRGs to make a cohesive approach to mitigate the HIV/AIDS vulnerability towards community.

| Name of the evaluators | Signature |
| --- | --- |
| Mr. Pitambar Panda , TL |  |
| Mr. N K Sinha, Consultant |  |
| Mr. Sabbir Ansari, CA |  |