Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

- Background of Project and Organisation:

GVM Established in 1998 With  the Objective to Promote education And health service to the Most vulnerable  in Chhindwara Dist. M.P. GVM Is A non political non partisan non religious and not for  profit development  organization working for improving the quality of  life of socially and economically backward communities of Chhindwara Dist.

- Name and address of the Organization :

Head Office:     GRAMIN VIKAS MANDAL

NEAR BAGGA TYRE

SHRIWASHTWA COLONY,

CHHINDWARA

Madha Pradesh

Project office:   GRAMIN VIKAS MANDAL,

Ward No 9

Chokimohalla,

Parasia

Madha Pradesh

o  Chief Functionary: G.C. MALVIYA

o  Year of establishment :1998

o  Year and month of project initiation: 01-10-2008

- Evaluation team : 	      Mr.P.Appa Rao(Team Leader),

Mr.Ajay Pratap Singh (External Evaluator)

Mr. CA Arun Kumar Rawat (Finance Evaluator)

o  Time frame : 21-03-2015 to 22-03-2015

Profile of TI

(Information to be captured)

o Target Population Profile: FSW / MSM / IDU / TG/TRUCKERS / MIGRANTS

|  | FSW |  |  | MSM |  |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Target Area | HB | SB | LB | Kothi | DD | TG |  |
| Pench East | 54 | 7 | 5 |  |  |  | 66 |
| Bai Pas,Rawanwada | 54 | 12 | 1 |  |  |  | 67 |
| Chhinda,Dhaliwada | 55 | 0 | 5 |  |  |  | 60 |
| Tek Mohalla ,Parasia | 62 | 10 | 3 | 40 | 10 |  | 125 |
| Shankargar,Dhala | 58 | 2 | 0 |  |  |  | 60 |
| Shankargar,Harrai,SHiddh Baba | 66 | 0 | 0 | 0 | 0 | 0 | 66 |
| 52 Quater-Umreth | 57 | 4 | 0 | 0 | 0 | 0 | 61 |
| B.G.Saiding,Kosmi | 62 | 0 | 2 | 0 | 0 | 0 | 64 |
| Basodi Mohalla,Nichi Lain | 52 | 8 | 0 | 0 | 0 | 0 | 60 |
| Indira Awas,Iklehra | 48 | 14 | 2 | 0 | 0 | 0 | 64 |
|  |  |  |  |  |  |  | 693 |

Type of Project: Core/ Core Composite / Bridge population

FSW & MSM (Core)

Size of Target Group(s)

FSW-600

MSM-50

Sub-Groups and their Size

| FSW |  |  | MSM |  |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- |
| HB | SB | LB | Kothi | DD | TG |  |
| 54 | 7 | 5 |  |  |  | 66 |
| 54 | 12 | 1 |  |  |  | 67 |
| 55 | 0 | 5 |  |  |  | 60 |
| 62 | 10 | 3 | 40 | 10 |  | 125 |
| 58 | 2 | 0 |  |  |  | 60 |
| 66 | 0 | 0 | 0 | 0 | 0 | 66 |
| 57 | 4 | 0 | 0 | 0 | 0 | 61 |
| 62 | 0 | 2 | 0 | 0 | 0 | 64 |
| 52 | 8 | 0 | 0 | 0 | 0 | 60 |
| 48 | 14 | 2 | 0 | 0 | 0 | 64 |
|  |  |  |  |  |  | 693 |

- Target Area

  - Pench East,

  - BaiPas,Rawanwada Chhinda,Dhaliwada

  - Tek Mohalla ,Parasia

  - Shankargar,Dhala

  - Shankargar,Harrai,SHiddh Baba

  - 52 Quater-Umreth

  - B.G.Saiding,Kosmi

  - Basodi Mohalla,Nichi Lain

  - Indira Awas,Iklehra

Key Findings and recommendations on Various Project

Components

- Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

- The evaluation team could not interact with TI Office bearers as NGO failed to arrange a meeting with them. Project Director only available to interact our evaluation team.

- Project director involvement is required for the NGO to do better results.

- Organizational Capacity

  - Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

  - HRG master raw data available.

  - Project Staff are in place as per proposal

  - Staff‘s understanding and knowledge about their role and responsibilities is to be improved.

  - Staff commitment to the project satisfactory.

  - Specific micro plan is not available.

  - Staff turnover is 33%.

  - Staff are well qualified

  - The number of new staff who joined in the last five months is two.

Staff details

| S.No. | Name of the Employee | Qualification | AGE | Designation | Date of Joining |
| --- | --- | --- | --- | --- | --- |
| 1 | UMASHANKAR PAWAR | M.S.W.,M.A.Sociology | 38 | P.M | 04/03/2010 |
| 2 | SAROJ PAWAR | M.S.W., | 35 | Counselor | 05/11/2014 |
| 3 | RAVI MARSKOLE | B.Com, MBA(Finance), | 31 | M&E | 02/01/2012 |
| 4 | JITENDRA GAJBHIYE | M.S.W.,M.A.Sociology | 38 | ORW-1 | 29/10/2008 |
| 5 | MITHLESH NAGIYA | B.A. | 42 | ORW-2 | 25/02/2014 |
| 6 | KU. NITEE DHAKRE | M.A. ECONOMICES | 30 | ORW-3 | 05/11/2014 |

Staff turn over

| Name of the staff | Designation | Date of Joining | Date of leaving |
| --- | --- | --- | --- |
| UMASHANKAR PAWAR | P.M | 04/03/2010 |  |
| RATNAMALA- Couns.1 | Counsellor | 20/05/2011 | 14/08/2013 |
| GEETA DHURVE-Couns.-2 | Counsellor | 23/08/2013 | 19/09/2014 |
| SAROJ PAWAR-Couns-3 | Counsellor | 05/11/2014 |  |
| DEEPMALA-ORW-1 | ORW | 20/05/2013 | 20/02/2014 |
| MITHLESH NAGIYA-ORW-2 | ORW | 25/02/2014 |  |
| RAVI MARSKOLE | M&E | 02/01/2012 |  |
| JITENDRA GAJBHIYE | ORW | 29/10/2008 |  |
| KU. NITEE DHAKRE | ORW | 05/11/2014 |  |

  - Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

- Improvement needs for a visible staff capacity building as per the requirement at project

- Documentation of the training programs is available, but quality is average.

| Period of April 2013 to March 2014 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S No |  | Name of the Training |  |  | Trained by | Type of Training |  | Staff attended |  | Designations |  |  |
| 1 |  | Primary Training |  |  | P.M | ORW Tools & Role & Resposibility |  | Deepmala,jitendra |  | ORW’s |  |  |
| 2 |  | Primary Training |  |  | P.M | ORW Tools & Role & Resposibility |  | Geeta Dhurve |  | Counselor |  |  |
| 3 |  | Refresher |  |  | MPSACS | SIMs |  | Umashanaker pawar,Ravi Marskole |  | P.M. , Accountant |  |  |
| 4 |  | Induction |  |  | MPSACS | STI Mangt. |  | Geeta Dhurve |  | Counselor |  |  |
| Period of April 2014 to March 21st 2015 |  |  |  |  |  |  |  |  |  |  |
| S No |  | Name of the Training | Trained by |  |  | Type of Training |  | Staff attended |  | Designations |
| 1 |  | Primary | NGO |  |  | ORW & Counselor Tools & Role & Resposibility |  | Neeti Dhakre,Saroj Pawar |  | ORW, Counselor |
| 2 |  | Induction | BSSS |  |  | STI Mangt. |  | Saroj Pawar |  | Counselor |
| 3 |  | Induction | BSSS |  |  | M &E & Finance |  | Ravi, G.C. Malviya |  | M&E, P.D. |

  - Infrastructure of the organization

- The Organization has adequate infrastructure and working space. They have a well equipped DIC in the same premises. Office location is accessible to HRG’s .  Assets are in place and properly codified.

  - Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if an

- With the support of Outreach workers, Peer educators are maintaining Form B.

- The Outreach workers maintain daily diaries.

- Availability of documents is moderate.

- Mechanism of review is satisfactory.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

- HRG’s master register is available.

- HRG’s UID Numbers are matching with Out Reach team data available

- Line listing is in place

- Specific micro plan is not available.(Weekly plans are available)

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

................Not Applicable .......

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

................Not Applicable .......

- Micro planning in place and the same is reflected in Quality and documentation.

- Knowledge level on Micro plan is yet to be improve at the grass root level.

- Individual tracking of HRG’s is need to be improve.

- Maximum PE’s are uneducated their tracking register is written by ORWs.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

- 67% of HRG’s covered in a month by Out Reach team.

- FGD meetings are conducted documentation is satisfactory.

- Display in DICs is satisfactory.

- The NGO is yet to reach the key population who are at high risk also NGO need to carry out the hot spot saturation at key hotspots to reach all the target population in the area.

|  | FSW |  |  | MSM |  |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Target Area | HB | SB | LB | Kothi | DD | TG |  |
| Pench East | 54 | 7 | 5 |  |  |  | 66 |
| Bai Pas,Rawanwada | 54 | 12 | 1 |  |  |  | 67 |
| Chhinda,Dhaliwada | 55 | 0 | 5 |  |  |  | 60 |
| Tek Mohalla ,Parasia | 62 | 10 | 3 | 40 | 10 |  | 125 |
| Shankargar,Dhala | 58 | 2 | 0 |  |  |  | 60 |
| Shankargar,Harrai,SHiddh Baba | 66 | 0 | 0 | 0 | 0 | 0 | 66 |
| 52 Quater-Umreth | 57 | 4 | 0 | 0 | 0 | 0 | 61 |
| B.G.Saiding,Kosmi | 62 | 0 | 2 | 0 | 0 | 0 | 64 |
| Basodi Mohalla,Nichi Lain | 52 | 8 | 0 | 0 | 0 | 0 | 60 |
| Indira Awas,Iklehra | 48 | 14 | 2 | 0 | 0 | 0 | 64 |
|  |  |  |  |  |  |  | 693 |

- Outreach planning – quality, documentation and reflection in implementation

- Staff diaries are  written in proper and satisfactory

- Monthly staff meetings minutes available.

- Condom gap analysis is not appropriate with regards to KPs needs.

- PE: HRG ratio, PE:migrants/truckers

- The PE:HRG ratio was maintained as 1:60 as per the records.

- 3 ORW’s and 11 PE’s in place at the time of visit by the team.

- All ORW’s & Peer Educators are attended while evaluation team interacted with them.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

- Regular contacts made by OR team on weekly basis is need to improve.

- There is good coordination among staff members.

- PEs have good rapport in the community

- Documentation of the peer education

- PEs documentation is done by ORWs on weekly basis.

- Most of the PEs are uneducated, though their project understanding levels are high.

- The formats provided by SACS are maintained and regularly reviewed by PM .

- Documentation needs improvement.

- Quality of peer education- messages, skills and reflection in the community

- The peer educators were actively involved in the minimal outreach they were doing. They referred to ICTC center and STI clinic at government hospital regularly.

- Most of the PEs is above 30 years age. All the PEs belongs to the category of home based and street based. There is a variation in the information and skills of PEs. The terminology, method followed varies and the knowledge levels are not the same. Overall the PE reflection in the community, especially with home based HRG is satisfactory.

- PEs  are keeping enough condoms stock with them

- Most of the PE’s are illiterate. They are using flip charts provided under the project for BCC. It’s recommended to conduct a refresher course on BCC to all PEs to better their present level of performance.

- In weekly meetings of PEs sessions on basic reading, writing and learning skills for one hour helps to record and asses their work.

- Supervision- mechanism, process, follow-up in action taken etc

- HRG tracking for clinic is to be improved.

- A system of regular monitoring and supervision based on Targets and actual achievement need to be inculcated among PM and PD initially and then ORWs

- MIS officer and Counselors need to take proactive involvement in monthly / weekly review meetings.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

- All the cases are referring to the Govt Hospital including RMC

- There is no static clinic at DIC.

- No health camp was conducted by the Organization.

- There is proper referral system adopted.

- Follow up of STI are satisfactory.

- Case studies are not documented by Counselor.

- The referral slips are maintained.

- The staff is not well trained on the procedure to be followed.

- The data in MIS need to be cross-verified.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- There is no Static clinic for Project

- No PPP Clinic are build-up it is very much important

- RMC cases referring to the government hospital.

- There is no availability of STI Kits in Govt hospital Parasia , Govt hospital Chandameta and PHC Umreth.

- VDRL tests are not happening in Govt hospital

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

................Not Applicable .......

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

- Follow up mechanism adopted and it is satisfactory.

- Referrals to service providers are satisfactory but there is no supportive documentation done.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- STI registers are maintained.

- Clinic registers are documented in proper manner.

- STI kits are not available in the govt hospitals

- Following stock registers are maintained as per SACS format.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- 10 Condom manned outlet are available in different hot spots

- Outreach team distributes condoms to the community without any planning.

- Condom Gap analysis is to be done for effective supply of the condoms to the HRG as per their need.

- The condom stock is maintained properly according to plan.

- The condom boxes should fix permanently in the hotspots

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

April 2013 to March 2014

- Demand:164400

- Distribution: 126025

April 2014 to March 2015

- Demand:172800

- Distribution :85380

- There is no condom supply from MPSACS in the period june 2014 to oct 2014

- No social Marketing

- No. of Needles / Syringes distributed through outreach / DIC.

................Not Applicable .......

- Information on linkages for ICTC, DOT, ART, STI clinics.

- Out of 839  hiv testings 286 are went twice inApril 2013 to March2014

- Out of 1176  hiv testings 432 are went twice in April 2014 to March2015

- Community accessing linkages services is low.

- The TV in the DIC is not working.

- Referrals and follows up

- Referrals and follows ups with Govt. hospitals are need to improve.

- Referral and follow ups are documented, but need to be improve.

- ORWs, PEs and counselors need to co-ordinate to work out a plan.

- Referral is carried out in planed manner.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- There is no  CBOs  registered

- Community involvement is very poor

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community participation in all the events and programs is very poor.

- There is good support for the project from the community.

- Community participation in project activities is not satisfactory.

- DIC attendance is not up to mark

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

TI established linkages with STI, ICTC, TB and ART. TI need to strengthened with these service providers.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

April 2013 to march 2014  73%

April 2014 to march 2015  75%

Gap between referred and tested

26% is the gap in ICTC testing.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- Project need to be established with the stakeholders.

VII. Financial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

- System of planning has according to NGO.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

- All Vouchers are printed and serialized found during evaluate of Voucher File.

- Bill/Vouchers are Properly verified by PD/PM and Seal &Sign of  PD/PM is also found in vouchers.

- Stock and Fixed assets register is also maintain by TI.

- No any Advance given by TI any payments has been made after fund received by TI.

- Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

- No any Assets and Drugs are purchased during financial year 2013-2014 and 2014-2015.So no any system was found for purchasing of Drugs/Assets by TI.

- No any Quality check is found during evaluation.

- Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

- NGO/TI has been operate separate bank account for this project in Bank of Maharashtra Parasia-Chindwada branch and Bank Account No. is 60015630553 as saving account.

- Bank Account has operate by two person one President as well as Secretary of NGO.

- Bank account reconcile on yearly basis not monthly basis.

- Cash Book and Ledger are physically maintained by NGO for this project.

- Audit has been done on regular  basis.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

- Project Manager is well experienced in TI Project, he is post graduate (M.S.W.,M.A.Sociology)  with computer skills. He needs to improve on program performance indicators, advocacy initiatives.though the project is old since 2010 he use initiate the community to build as CBO.

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

- Counsellor is Post Graduate (MSW), and she involved in field visits to the hotspots to provide counseling, maintain records, linkages etc. She is a hard worker and committed to work for the Project.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.For ANM, adequate abscess management skills.

................Not Applicable .......

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

- All the 3 ORW’s are in place as per the sanction made by NACO/SACS, they are educated. They know the outreach protocols, and capable of providing the support for the Peer Educators at the hotspot level.

- ORW’s  knowledge on documentation and outreach skills need to be capacitated for the better implementation of the program.

- Two ORW’s are not trained. There should be  proper induction training by MPSACS

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

- As Peer Educator turnover is witnessed (out of 11 PE's 1 turnover is noticed), and most of the peer educator are more than 30 years of age.

- Present PE’s field work is average as per the FGD, and need to be improved.

- PE’s have condom demonstration skills, they need training for skill development.

- They have good knowledge about the STI symptoms.

- There is a need to shine them in their roles and responsibilities.

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

................Not Applicable .......

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritise the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

................Not Applicable .......

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

................Not Applicable .......

VIII i. M&E officer

Whether the M&E officer ( FSW and MSM/TG TIs with more than 800 population and all migrant Tis are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

- M&E officer is a post graduate with computer knowledge and he is well experience to the project. He is dedicated and willing to work in the project.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- Micro plans are not available

- ICTC referrals to be improved

- Field level monitoring and cross check by ORW’s and PM to be done

- There is a need to capacity build the OR team for effective outreach

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

..............Not Applicable .......

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- DIC services are need to improve

- Condoms reaching to HRG’s are not up to mark.

- Need to keep condom outlet boxes in hotspots.

- Referrals and follow up documentation need to improve.

- VDRL tests are not happening due to lack of kits in govt hosipital

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- As the TI is focusing various committees are being formed like Project Advisory Committee, Advocacy committee, DIC Committee but there is no documentation and they need to be strengthened documentation and involving the Community.

- Involvement of community in events is very minimal.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

- Condoms are not distributing according to condom gap analysis.

- HRG’s are not aware of their condom demand.

- Need to keep condom outlet boxes in hotspots

- There is no distributed through Social marketing against demand, and it need to be improve.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services

etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

- TI is not documenting advocacy register.

- TI need to conduct advocacy programs with police department, Govt. Hospital doctors, RTC department, Revenue department and social welfare department.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- TI is not established social protection schemes like with social welfare department, Revenue department, SC,BC welfare department etc.,

XV. Best Practices if any

Confidential

Annexure C

Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| P.Appa Rao(Team Leader) | 9951282028 |
| Mr.Ajay Pratap Singh (External Evaluator- II) | 07398982415 |
| Mr. CA Arun Kumar Rawat (Finance Evaluator) | 09755871561 |
| Officials from SACS/TSU (as facilitator) | Mr. Mukesh Jatav (9039027354) |

| Name of the NGO: | GRAMIN VIKAS MANDAL - Chhinadawada |
| --- | --- |
| Typology of the target population: | FSW &MSM |
| Total population being covered against target: | 600 FSW + 50 MSM =650 |
| Dates of Visit: | 21-03-2015 to 22-03-2015 |
| Place of Visit: | GRAMIN VIKAS MANDAL, Ward No 9 Chokimohalla, Parasia, Madha Pradesh |

Overall Rating based programme delivery score:  59.1%

| Total Score Obtained (in %) | Category | Category; Rating. | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for continuation with periodical monitoring |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- Two ORW’s are new they need training for better results. - More Peer Educators are above age 30 years they need to change and should be give chance to others who are well educated and young. - Staff documentation and communication skills to be improved. - Need to improve strong linkages with the external stakeholders. - More involvement of PD in providing, motivation, capacity building of the staff is very required. - The NGO must establish CBO since it is working from 2010 - Community involvement is very poor it should be develop by NGO staff - NGO need to linkage with ppp clinic and establish ppp clinic with immediate effect. - Documentation needs to be improved - Referrals to ICTC, DOT, and RMC to be improved. - Reconciliation of Bank account has been done on yearly bases it should be done on monthly bases.

| Name of the evaluators | Signature |
| --- | --- |
| P. Appa Rao (Team Leader) |  |
| Mr. Ajay Pratap Singh (External Evaluator- II) |  |
| Mr. CA Arun Kumar Rawat (Finance Evaluator) |  |