Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

- Background of Project and Organisation:

Jabalpur Vavsayik Prashikchan & Samaj Kalyan Samiti (J.V.P.S.K.S.) which is virtualy means jabalpur vocational training & social welfare society Was Established  & Registered Under The Madhya Pradesh Society Registration Act 1973 Sec 44(1).The Registration Number Is J.J.-2989  (08-10-1996)With The Noble Vision Of Imparting Enriched Quality Of Education, Situated At The Prime Location Of Jabalpur, (JDA Building Plan No.19 ,Four Lane NH-7/NH-12 Madan Mahal Chowk Jabalpur Madhya Pradesh-482001).

Name and address of the Organization :    Jabalpur Vyasayik Pracikhan Evam samaj Kalyan samiti

Jarjola Road

Paras Vihar Colony

Near Finix School

Narsinghpur

Cotact No-07792-230065 Mob.No- 9981657766

Chief Functionary: Dr. Prashant Kourav

Year of establishment : 1996

Year and month of project initiation: 01 July 2010

Evaluation team : 	      Mr.P.Appa Rao(Team Leader),

Mr.Ajay Pratap Singh (External Evaluator)

Mr. CA Arun Kumar Rawat (Finance Evaluator)

Time frame : 25-03-2015 to 26-03-2015

Profile of TI

(Information to be captured)

o Target Population Profile: FSW / MSM / IDU / TG/TRUCKERS / MIGRANTS

Type of Project: Core/ Core Composite / Bridge population

IDU

Size of Target Group(s)

Sub-Groups and their Size

- Target Area

Key Findings and recommendations on Various Project

Components

- Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

- Interacted with project director and society members. In the feedback we expressed those society members as to established contact with the social welfare departments and need advocacy with the external stake holders, and to construct project advisory board to strengthen the TI.

- Organizational Capacity

  - Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

- All staff is as per project proposal.

- Three staff members who joined in the last five months.

- Reporting pattern is need to be improved.

- Supervision of PEs is carried out by ORWs need to be improve.

- Project Manager as to establish regular supervision with PE’s ORW’s and ANM to strengthen the projects. He has to establish rapport with the line departments.

- The supervisions are not structured and the findings and actions taken are not reported in review meetings.

- Staff understanding  & knowledge is need to improve

Staff Turn Over

| Name of the staff | Designation | Date of Joining | Date of leaving |
| --- | --- | --- | --- |
| Smt. Shusma Chouarsiya | FORW | 11/11/2014 | 23/01/2015 |

| PEER’S turn over-2013-2015 |  |  |
| --- | --- | --- |
| Name of PEERS | Designation | Date of Joining | Date of leaving |
| 1 Mujeeb Khan | PE | 01/11/2010 | 30/09/2014 |
| 1(A) Bhanu Vishkarma | PE | 30/11/2013 | 31/01/2015 |
| 1(B) Mujeeb Khan | PE | 01/02/2015 | Continue |
| 2 Abid Khan | PE | 01/01/2012 | 30/04/2013 |
| 2(A) Jeewan Lal | PE | 01/05/2013 | 31/07/2013 |
| 2 (A) Rajesh Noriya | PE | 01/08/2013 | Continue |
| 3 Neelesh Yadav | PE | 01/02/2013 | Continue |
| 4 Gopal Mehra | PE | 01/11/2010 | 30/11/2013 |
| 4(A) Shivraj Thakur | PE | 23/09/2011 | 28/02/2014 |
| 4(B) Gopal Mehra | PE | 01/03/2014 | Continue |
| 5 Ashish Yadav | PE | 01/04/2011 | 30/11/2012 |
| 5(A) Abhishek | PE | 01/12/2012 | 28/02/2013 |
| 5(B) Krishn Kumar | PE | 01/03/2013 | 30/06/2013 |
| 5(C) Tamrej Ali | PE | 01/07/2013 | 30/09/2013 |
| 5(D) Ashish yadav | Pe | 01/04/2011 | Continue |
| 6 Ujiyar Rajak | PE | 01/11/2010 | 30/08/2013 |
| 6(A) Shek Raseed | PE | 01/10/2013 | 30/05/2014 |
| 6(B) Ashish Kahar | PE | 01/06/2014 | 31/12/2014 |
| 6(C) Ujyar Rajak | PE | 01/11/2010 | 01/01/2015 Continue |
| 7 Ajay Gujar | PE | 02/04/2011 | 30/06/2013 |
| 7 (A) Radheshyam Patwa | PE | 01/07/2013 | 28/02/2014 |
| 7 (B) Mohan Singh | PE | 01/03/2014 | 30/09/2014 |
| 7 (C)Mahendra jatav | PE | 01/10/2014 | Continue |
| 8 Surkant sharma | PE | 01/11/2010 | Continue |
| 9 Narmda Prasad | PE | 01/09/2011 | Continue |
| 10 Sachin Raghuvaci | PE | 01/03/2011 | 30/06/2013 |
| 10 (A) Ashish Thakur | PE | 01/07/2013 | 30/03/2014 |
| 10 (B) Arun Soni | PE | 01/04/2014 | Continue |
| 11 Kamlesh Vishkarma | PE | 01/02/2013 | 30/06/2013 |
| 11(A) Shek Shahid | PE | 01/07/2013 | 28/02/2014 |
| 11 Arun Thakur | PE | 01/03/2014 | Continue |
| 12 Salman Khan | PE | 01/09/2011 | Continue |
| 13 Teekram jatav | PE | 01/09/2011 | Continue |
| 14 Rohit Mahar | PE | 01/04/2013 | 28/02/2014 |
| 14(A) Anish Jat | PE | 31/01/2014 | 31/03/2014 |
| 14(B) Rishi Namdev | PE | 01/04/2014 | 30/04/2014 |
| 14(C) Dharmendra yadav | PE | 01/05/2014 | 30/09/2014 |
| 14(D) Rohit Mahar | PE | 01/10/2014 | Continue |
| 15 Najeer Khan | PE | 01/12/2012 | 31/03/2014 |
| 15(A) Rahul Nema | PE | 01/03/2014 | Continue |

Staff details

| S.No. | Name of the Employee | Qualification | AGE | Designation | Date of Joining |
| --- | --- | --- | --- | --- | --- |
| 1 | Pradeep Sahu | MSW MA Sociology | 29 | PM | 01/02/2013 |
| 2 | Atul Nema | B.Com MSW | 25 | A/C Cum M&E | 14/05/2012 |
| 3 | Yogendra jatav | MSW | 34 | Counsellor | 01/12/2014 |
| 4 | Atul Jat | BAMS | 33 | ANM | 01/12/2014 |
| 5 | Ranjeet Noriya | 8 th standard Community | 31 | ORW | 12/05/2012 |
| 6 | Jannu Beg | 8 th Standard Community | 28 | ORW | 01/02/2013 |
| 7 | Sailendra Jat | MA Sociology | 30 | ORW | 01/12/2014 |
| 8 | Ku. Lalita sen | BSc | 22 | FORW | 23/11/2014 |
| 9 | Smt. Jyoti Pandey | BA | 32 | FORW | 23/01/2015 |

  - Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

- Micro planning done and is need to implemented effectively.

- Documentation needs improvement.

- Quality of training materials is average.

| Period of April 2013 to March 2014 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S No |  | Name of the Training |  |  | Trained by | Type of Training |  | Staff attended |  | Designations |  |  |
| 1 |  | Co-morbidity |  |  | Hifajat RTTC | Induction |  | Atul Jat |  | Counsellor |  |  |
| 2 |  | OST |  |  | Aimms | Induction |  | Ranjeet Noriya |  | ORW |  |  |
|  |  |  |  |  |  |  |  | Jannu Beg |  | ORW |  |  |
| 3 |  | Harm Reduction |  |  | Kalyani Orgnasaiton | Induction |  | Yogendra jatav |  | ORW |  |  |
|  |  |  |  |  |  |  |  | Jannu beg |  | ORW |  |  |
| 4 |  | Harm Reduction |  |  | Kalyani Orgnasaiton | Induction |  | Suryakant |  | PE |  |  |
|  |  |  |  |  |  |  |  | Radheshyam patwa |  | PE |  |  |
|  |  |  |  |  |  |  |  | Gopal mehra |  | PE |  |  |
| 5 |  | Harm Reduction |  |  | STRC Samartan | Refresher Training |  | Pradeep sahu |  | PM |  |  |
| 6 |  | Harm Reduction |  |  | Kalyani Orgnasation | Induction |  | Mujeeb Khan |  | PE |  |  |
|  |  |  |  |  |  |  |  | Suraj Noriya |  | PE |  |  |
|  |  |  |  |  |  |  |  | Tamrej Ali |  | PE |  |  |
|  |  |  |  |  |  |  |  | Dharmendra |  | PE |  |  |
| 7 |  | SIMS |  |  | SACS | Refresher |  | Pradeep sahu |  | PM |  |  |
|  |  |  |  |  |  |  |  | Dr Prashant Kouraw |  | PD |  |  |
| 8 |  | HRH Validation |  |  | SACS | Induction |  | Pradeep sahu |  | PM |  |  |
|  |  |  |  |  |  |  |  | Jannu beg |  | ORW |  |  |
| 9 |  | Harm Reduction |  |  | Kalyani Orgnaisation | Induction |  | Narmda Jatav |  | PE |  |  |
|  |  |  |  |  |  |  |  | Mhendra sing |  | PE |  |  |
| 10 |  | Harm Reduction |  |  | Kalyani Orgnaisation | Induction |  | Teekram |  | PE |  |  |
|  |  |  |  |  |  |  |  | Papupu Mehra |  | PE |  |  |
|  |  |  |  |  |  |  |  | Ghansyam |  | PE |  |  |
| 11 |  | Harm Reduction |  |  | Kalyani Organation | Refresher |  | Ranjeet NOriya |  | ORW |  |  |
| Period of April 2014 to March 21st 2015 |  |  |  |  |  |  |  |  |  |  |
| S No |  | Name of the Training | Trained by |  |  | Type of Training |  | Staff attended |  | Designations |
| 1 |  | Harm Reduction | RTTC Munbai |  |  | Refresher |  | Dr. T R Dhingra |  | PPP |
| 2 |  | Harm Reduction | Kalyani Orgnasation |  |  | Refesher |  | Yogendra Jatav |  | ORW |
|  |  |  |  |  |  |  |  | Jannu beg |  | ORW |
| 3 |  | OST | Aiims |  |  | Refesher |  | Pradeep sahu |  | PM |
|  |  |  |  |  |  |  |  | Atul jat |  | Counsellor |
|  |  |  |  |  |  |  |  | Yogendra jatav |  | ORW |
|  |  |  |  |  |  |  |  | Jannu beg |  | ORW |
| 4 |  | Harm Reduction | Kalyani Organsation |  |  | Refesher |  | Mujeeb Khan |  | PE |
|  |  |  |  |  |  |  |  | Gopal Mehra |  | PE |
|  |  |  |  |  |  |  |  | Rajesh Noriya |  | PE |
|  |  |  |  |  |  |  |  | Tamrej Ali |  | PE |
|  |  |  |  |  |  |  |  | Narmda Prasad |  | PE |
|  |  |  |  |  |  |  |  | Mahendra sing |  | PE |
| 5 |  | Harm Reduction | Kalyani Organsation |  |  | Induction |  | Pradeep sahu |  | PM |
| 6 |  | Harm Reduction | Kalyani Organsation |  |  | Induction |  | Yogendra jatav |  | Counsellor |
| 7 |  | Harm Reduction | Kalyani Orgnaisation |  |  | Induction |  | Sailendra jat |  | ORW |
|  |  |  |  |  |  |  |  | ku. Lalita sen |  | FORW |
|  |  |  |  |  |  |  |  | SMt. Jyoti pandey |  | FORW |

  - Infrastructure of the organization

- Infrastructure of NGO is satisfactory

- Building is at residential area and accessibility is comfort to HRG

- DIC is in the same office

- DIC room should be privacy

- Assets are in place and codified as per guidelines.

  - Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any

- Availability of documents is moderate, is need to be improve.

- Display of various activities conducted is done.

- Mechanism of review is needed to be improved.

- As for the SACS all formats are maintaining.

- All clinic records maintained up to mark.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

- HRG master raw data available.

- Line listing is in place

- Specific outreach/activity plan is available.

- Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

................Not Applicable .......

- Registration of truckers from 2 service sources i.e. STI clinics and counseling.

................Not Applicable .......

- Micro planning in place and the same is reflected in Quality and documentation.

- The Micro planning is reflecting in Clinical services and documentation.

- Knowledge level on Micro plan is yet to be improved at the grass root level.

- PE’s tracking register is written by ORWs.

- Individual tracking of HRG’s is needed to be improved.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

- 80% of HRG’s covered in a month by Out Reach team as per record but there is need to give more services as practically.

- FGD meetings are conducted but documentation is needed to be improved.

- Display in DICs is satisfactory.

- The TI is yet to reach the key population who are at high risk.

- PE’s and ORW’s have to contact HRG’s regularly.

- Outreach planning – quality, documentation and reflection in implementation

- Staff diaries are maintained.

- Monthly staff meetings minutes available.

- Condom gap analysis is not appropriate and need to be improved.

- PE: HRG ratio, PE:migrants/truckers

- There are 15 peer educators as per proposal. Out of 15 peer educators 08 Peer Educators are present at the time of meeting, and 1 peer educator is available in field at the time field visit.

- Total 09 Peer Educators are  available at the time evaluation team visit

- Averagely 1:40 are maintaining.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

- Regular contacts by Out Reach team are needed to be improved.

- PEs documentation is done by ORWs on weekly basis.

- PEs rapport in the community is not satisfactory there is need to enhance knowledge levels.

- PM is needed to conduct regular capacity building to PE’s and ORW’s

- The formats provided by SACS are maintained and regularly reviewed by PM .

- Documentation needs  improvement.

- Documentation of the peer education

- ORW’s are need to improve liaison with the line departments.

- Peer educators meetings minutes available.

- The formats provided by SACS are maintained.

- They referred HRG’s to ICTC center and OST center regularly. Referrals are  available in the ICTC  and OST center

- Quality of peer education- messages, skills and reflection in the community

- There is a variation in the information and skills of PEs. The terminology, method followed varies and the knowledge levels are not the same.

- Overall the PE reflection in the community not satisfactory.

- PEs  are not  keeping enough commodities  with them

- It’s recommended to conduct a refresher course on BCC to all PEs to better their present level of performance.

- In weekly meetings of PEs sessions on basic reading, writing and learning skills for one hour helps to record and asses their work

- Supervision- mechanism, process, follow-up in action taken etc

- Monitoring system is satisfactory. The daily dairies are maintained by PEs and ORWs are satisfactory

- HRG tracking for clinic is to be improved.

- A system of regular monitoring and supervision based on Targets and actual achievement need to be inculcated among PM and PD initially and then ORWs

- ANM, MIS officer and Counselor need to take proactive involvement in monthly / weekly review meetings

- Documentation is satisfaction and it is not reflected in the field.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

- There is static clinic at DIC.

- Referral system needs to be improved.

- Follow up of STI are not satisfactory.

.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Static clinic is in place as per NACO guidelines

- All the clinic equipment is in place as per protocols

- Clinic is in  TI office premises

- STI drugs are procured and maintaining record

- Privacy in the clinic is as per Static clinic protocols.

- ANM has experience of working in TI project,

- Counsellor skills in counselling needs build up.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

................Not Applicable .......

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

- Referral system is established with ICTC, ART, DOTS centers.

- Treatment is done according to SCM protocols.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable-mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- STI registers are maintained, referral slips are need to be document properly.

- Clinic registers are documented in proper manner.

- STI stock is tallying with Stock register.

- Following stock registers are maintained-condom register, patient medicine stock register as per SACS format.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- 30 Paper outlet boxes fix at hot spots. But it is  available  for HRG’s less

- Outreach team distributes condoms to the community without any planning.

- Condom Gap analysis is to be done for effective supply of the condoms to the HRG as per their need.

- The condom stock is not maintained according to plan.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

April 2013 to march 2014 -10616

April 2014 to march 2015 -298395

- No. of Needles / Syringes distributed through outreach / DIC.

April 2013 to march 2014 –63511(3ml)

21600(5ml)

April 2014 to march 2015 -106289(3ml)

41500(5ml)

- Information on linkages for ICTC, DOT, ART, STI clinics.

April 2013-March 2014.

| RMC | 0 |
| --- | --- |
| RPR | 456 |
| ICTC | 1081 |
| TB | 0 |
| STI | 988 |
| HIV POSITIVE | 0 |
| ART | 0 |

April 2014-Dec. 2015.

| RMC | 0 |
| --- | --- |
| RPR | 639 |
| ICTC | 1030 |
| TB | 0 |
| STI | 916 |
| HIV POSITIVE | 0 |
| ART | 0 |

- Referrals and follows up

- Referrals and follows ups with Govt. hospitals are need to improve.

- Referral and follow ups are documented, but need to be improve.

- ORWs, PEs and counselors need to co-ordinate to work out a plan.

- Referral is carried out in planed manner.

- At present the referrals are carried out with ORW’s

- PEs outreach is yet to cover all the registered HRG’s.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- There is no CBO formation

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- There is no active participation in TI programme.

- Community participation in project activities is satisfactory.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkage are established with govt hospital assess isgood

- Percentages of HRGs tested in ICTC and gap between referred and tested.

30% gap between referred and tested.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

Stakeholders and involvement of various stakeholders in the project is satisfactory.

VII. Financial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

- System of planning has existence during TI evaluation.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

- All payments  has been made with  bill/vouchers

- All Vouchers are printed and serialized number.

- Bill/Vouchers are approved by PD.

- Stock and Fixed assets register is also maintain by NGO in respect of  TI project.

- NGO has  purchased drugs/Needles/Syringe during FY 2013-2014 and 2014-2015 but not Call three quotation & compare chart procedure and also not verified by purchasing committee.

- Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

- NGO has  purchased drugs/Needles/Syringe during the  FY 2013-2014 and 2014-2015 but not Call three quotation & compare chart procedure and purchasing  is not also verified by purchasing committee.

- No any system  is  found of  quality check.

- Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

- NGO/TI has been operate separate bank account for this project in Bank of India Narsinghpur branch and it Bank Account No. is 943610110000521 as saving account.

- Bank Account has operated by two people one President as well as Secretary of NGO.

- Bank account not timely reconciles.

- Cash Book and Ledger are physically maintained by NGO for this project.

- Audit has been done on regular  basis.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

- Project Manager is a postgraduate in MSW MA Sociology

- He is experienced and had trained in TI project under SACS.

- His monitoring levels with the staff and HRG is moderate.

- He conducts monthly meetings, staff review meetings, and hotspot meetings. But there is no evidence based meetings

- Documentation need to improve

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

................Not Applicable .......

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments.For ANM, adequate abscess management skills.

- Counsellor is a qualified MSW

- He has experience in TI project he is promoted from ORW’s to counsellor

- He need more skills to conduct the counselling sessions

- He keeps good documentation.

- ANM is a qualified BAMS

- He has experience in ANM

- He keeps good documentation.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

- 5 ORW’s are in place.

- Out of 5 ORW’s 3male and 2 female

- 2 male outreach workers are from community, remaining ORW’s are non community

- Their community mobilization is not up to the mark.

- Their support to the PE’s at the hotspot level is moderate.

- Female outreach workers are counselling family without any counselling qualification.

- Their knowledge levels need to improve

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

................Not Applicable .......

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

- Out 15 peer educators 09 peer educators are observed by the evaluation team.

- Their hotspot level work done is need to improve.

- As huge turnover is noticed.

- There is a need of trainings to Peer Educators to enhance their knowledge and Out Reach skills.

- Peer Educators are distributing commodities without planed manner.

- Distribution of Needle and Syringes are not observed in the field at the time of field visiting.

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritise the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

................Not Applicable .......

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

................Not Applicable .......

VIII i. M&E officer

Whether the M&E officer ( FSW and MSM/TG TIs with more than 800 population and all migrant Tis are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

- He is qualified commerce graduate with computer knowledge

- His qualification is Bcom with MSW

- He is having  3yr experienc to the program

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- Micro plans are in place, but the evidence based work done by the Outreach team is not satisfactory.

- Outreach workers and PE’s need knowledge in all components.

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

..............Not Applicable .......

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- Medical services in the Static clinic run by TI are satisfactory

- DIC services are satisfactory

- Commodities reaching to HRG’s are not up to mark.

- Referrals and follow up documentation is satisfactory.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- TI is not maintaining proper plan regarding community participation.

- As the TI formed like Project Advisory Committee, Advocacy committee, DIC Committee but they have  to be strengthened by involving the Community.

- Events are condecting but community involvement is less

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

- No social marketing condoms are sold in the Evaluation period(April 2013 to march 2015)

- Condom outlet boxes are not properly displayed in the hot spots

- No proper planning to distribute condoms  and Needle/Syringes

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services

etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

- Project management committee is in place but not proper wok done

- Advocacy, Crisis, DIC committees are formed and there is a need to improve their effective functioning.

- TI has good linkages with line departments.

.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- There are no social protection schemes provided to HRG

XV. Best Practices if any

Confidential

Annexure C

Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| P.Appa Rao(Team Leader) | 09951282028 |
| Mr.Ajay Singh (External Evaluator-II) | 07398982415 |
| Mr. CA Arun Rawat (Finance Evaluator) | 09755871561 |
| Officials from SACS/TSU (as facilitator) | Mr.Mukesh Jatav |

| Name of the NGO: | Jabalpur Vyasayik Pracikhan Evam samaj Kalyan samiti |
| --- | --- |
| Typology of the target population: | IDU’s |
| Total population being covered against target: | 600 |
| Dates of Visit: | 25-03-2015 to 26-03-2015 |
| Place of Visit: | Jabalpur Vyasayik Pracikhan Evam samaj Kalyan samiti, Jarjola Road Paras Vihar Colony Near Finix School Narsinghpur Cotact No-07792-230065 Mob.No- 9981657766 |

Overall Rating based programme delivery score: 63.4%

| Total Score Obtained (in %) | Category | Category; Rating. | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

- All the staff need training for better results. - More Peer Educators are above age 30 years they need to change and should be give chance to others who are well educated and young. - Out let boxes are not properly intact - Staff documentation and communication skills to be improved. - Need to improve strong linkages with the external stakeholders. - The NGO must establish CBO since it is working from 2010 - Community involvement is very poor it should be develop by NGO staff - Documentation needs to be improved. - Referrals to ICTC, DOT, and RMC to be improved. - Reconciliation of Bank account has been done on yearly bases it should be done on monthly bases. - All the vouchers/ bill are maintained but need is to be improved. - Stock & Fixed assets register is maintaining but need to be improve. - OST referrals are satisfactory but by the word of nodal officer there is shortage of staff. Doctor is available only one day in the week

| Name of the evaluators |  | Signature |
| --- | --- | --- |
| P. Appa Rao (Team Leader) |  |  |
| Mr. Ajay Pratap Singh (External Evaluator- II) |  |  |
| Mr. CA Arun Kumar Rawat (Finance Evaluator) |  |  |