Nagaland State AIDS Control Society

Targeted Intervention - Evaluation Report

April 2014- January 2016

Care & Support Society

IDU

Ongpangkong

Mokokchung District

Evaluation team:

- Mr. Kholi. A		: Team Leader, External Evaluator

- Mr.Kevileme Visezuo : External Evaluator

- Mr. Raju Gupta	: Finance Evaluator

Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

OBackground of Project and Organisation

The Organization has been implementing the Targeted Intervention Project for IDUs for the last six years, i.e., April 2009- March 2015.

NGO has been implementing TI project at Ongpangkong with a DIC located at Ungma Village and giving TI services to 11 (Eleven) sites/areas. A Sub DIC has also been established at Chungtiayimsen village of Tzurangkong range of Mokokchung district to covers 7 (Seven) sites/Areas.

NGO is also undertaking Mobile ICTC, Mokokchung Unit since June 2008 where efforts are being given to give coverage to all the Targeted Intervention sites under Mokokchung district. The Organization has undertaken the PPTCT project since 2002 to 2008, and re-initiated again from December 1, 2010. Under this program services like Counselling, Community mobilization program, referral etc., are being provided to the general public, particularly to the pregnant mothers. The Organization also had the privilege to facilitate the implementation of Learning Site (LS) under EHA from 1st September, 2013. The Organization also runs a TB program in Tzurangkong range called Project AXSHAYA under DAN/CHAI. Since April 2012, the Organization is implementing the Community Based Rehabilitation (CBR) program that caters to the needs and welfare of people with disabilities (PWDs) in Mokokchung district. Beside this, the society is also implementing a Family Counselling centre (FCC) mainly for Women and Children from 1st April 2007. Right from the inception of the organization, the core staffs members’ remains intact as a result bringing in work experience and adoptability to the fieldwork.

O Name and address of the Organization

Care & Support Society, Mokokchung

Email address: careandsupportmokok@gmail.com

O Chief Functionary:

ImchawatiKichu

O Year of establishment:

27/ 09/ 1995

O Year and month of project initiation:

June 2009

OEvaluation team:

- Kholi. A (External Evaluator- Team Leader)

- Kevileme Visezuo(External Evaluator)

- Raju Gupta (External Finance Evaluator)

OTime frame:

Assessment Period: April 2014- January 2016

Date of Evaluation: 21st February – 22nd February 2016

Profile of TI

OTarget Population Profile:	Injecting Drug User (IDU)

OType of Project:			Core Group (IDU)

OSize of Target Group(s)

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
|  | IDU | IDU |
| Target | 430 | 430 |
| Achievement | 429 | 430 |

OTarget Area:

| Sl. No. | Name of the Coverage area |
| --- | --- |
| Sl. no | SITES/AREA |
| 1 | Ungma |
| 2 | Aolijen |
| 3 | Settsu |
| 4 | Kubza |
| 5 | Alichen |
| 6 | Sumi Settsu |
| 7 | Longkhum |
| 8 | Mangmetong |
| 9 | MokokchungVillage |
| 10 | Chuchuyimpang |
| 11 | Longmisa |
| 12 | Chungtiayimsen |
| 13 | Longpayimsen |
| 14 | Moayimti |
| 15 | Watiyim |
| 16 | Meralenden |
| 17 | Longtho |
| 18 | Medemyim |

I. Organizational support to the programme

- The organization has a managing board comprising of the following members:

- Mr. ImchawatiKichu – Chairman

- Mrs.Awala – Secretary

- Mr. Imsunensang – Treasurer

- Mr. C. Longkok - Member

- Mr. Imkong – Member

- Mrs. M. Amongla – Member

- Miss. Arenla – Member

- Mr. M. Yanger – Member

- Mr. I. Manko – Legal Advisor

- The Chairman who is also the Chief Functionary of the TI project and the Legal Advisor are also part of the Crisis Management team.

- To achieve its objectives, the organization plan to have activities such as outreach to IDUs through peers, ORWs & DIC; STI care and treatment; NSEP; condom demonstration & distribution; enabling environment; community mobilization; capacity building of staff; monitoring & evaluation.

- Monitoring and evaluation of TI is done on a monthly basis by the Project Director or Governing Body.

- The Organisation has also linked some HRGs in Social Protection Schemes.

- NGO has also developed IEC material in local language.

II. Organizational Capacity

1. Human resources:

- Trained, experienced and qualified staffs in social activities are preferred and all appointments are done with the approval of the Governing Body.

- All staffs and PE positions are filled as per contract agreement. Appointment letters for all staffs properly documented. A separate file is also maintained to keep track of PE’s profile, appointment date and resignation/ termination.

- Weekly and monthly reporting structure in place and monitored closely. Performance of each staffs and PEs is assessedduring weekly and monthly meetings. Basing on their monthly performance, staffs and PEs are given acknowledgement (small token gifts).

- Turnover occurs due to transfer, appointed in other jobs, personal problems or due to non-performance.

2. Capacity building:

- Training needs assessment is conducted for all categories of project staff and appropriate plans developed for in-house trainings.

Training Details of Staff and PE

| Sl.no | Name | Designation | Date of Training | Training Conducted By | Type of Training | Areas in which training was given |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Yashisutsung | PM | April 2014 | NSACS | Orientation | Female sex worker |
| 2 | Sungjemkaba | Accountant | April 2014 | NSACS | Refresher | SIMS |
|  |  |  | Feb 2015 | STRC | Induction | Accounts & MIS |
|  |  |  | Oct 2015 | STRC | Refresher | Finance & Program Management |
| 3 | Imtimenla | Nurse | April 2014 | NSACS | Induction | Harm Reduction |
|  |  |  | March 2015 | SACS | Re-Orientation | Clinic Management |
| 4 | Imchanechet | ORW | June 2015 | LS C&SS | Refresher | Program Management |
| 5 | Imchatemjen | ORW | May 2014 | LS C&SS | Refresher | Harm reduction |
|  |  |  | June 2015 | LS C&SS | Refresher | Harm reduction |
| 6 | Kilemsungba | ORW | NIL | NGO staffs | In-House | Harm Reduction |
| 7 | MerenImchen | PE | Sept 2014 | LS C&SS | Induction | Harm reduction |
|  |  |  | OCT 2015 | LS C&SS | Refresher | Harm reduction |
| 8 | Lima nuksung | PE | April 2014 | LS C&SS | Refresher | Harm reduction |
| 9 | Zalipu | PE | May 2014 | LS C&SS | Refresher | Harm reduction |
| 10 | Sentinaro | PE | May 2014 | LS C&SS | Refresher | Harm reduction |
| 11 | Toshisangba | PE | May 2014 | LS C&SS | Refresher | Harm reduction |
| 12 | Chubanungla | PE | Nov 2014 | LS C&SS | Refresher | Harm reduction |
| 13 | Shiluyanger | PE | Feb 2015 | LS C&SS | Refresher | Harm reduction |
| 14 | Imnawati | PE | Feb 2015 | LS C&SS | Refresher | Harm reduction |
| 15 | Sungjemmeren | PE | Oct 2015 | LS C&SS | Refresher | Harm reduction |
| 16 | Bendangnungsang | PE | Nov 2015 | LS C&SS | Refresher | Harm reduction |
| 17 | Putikokba | PE | Nov 2015 | LS C&SS | Refresher | Harm reduction |
| 18 | Khahuto | PE | Nov 2015 | LS C&SS | Refresher | Harm reduction |

3. Infrastructure of the organization:

- TI DIC has 4 rooms (1 room partitioned into PM’s room and meeting room, 1 for counselling cum STI clinic observation and 1 room allotted for ORWs. Aseparate kitchen is also attached within the premises.

- A sub-DIC has also been established at

- Laptop, desktop with peripherals &printer,and Digital cameraavailable at project office.

- Static STI clinic set up and in place. Clinical equipment’s, medicines, disinfectants, gloves and colour coded waste disposal bins in place.

- Adequate IEC and BCC materials, Condom demo-models, puncture proof container available at TI DIC.

- Basic office furniture’s and steel lockers in place.

- All 17 formats available and in use.

- Board games (carom) and TV sets available for recreation. No DVD for audio visual dissemination of media information.

- Documentation and Reporting:

- TI is adhering to the reporting protocols and all 17 formats for data collection is in use.

- Timely submission of SIMS is done on a regular basis.

- Submission of PE’s reports to ORW is done on a weekly basis.

- All reports (outreach and clinic) are collated and shared during weekly review meeting. Gaps are identified and action plans are developed.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
|  | IDU | IDU |
| Target | 430 | 429 |
| Achievement | 430 (1 expired) | 430 |

OSub-Groups and their Size: None

2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counselling.

Not applicable

3. Registration of truckers from 2 service sources i.e. STI clinics and counselling.

Not applicable

4. Micro planning in place and the same is reflected in Quality and documentation.

- Micro plansin place and developed half yearly and is based on commodity requirements, risk and vulnerability and sites to be covered.

- Outreach plans are done on a monthly basis and followed-up on a weekly basis, based on need for achieving target or gaps in commodity distribution, referrals and follow- ups on uptake of project services.

5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
|  | IDU | IDU |
| Target | 430 | 429 |
| Achievement | 430 | 430 |
| Nos. of New HRGs | 1 | 3 |

6. Outreach planning – quality, documentation and reflection in implementation

- Monthly outreach plan in place at the project level.

- Coordination meeting between staffs and PEs are done on a weekly basis and actions are taken up based on gaps and achievements.

- Prioritisation of outreach is determined by commodity demand and overdue referrals.Low travelling allowances for covering long distances and vast coverage area limits frequency of outreach activities.

- ORW provide supportive supervision to their respective PEs. Based on PE needs, ORW conducts FGDs at the hotspot level.

- The process of reviewing staffs and PEs, nature of actions plans are reflected in meeting minutes.

7. PE: HRG ratio:

|  | Ratio of PE to HRG |  |
| --- | --- | --- |
|  | April 2014- March 2015: | April 2015- Jan. 2016 |
| IDU | 1: 35 | 1: 35 |

8. Regular contacts

- On an average, 22 HRGs were contacted for 20 days in every month with any or all project services (NSEP/ BCC/ IEC/ Referral/ Condom distribution).

9. Documentation of the peer education

- Peer field dairies and Form B in use.

- Peer dairies reflect nature of outreach: topic discussed and number of HRGs contacted. Quantity of N/S and condom distributed, numbers of HRGs referred for HIV and Syphilistesting is also reflected.

10. Quality of peer education- messages, skills and reflection in the community

- Quality of peer education is reflected from community members’ awareness on risk reduction practices-safe injecting methods, single use of N/S, high return rate of used N/S; basic knowledge on HIV and STI - routes of transmissions, knowledge about health care provider and high percentage of HIV and Syphilis testing.

- Community members are also aware of various services provided in the TI DIC and haveknowledge about presence of other health care service providers.

11. Supervision- mechanism, process, follow-up in action taken etc.

- A 2 tier supportive supervision is carried out: Program manager level and ORWs level.

- At the Program Manager level, ORWs are assisted by the PM in helping develop their skills in rapport building, field/ outreach activity and documentation. At the ORW level, each PE’s are oriented on dissemination of correct information to their peers.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- Static STI clinic established at TI DIC and all STI cases are handled by part time TI Doctor and assisted by Nurse.

- Part time Doctor visit TI STI clinic every Thursday,during which the number of footfall in the clinic is high. Doctor is available on call.

- Nurse has been working in the TI project since 2012 and has attended/ received various trainings for Nurses.

- STI medicine Kits 1, 4 and 6 available but stock out of Kit 3, 4, 5 & 7 reported since last project year. These KITS were not indented because requirement did not arise for treating related STI cases.

- Buffer stock of STI medicines not maintained.

- All Clinical information’s are kept confidential by the nurse.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Static STI Clinic established at TI DIC with separate room for examination.

- Basic clinical equipment, gloves, disinfectants,furniture and observation bed in place.

- Waste Disposal mechanism: Collection and final disposal is done as per NACO guidelines.

- STI medicine Kits 1, 4 and 6 available but stock out of Kit 3, 4, 5 & 7 reported since last project year. These KITS were not indented because requirement did not arise for treating related STI cases.

- Buffer stock of STI medicines not maintained.

- Abscess prevention and management materials are also available.

- All Clinical information’s are kept confidential by the nurse.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not applicable

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- Syndromic case Management chart in place at the clinic and standard protocols are followed.(TI part time Doctor and Nurse has been trained on Syndromic Case Management).

- Network Clinic Format in use and properly updated for follow-up action.

- Information about individual HRGs to be follow-up (ICTC, RMC, Syphilis) is shared during weekly review meetings and action plans are taken up.

- TI NGO is managing Mobile ICTC where all HIV testing are referred to.

- Linkages have also been established with ICTC & ART Centre at IMDH, Mokokchung and with Mobile ICTC.

- Linkages also established with RNTCP centre at IMDH, Mokokchung

5. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- All Clinic Network Formats/ Registers in use by Nurse.

- A standard Referral slip is in use and all referrals are properly tracked.

- Stock registers of medicines maintained and updated on a regular basis.

- STI medicines Kits are procured from NSACS. Indent Register also maintained for requisitioning STI medicines from NSACS.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Free condoms are distributed by PE’s and staffs of TI DIC. No secondary distribution outlets has been created however, a sub-DIC has also been established at Chungtiayimsen village, Tzurangkong range inMokokchung district to covers 7 (Seven) sites/Areas.

- Social Condom Marketing (SCM) was initiated during the project year 2015-2016 to cater to the needs of the community members.

- Community members reported that they get free condoms as and when they demand.  No shortage has been reported during the assessment period.

7.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

| Total nos. of free condom distributed against requirement | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| Requirement | 23198 | 19479 |
| Distribution | 22230 | 18149 |

- A total of2589 branded condoms were also sold to HRGs as part of Condom Social marketing.

8. No. of Needles / Syringes distributed through outreach / DIC.

| Total nos. of N/S distributed | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| Requirement | 44250 | 36735 |
| Distribution | 43797 | 36374 |
| Used N/S Returned | 37164 | 30647 |

9. Information on linkages for ICTC, DOT, ART, STI clinics.

- Static STI clinic has been established at Care and Support TI Project site and all STI cases are handled by the Nurse and part time Doctor.

- Linkage has been created at ICTC at IMDH, Mokokchung for HIV testing.

- Referral linkagehasalso been established at RNTCP at IMDH, Mokokchung.

- All HIV positive cases are referred to ART centre at IMDH, Mokokchung.

10. Referrals and follows up

- All blood testing for HIV is referred to mobile ICTC which is operated by the TI NGO.

- HIV testing is also referred to fixed-ICTC at IMDH, Mokokchung.

- All HIV positive cases are followed-up and linked to ART centre at IMDH, Mokokchung.

- Follow up actions are initiated by the Nurse during weekly and monthly review meetings. PEs or ORWs provide accompanied referral.

- A total of 429 underwent HIV testing at least once in the last one year against 430 registered (99.76%).

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- A Core Committee (DIC Committee) has been set up to oversee management of DIC and organising Community Events.

- A total of seven [n=7] Community Events has been organised during the assessment period and a total of 81 HRGs participated in the events.

- Seven [n=7] important dates were observed.

- Two [n=2] Health Camps were organised and a total of 48 HRGs attended.

- A Crisis Response Team has also been set up representedby 3 PEs, 1 ORW, Program Manager, TI part time Doctor, an Advocate and a Doctor [n=8 members].

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members are involved in the project as PEs and ORWs. They take active part in outreach activities like commodity distribution, providing referrals, conduct of FGDs, organising community events, observation of important dates. All activities are properly documented.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- Static STI clinic has been established at Care and Support TI Project site and all STI cases are handled by the Nurse and part time Doctor.

- All blood testing for HIV is referred to mobile ICTC which is being operated by the TI NGO.

- HIV testing is also referred to fixed-ICTC at IMDH, Mokokchung which is located 3-4 Kms. away from TI DIC.

- All HIV positive cases are followed-up and linked to ART centre at IMDH, Mokokchung.

- Referral linkagehasalso been established at RNTCP at IMDH, Mokokchung.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

|  | April 2014- March 2015 | April 2015- Jan. 2016 |
| --- | --- | --- |
| Referred for HIV testing | 800 times to 430 HRGs | 668 times to 430 HRGs |
| Nos. of HRGs who tested at least once during the last one year (Actual tested) | 429 | 429 |
| Nos. of HRGs who tested twice during the last one year | 350 | 233 |

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- NGOstarted implementing TI project in the year 2009 and had since then created support system with the local leaders, Church community, colony/ ward leaders, NGOs and student’s organizations in the coverage areas.

- Advocacies with various key stakeholders had been done since the inception of the project in 2009 with continued support and participation from the stakeholder as well as from general community.

- The Church had also appointed one of its members to represent the church in any of the project programs whenever required.

- During the assessment period (April 2014 till Jan 2016), involvement of stakeholders in the project has been observed and they were willing to support and collaborate with any TI project activities.

VII. Financial systems and procedures

1. Systems of planning:

- All the Planning & decision making is done by the Director, secretary and Members of the Organization. Planning is also done according to the prescribed system endorsed by SACS & NACO.

- The members involved in planning are listed below:

- Project Director/ Chief functionary

- Secretary

- Members of the Organization.

- Budget Utilization is more than 60% against the released fund and all expendituresare within approved budget in all budget head

- Separate bank A/c is in place for TI project in the project area.

- SOEs are submitted before the 5th of every month.

- Adequate measures have been taken by NGO to audit observations and recommendations.

2. Systems of payments:

- The NGO is practising the systems of getting approval from PD before any transaction or payments.

- All payments are made with proper bills and vouchers, but most of the bills are ‘katcha’.

- The Organisation is adhering to NACO’s directive of making all payments above ₹5000/- in cheques.

- Instances of cash in hand exceeding NACO’s limit of ₹. 5000/- noticed.

3. Systems of procurement-

- Purchase of drugs is done as per GMP guide line.

- Quotations are taken before procurement of assets and commodities.

4. Systems of documentation-

- Separate bank A/c is in place for TI project in the project area.

- Vouchers are printed and machine numbered, but ledger is not maintained for vouchers.

- Cash book, bills and vouchersare updated on daily basis.

- SOE is submitted in time.

- No mismatch found between physical and financial reporting.

- Audit report is in place.

- Assets register properly maintained and all assets are codified/ marked accordingly.

VIII. Competency of the project staff

VIII a. Project Manager

- Program Manager is a Graduate and has an additional Degree in Computer Course (A Level). He had also served as a teacher.

- PM was appointed in the month of August, 2013 and attended Orientation training on Female Sex Worker, organised by NSACS.

- PM is familiar with project proposal: conducting Need Assessment with staffs and HRGs. Review of last project year’s achievements, commodity distributions, referral targets, etc.

- Is able to explain his roles and responsibilities and was able to describe the various performance indicators.

- Quarterly and Monthly plan in place at the project level.

- Have a fair knowledge about budget heads and costing in TI project.

- Is competent in use of computer and management of data.

- Review of staffs is done monthly based on performance and achievements.

- Conducts supportive supervision to assess outreach activities.

- Field 3-4 times in a month. All movement documented.

VIII b. Counsellor

Not applicable

VIII c. ANM/ Counsellor in IDU TI

- Nurse has been working with the TI Project since 2012 and has attended several trainings conducted by NSACS.

- Is able to explain risk assessment and risk reduction processes.

- Is able to give basic counselling on HIV and STI.

- Has adequate knowledge about local drug use scenario.

- All registers and clinic formats are maintained and updated regularly.

- Conducts 3-4 field visitsin a month and reflected in movement register.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

- 3 ORWs on board as per contract agreement.

- ORWs are able to explain various indicators for their respective PEs.

- 1 ORW recently appointed (Feb. 2016). In-house orientation given.

- Monitoring of PEs is done by the ORW and key performance indicators are closely checked. Outreach planning is done in consultation with Program Manager, Nurse and Counsellor.

- Understands hotspot analysis and is able to explain it.

- ORWs have basic knowledge of STI symptoms.

- Supportive supervision is done based on needs and PE’s are assisted in conducting FGD meetings at the hotspots level.

- Capacity building on rapport building, condom demonstration, safer injecting practise, abstinence, OST and overdose prevention are imparted.

VIII e. Peer educators in FSW TI

- Not Applicable

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

- Prioritisation is done as per demand for commodities by HRGs and referral for HIV testing, RMC and Syphilis.

- Have adequate understanding about importance of RMC and HIV testing.

- Possesses fair condom demonstration skills and have basic knowledge on common symptomatic STI.

- Have a fair knowledge about various health care service provider and centres.

VIII h. Peer Educators in Truckers Project

Not Applicable

VIII i. M&E officer

Not applicable

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- Project related services are given to HRGs on a regular basis and follow-up mechanism is in place.

- Prioritisation of service delivery is based on demand for commodity, uptake of referrals services and follow-ups. Individual HRGs are tracked for ICTC, syphilis testing and RMC.

- Micro plans are updated on a quarterly basis and outreach plans are developed on a monthly and weekly basis.

IX. b. Outreach activity in Truckers and Migrant Project

Not applicable

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

| Services | Apr 2014- March 2015 | April 2015- Jan. 2016 |
| --- | --- | --- |
| Nos. of HRGs provided Counselling | 429 were counselled 1517 times | 429 were counselled 1293 times |
| Total nos. of HRGs referred for HIV testing | 430 referred 800 times | 430 referred 668 times |
| HIV Testing (Twice in a year) | 350 | 233 |
| Syphilis Testing (Twice in a year) | 350 tested and 1 found reactive | 233 |
| Referred to DOTS | 0 (2 tested for TB but negative) | 0 (3 tested but negative) |
| Abscess Treated | 6 | 7 |
| Condom distributed | 22230 | 18149 |
| N/S distributed | 43797 | 36374 |
| N/S Returned | 37164 | 30647 |

Linkage Referrals to Service Providers:

- ICTC: NGO managing Mobile ICTC. Linkage also established at CHC Ungma

- ART: Linkage established at ART Centre in IMDH, Mokokchung.

- DOT: Linkage established at RNTCP at IMDH, Mokokchung.

- FGD respondents reported satisfaction of services provided by TI project.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- Two [n=2] ORWs on are from users background and had been appointed directly as ORW. They take part in project planning and development of project proposal.

- All outreach activities: commodity distribution, referrals, group discussions, IEC based outreach and advocacy are planned as per the needs of the community members.

XII. Commodities

- Condom and N/S requirement are done at the project level after conducting Need Assessment with the community members. Commodity distribution of the previous project year is also referred for assessing HRGs requirement.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc.

- No systematic advocacy plan in place. Advocacy is done only when need arises.

- Advocacies are conducted to sensitise or create awareness of project activities, OST programs, to create awareness on HIV/ AIDS and for creating a favourable environment for smooth delivery of project services. A total of seven [n=7] advocacies was conducted with family members of HRGs, Ward Council members and General community.

- Community Members expressed happiness with the project for sensitising the public about the issues of HRGs and creating linkages to various service providers.

- Good networking with key stakeholders established and joint collaboration initiatives observed.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- TI NGO has linked staffs and HRGs with Labour Department. The scheme provides seed money to buy tools and equipment for carpenter, painters and labourers.

- TI NGO has also provided insurance plan for staffs.

XV. Best Practices if any

- Involvement of stakeholders andcommunity members in Crisis Response Team.

- Separate profiling register for PEs are maintained. Spouses of HRGs are also appointed as PEs for easier accessibility.

- Regular visit by part time doctor observed. Clinic visits(footfall) very high during doctor’s scheduled visits at STI Clinic (every Thursday).

- Good monitoring system in place. Performance of each staffs and PEs are assessed on a monthly basis and based on their performances, acknowledgement is given. Non performing staffs are PE’s are terminated

- Good documenting system in place.

- Organisation has linked HRGs to Welfare Schemes.

- Organisation has covered all staffs Life Insurance Policy.

- NGO has developed IEC material in local language.

Confidential                                      Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Kholi. A | +91 9862797996 |
| Kevileme Visezuo | +91 9774978143 |
| Raju Gupta | +91 7085169800 |
| Officials from SACS/TSU (as facilitator) Ms. Imtisenla | +91 9856534957 |

| Name of the NGO: | Care and Support Society |
| --- | --- |
| Typology of target population | CoreGroup (IDU) |
| Total population being covered against target: | April 2014- March 2015:; April 2015 - Jan. 2016. IDU; IDU. Target; 432; 430. Achievement; 429; 430. |
| Dates of Visit: | 21 – 22nd February 2016 |
| Place of Visit: | Care and Support Society DIC, Ungma. |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 83.6% | A | Very Good | Recommended for Continuation |

Specific Recommendations:

Organisation: - Ensure that stock-out of commodities does not occur. - Stock out of STI medicines should be indented and reported to NSACS immediately. Financial management: - Should try to ensure that cash-in-hand does not exceed₹5000/- as per NACO’s directive. - To maintain a Ledger for vouchers. Program Delivery: - PE to HRG ratio is only 1:35. Therefore, ensure that all HRGs are contacted regularly on a monthly basis for delivery of any project services. - Put more focus on newly registered HRGs to participate in group meetings (hotspot/ DIC). - Ensure that stock-out of commodities does not occur. - Scale up twice testing for HIV. - Encourage collectivisation and formation of support groups within the community members. - Encourage more community members to participate in events organised/ observed by the TI DIC.

Name of the Evaluators				Signature

| Kholi. A (External Evaluator) |  |
| --- | --- |
| Kevileme Visezuo (External Evaluator) |  |
| Raju Gupta (Finance Evaluator) |  |