Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organisation:

The Frontier Development Society (FDS) established in 2004 has been implementing various projects on community health care under Tuensang district.  The TI Project was initiated September 2010 among IDUs in Noksen Area in Tuensang district.

| Name and address of the Organization | : | Frontier Development Society (FDS) Post Box – 87, Tuensang |
| --- | --- | --- |
| Chief Functionary | : | Mr. S.B. Chuba |
| Year of establishment | : | 2004 |
| Year and month of project initiation | : | September, 2010 |
| Evaluation team | : | - Mr. Jongpongciten, Team Leader - Mr. Kenyulo, 2nd Evaluator - Mr. Akhumtong Jamir, Finance Evaluator - Mr. Visheto Mekro, NSACS |
| Time frame | : | April 2014 to January 2016 |

| Profile of TI |  |  |
| --- | --- | --- |
| Target Population Profile | : | IDU |
| Type of Project | : | Core |
| Size of Target Group(s) | : | 243 IDUs & 64 SPs in 2014-15 and 256 IDUs & 72 SPs in 2015-16. |
| Target Area | : | 11 interventions sites in Tuensang Village and Noksen area under Tuensang district |

Key Findings and recommendations on Various Project Components

- Organizational support to the programme

During the visit, the Evaluation team was unable to meet with any of the key members of the organization even the Project Director. Most of the project activities are managed by the Programme Manager.

II. Organizational Capacity

1. 	Human resources

All the staff and PE positions are filled as per approved project. The project 1 Programme Manager, 1 M&E cum Accountant, 1 Nurse, 1 ORW and 8 PEs for IDUs, 1 ORW and 1 PE for SPs and 1 Part-time Doctor.

There were 2 PEs turnovers in 2014-15 and the nurse in 2015. The present ORW for IDU was graduated from PE.

2. 	Capacity building

All the project staff and PEs, including the part-time Doctor have attended trainings conducted by NSACS, STRC and Learning Site.

3. 	Infrastructure of the organization

The TI office located in Tuensang village is a temporary shift of office and does not have adequate space for the current needs of the project. The office will move to the previous complex on completion of the building construction. There are only three rooms – 1 room for outreach the team, 1 room for Programme Manager and M&E cum Accountant and 1 room for the nurse and the doctor. The DIC does not have a separate room for recreation.

4. 	Documentation and Reporting

The TI project adheres to forms, formats and registers prescribed by NACO/SACS and available in the project office.

Weekly and Monthly review meetings held at the project level whereby activities of each staff and PEs are reviewed, provide feedbacks on the activities carried out and plan for the subsequent month. PD attendance in monthly review meetings were less than 50% in both the years.

Activity Reports and SOEs are submitted in SIMS to NSACS through DAPCU in the first week of succeeding month. The DAPCU reviews the reports and forwards them to NSACS

In the current project year there are instances of delay in final submission of TI reports and SOEs to NSACS from DAPCU level owing to problem in internet connectivity.

Sharing of project reports and technical inputs takes place during the quarterly review meeting at DAPCU level, half-yearly and annual review meeting conducted by NSACS.

Electronic database and management reporting systems exist for tracking clients at all project level, programme outcomes and financial information.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

256 IDUs registered against the target of 243 in 2014-15 FY and 295 against 256 in 2015-16.

23 new IDUs were registered in 2014-15 and 39 in 2015-16.

- Micro planning in place and the same is reflected in Quality and documentation.

Form-B/B1 is maintained by PE. Proper prioritization done by ORW. Some of the Peers had good understanding about prioritization of HRG and are able to explain risk, vulnerability, condom demand data, BCC, and service delivery.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

100% coverage of active population was covered with NSEP in both the years.

- Outreach planning

As per the document verified it was observed that outreach and micro plan in place and the same is used by ORW and Nurse in delivering project services. Individual HRGs were tracked for clinical services.

- PE: HRG ratio

There were 8 PEs as per approved budget for the target of 256 in 2014-15 and 295 in 2015-16.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

There are no daily or medium high volume injectors among the HRGs, however all HRGs have been provided with N/S as per their requirement by PEs.

- Documentation of the peer education

Form-B/B1 is maintained by PE. Proper prioritization done by ORW.

- Quality of peer education- messages, skills and reflection in the community

Some of the Peers had good understanding about prioritization of HRG and are able to explain risk, vulnerability, condom demand data, BCC, and service delivery.

- Supervision- mechanism, process, follow-up in action taken etc

ORW could able visit upto two times in a month. Verification of the ORW weekly reports and movement register shows the same.

IV. Services

- Availability of STI services

Static clinic located in the project office and all prescribed formats are maintained by the nurse and up-to-date, but it needs to improve in terms of cleanliness. Clinic has a full-time nurse and a part-time doctor.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Requisite equipments and tools for the operation of clinic are available. Drugs were available.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

67.27% (n=185) of 275 clinic attendees were counseled and 1 STI treated in 2014-15 and 5 in 2015-16. 62% (n=185) of 295 were counseled at project level by nurse.

75.87% (n=194) of 256 HRGs line listed have underwent the biannual Syphilis screenings and 100% (n=255) have tested once in 2014-15. In 2015-16, 53.89% (n=159) of 295 HRGs line listed have tested twice and 91.18% (n=269) have tested once.

76.98% (n=194) of 252 HRGs line listed have tested twice for HIV and 100% have tested once in 2014-15. 54.63% (n=159) of 291 HRGs line listed have tested twice and 92.43% (n=269) have tested once in 2015-16. All were tested negative in both the years. 4 tested HIV positive in 2013-14 are still accessing project services. MICTC visits the TI intervention sites every Thursday. The proportion of testing done in MICTC was higher than testing done at Standalone ICTC.

Two abscess cases were treated in 2014-15. There was no abscess cases reported in 2015-16.

9 linked in 2014-15 as per the registration slips (at RNTCP) available in DIC. No referrals made in 2015-16.

- Documentation

All the prescribed registers and format are maintained by the nurse in the clinic and are up-to-date.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Condoms are made available for free as well through social marketing. Distribution of free condoms as well the marketing are done by the outreach team during outreach. There was no shortage of condoms reported in both the years. The same was reported by the HRGs during FGDs.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

91.85% (16803 pcs) of 18292 condom requirement forecasted in the project in 2014-15 and 99.61% (15183 pcs) of 15242 in 2015-16 were distributed to 100% of HRGs in both the years. Demand and gap analysis have been done for both the years.

120 pcs of condoms in 2014-15 and 1316 pcs in 2015-15 were marketed by the outreach team. No demand analysis has been carried out by the TI.

- No. of Needles / Syringes distributed through outreach / DIC.

98.47% (19965 Nos) of 20274 in 2014-15 & 99.87% (17897 Nos) of 17920 in 2015-16 were distributed to 100% of HRGs line listed in both the years Demand/gap analysis is updated quarterly.

93.18% (18892) of 20274 distributed in 2014-15 and 97.35% (17424) of 17897 distributed in 2015-16 were returned / collected for safe disposal.

Concrete pit has been constructed behind the TI Office as per the guidelines and final disposal of used N/S is dumped there.

- Information on linkages for ICTC, DOT, ART, STI clinics.

HIV testing and Syphilis screening is done at MICTC and ICTC centre. Greater proportion of testing and screening were done at MICTC. MICTC visit a TI site every Thursday.

The TI has established linkage with OST, ART and DOTS centres in District Hospital Tuensang. 22 HRGs are currently on OST.

- Referrals and follows up

There is individual tracking system in place for clinic services. Referrals were for TB suspect cases and for enrolling in OST programme. Follow-up have been done for all OST referrals.

V. 	Community participation

1. 	Collectivization activities

20.33% (n=60 IDUs) of 295 are part of 6 SHGs formed. DIC committee has not been constituted.

2. 	Community participation in project activities

Community members involved in the project as PEs and ORW. Activities include planning of outreach activities, commodity distribution, referrals and conduct of FGD.  Only 13.67% (n=35 IDUs) of 256 line listed in 2014-15 participated in an event organized by the project. No programme was organized in 2015-16.While documentation of all activities carried out are maintained, reports of held are brief and lacks details.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

TI has established very good coordination with MICTC, TI Project in Tuensang Town, and District Hospital for STI, ICTC, and OST. Sharing of information and resources has been observed with MICTC and TI Project in Tuensang.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

100% of the HRGs referred have tested in MICTC and ICTC. Since the MICTC station its team every Thursday in a TI site and accompanied referrals were made to ICTC, there were no gaps between referred and tested in both the years.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

1 meeting was conducted with 13 stakeholders to address misconceptions about harm reduction programme in 20145-15 and 3 meetings were held with 53 stakeholders on OST, HIV testing and harm reduction programme in 2015-16 as planned and documented in Form J. Stakeholders interviewed were well aware of the issues of HRGs reported their participations in 3 meetings organized by the TI.  Some of them have even gone up against OST programme when it was first launched. With clarification made to them by the NGO, they understood and have seen its benefits and now are advocating among the parents of HRGs to enroll in OST.

VII. Financial System and Procedures

- Systems of planning

- Monthly requisition for the budget to be utilized is not prepared as per the monthly work plan.

- Except for the budget line item “2.6 Other Administrative Cost” which was utilized for purchased of NSEP without approval from NSACS, the other expenditures were as per the approved budget heads.

- Separate bank account is being maintained in the local bank.

- Systems of payments

- All vouchers are machine numbered and ledgers are in order.

- Vouchers from October 2015 to January 2016 did not have either PD's or PM's signature.

- Except for salary to staff, other payments of more than Rs.5000/- were made by cash.

- Transactions of receipt and repayment of temporary loans has been by cash.

- Systems of procurement

- The NGO did not adhere to procurement guidelines of SACS/NACO for purchase of N/S. No quotations as well as the decision of the NGO for selection of a vendor were available.

- Systems of documentation

- Joint bank account operated in the project location.

- Audit reports are available.

- BRS were not done.

- There was only on receipt of professional tax paid while it was paid for all the staff as per bank statements.

- Most of the SOE reports were wrongly prepared. December 2015 SOE report is entirely wrong. Bank amount has been added twice and most of the SOEs do not tally with Cash book and Ledger.

VIII. Competency of the project staff

VIII a. Project Manager

- Project Manager has the required qualification with experience in the TI project in position of PE, peer counselor, ORW and counsellor.

- Manages data and computerized data collection tools in use.

- Has knowledge about project proposal planning and on performance indicators.

- Program Manager is aware about the budget components under various heads but limited knowledge about financial management.

VIII c. ANM/Counselor in IDU TI

- ANM maintains all clinical records including diagnosis and prescription made by the doctor. The ANM maintains and updates all clinical records which are compiled for CMIS reporting to NSACS. Referral slips and medicine stock are maintained and updated daily by the nurse.

VIII d. ORW

- ORW is aware of the project indicators and able to understand the Formats used for planning and reporting including.

VIII f. Peer educators in IDU TI

- All the PEs are oriented on project activities. Assisted by ORW they make need based commodity requirement such as condoms, NSEP and referrals. However, some of the PEs are not able to fill in the format and plan outreach according to the weekly/ monthly work plan due to poor literacy.

- PEs are aware of ICTC referrals and OST services. Most PE are aware of referrals centres providing services to IDU in the project intervention sites.

IX. a. Outreach activity in Core TI project

X. 	Services

Service uptake through the project was documented and was at the level of satisfaction of beneficiaries.

XI. 	Community involvement

Community members involved in the project as PEs and ORW. Activities include planning of outreach activities, commodity distribution, referrals and conduct of FGD.  Only 13.67% (n=35 IDUs) of 256 line listed in 2014-15 participated in an event organized by the project. No programme was organized in 2015-16.While documentation of all activities carried out are maintained, reports of held are brief and lacks details.

XII. Commodities

- Condom demand is being calculated by following week recall method: No. of sexual act; Use of condom; Condom bought

- N/S demand is calculated by frequency of injecting drug: daily/weekly/occasionally

- Project/hotspots level planning for condoms is based on the requirements of individual HRGs in each site the project is covering. Condom and N/S demand and gap analysis is carried out during the planning of the project and updated quarterly. The requirement differs from each individual HRG’s depending on risks and vulnerabilities assessment conducted by PEs.

XIII. Enabling environment

1 meeting was conducted with 13 stakeholders to address misconceptions about harm reduction programme in 20145-15. 3 meetings were held with 53 stakeholders on OST, HIV testing and harm reduction programme in 2015-16 as planned and documented in Form J. While the stakeholder holders are aware of the issues of HRGs and participates in project activities, the project staff lacks clarity on advocacy works.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- Facilitated:

  - 18 IDUs and 3 SPs get registered in Building & Construction Workers Schemes, under Department of Labour & Employment, Government of Nagaland.

  - 1 SHG of 10 SPs registered with Eleutherus Christian Society (Tuensang).

  - 5 IDUs and 3 SPs registered for job card in DRDA.

  - 8 IDUs and 5 SPs in opening of bank account in SBI with zero balance.

XV. Best Practices if any