Annexure C

Confidential				Reporting Form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the Evaluator(s):

| Name of the Evaluators | Contact Details with phone No. |
| --- | --- |
| Mr. Jongpongchiten | 9436093045 jcimsong@gmail.com |
| Mr. Kenyulo | 8974343146 kensebu@gmail.com |
| Mr. Akumtong Jamir | 8014632815 akumtongjamir@gmail.com |
| Mr. Sheto Official from Nagaland SACS | 8413840165 |

| Name of the NGO | Frontier Development Society (FDS) |
| --- | --- |
| Typology of the Target Population | IDU |
| Total population being covered against target | 256 IDUs against the target of 243 in 2014-15 and 295 IDUs against 256 in 2015-16. |
| Date of Visit | 18th & 19th February, 2016 |
| Place of Visit | Tuensang Village |

Overall Rating based on Programme Delivery Score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 59% | C | Average | Recommended for with specific focus on increased involvement of GB Members of the NGO in the TI Project. |

Specific Recommendations:

Organizational Capacity: - Community consultations: Once in a quarter community feedback to be solicited to understand the responsiveness, comprehensiveness, adequacy and other aspects related delivery of quality project services. This process can be done through focused group discussion or through informal feedback mechanisms. Feedbacks from HRGs to be take into consideration while planning and delivering project services. - Increased involvement of the Project Director is required for effective implementation of the project. Monthly review of project progress by the PD is very low. Program Delivery - Supportive Supervision of PE: ORW to monitor PEs’ activities and documentation works. ORW to also provide onsite mentoring to build their skills in carrying out their role as peer educators. - New registered HRGs to be covered in hotspot level meeting in every month. - Nurse to ensure that all clinic attendees are provided counselling. - HRGs that have undergone the 1st biannual HIV test to be timely followed up with the 2nd test. - To take condom social marketing forward, demand analysis to be carried out and marketing strategy to be devised. - Advocacy to be regularly conducted at all levels with proper documentation and follow-up. - Efforts to be made to mobiles more HRGs and facilitate them to form support groups. - Meaningful events for the HRGs to be organized regularly targeting increased participations. Finance - Prior approval to be sought from NSACS for re-appropriation of funds. - Proper approval to be taken from PD for any expenditure. PM to verify vouchers and sign. - Minimize cash transaction for the amount of more than Rs.5000/-. - NACO guidelines on procurement to be followed for purchase of N/S. - Cash book to be properly maintained and update it regularly. - SOEs reports to be prepared as per the books of account and bank balance and also ensure timely submission. - Accountant needs further training on accounting (records and book keeping).

| Name of Evaluators | Signature |
| --- | --- |
| Mr. Jongpongchiten |  |
| Mr. Kenyulo |  |
| Mr. Akumtong Jamir |  |
| Mr. Sheto Official from Nagaland SACS |  |