Nagaland State AIDS Control Society

Targeted Intervention - Evaluation Report

April 2014- January 2016

Grace Society

IDU

Akhoya

Mokokchung District

Evaluation team:

- Mr. Kholi. A			: Team Leader, External Evaluator

- Mr.Kevileme Visezuo 	: External Evaluator

- Mr. Raju Gupta		: Finance Evaluator

Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

OBackground of Project and Organisation

Grace Society, Mokokchung is a registered Society registered under Society Registration Act XII of 1860, and was amended vide Nagaland (First amendment) Act 1969, Government of Nagaland with a registration No.H/RS-2762 dated 21/10/02 and was established in the year 2002 itself. It came into being with an aim to bring social development specially targeting the young population of Nagaland State. Viewing the situation of substance abuse, it has conducted several awareness programs, seminars and advocacy meeting during its four years existence with the help of public co-operation.

Akhoya is one of the most highly substance abuse affected village in Mokokchung district of Nagaland. It is only 43 kms away from Amguri (Assam) where pharmaceutical drugs could be easily accessed without hindrances which make this area the main supply zone for neighbouring areas, therefore threatening the harmony of the whole population of this area not only through substance abuse but also through its related disease such as HIV/AIDS through injecting and sharing. There is about 600 drug user in and around the area (Base line survey June 2005)

So far, the Drop-in-centre tried to tackle the problem which creates chaos and pain in the mind of the people in the area by means of NSEP (Needle Syringes Exchange Programme) and condom promotion. Thus, the Drop-in-centre was able to change their behaviors (from sharing to non-sharing) up to the extent of 70-80 percent among the IDUs.

Due to the limitation of infrastructure and recreational activities there is a wide chance for the addicts to relapse after their detoxification period. This also creates one of the problems when trying to make abstain from the habits of drugs.

Nearby, the area and villages of Akhoya, the people were given negative impact about NSEP and condom promotion. They are disturbed by the rumours from within and outside the area. Thus the drop in centre needs to educate and make aware of such services to the people regularly.

Thus, a Drop-in-centre stand as a platform for targeted intervention and others to provide service like education on preventive measure harm minimization concept, individual counselling, group discussion, and family meetings follow ups etc, to understand and control the problems of drug usage and related harms among the general population, drug users and particularly the IDUs.

O Name and address of the Organization

Grace Society, Akhoya

C/o Grace Society Changtongya, DIC

PWD Ward, Changtongya Town.

798613.

Email ID  : grcscty@rediffmail.com.

Contact number          :9856899237/ 9612939852.

O Chief Functionary:RazianlungGonmei. (Project Director)

O Year of establishment:2001

O Year and month of project initiation: 2006

OEvaluation team:

- Kholi. A (External Evaluator)

- KevilemeVisezuo (External Evaluator)

- Raju Gupta (External Finance Evaluator)

OTime frame:

Assessment Period: April 2014- January 2016

Date of Evaluation: 27th- 28th February 2016

Profile of TI

OTarget Population Profile:Injecting Drug User (IDU)

OType of Project:Core Group (IDU)

OSize of Target Group(s)

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 269 (1 expired) | 268 |

OTarget Area:

| Sl. No. | Name of the Coverage area |
| --- | --- |
| 1 | Akhoya Village |
| 2 | Unger Village |
| 3 | ChuchuyimlangVillage |
| 4 | ChuchuyimlangTown |
| 5 | MongsenyimtiVillage |
| 6 | MongsenyimtiCompound |
| 7 | YisemyongCompound |
| 8 | SungratsuVillage |
| 9 | AlongchenCompound |
| 10 | MopungchuketVillage |
| 11 | Kubolong |
| 12 | LongjangVillage |
| 13 | LongjangCompound |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

The Grace Society with the objective to prevent and control the spread of HIV/AIDS & STI among IDU’S  through opening the DIC in Akhoya village under Mokokchung District is on its 4th  phase of implementing TI project supported by NSACS. All the staff and PEs are in position as per contract agreement with NSACS. All  staffs are provided with necessary trainings and induction. Job descripition is provided to all the  staffs and appointment letters and is available at DIC. Review meetings are held twice every month(first and last week of every month).

II. Organizational Capacity

1. Human resources:

| Sl.No. | Name of Staffs/ PE | Designation |
| --- | --- | --- |
| 1 | RAZIANLUNG GONMEI | Project Director |
| 2 | SAMUEL | Program Manager |
| 3 | TSUKTI | Accountant |
| 4 | TIASANGLA | Counsellor/Nurse |
| 5 | MOATOSHI | ORW |
| 6 | TEMSHI | ORW |
| 7 | LIMASANEN | PE |
| 8 | LIMATEMSU | PE |
| 9 | CHUBA | PE |
| 10 | CHUBAONEN | PE |
| 11 | BUR | PE |
| 12 | SASHIAKUM | PE |
| 13 | LIMAJUNGBA | PE |
| 14 | ANNA | PE |
| 15 | SUNGIT | PE |
| 16 |  | Part time Doctor |

- Appointments of staffs aredone by the Governing Body.

- Appointments of PEs done on recommendations from the community members and ORW.

- Weekly and monthly reporting structure in place and monitored. Performance of each staffs and PEs is assessed on a weekly and monthly basis.

- All staffs and PEs are committed towards the project activities. Project staffs and PEs are terminated if they do not perform their duty (HR Manuel).

- No staff turnover observed.

- 3 PE turnovers witnessed during the assessment period.

- Accountant is based at TI DIC.

2. Capacity building:

| Designation | Name of the staff | Name of training attended & No of days | Who conducted the training |
| --- | --- | --- | --- |
| PM | Samuel | Program Management & DCT for PM | STRC |
| NURSE | Tiasangla | - Appointed in February 2016 and yet to be trained. Received in-house training on data collection given by Program Manager. - Has work at Sub CenterLongjangfor 1 year and CHC, Tubo for 1 year. |  |
| ORW | Moatoshi&Temshi | ORW refresher | LS-MKG |
| PE | Chuba/Temjen/ Anna/ Limasanen/ Temjen/ Imtisungit. | PE Induction & refresher - 3 PEs yet to be called for training from Learning Sites (Care and Support Society). In-house orientation given. | LS-MKG. |

3. Infrastructure of the organization:

- The TI has 2 rooms. Oneroom has been partitioned into Program Manager cum Accountant’s room and Counselling room cum Observation room. Another room is used as a recreation room for the HRGs. Separate kitchen is also in place.

- Basic office furniture’s are in place.

- Computer, laptops, TV &DVD Player, printer and lockers in place.

- Static STI clinic set up and in place. Clinical equipment’s, weighing machine, medicines, disinfectants, gloves and colour coded waste disposal bins in place.

- Abscess prevention and management materials in place.

- Waste disposal bins are used.

- Buffer stock of medicines and commodities not maintained. Buffer stock of condom could not be maintained because stock out was reported from source (DAPCU/ CMO).

- Adequate IEC and BCC materials, Condom demo-models, plastic puncture proof container available at the TI DIC.

- Board games (carom) and TV sets available for recreation.

- Documentation and Reporting:

- All 17 formats for data collection in use.

- PE’s submit their reports to their respective ORW on a weekly basis.

- Review meeting done on a weekly and monthly basis and actions are taken as per the gaps and achievements for each staffs and PEs.

- Action plans are developed for each staffs and PEs after every review meetings.

- SIMS submitted to NSACS every month.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 269 (1 expired) | 268 |
| Line listed HRGs | 268 | 268 |

- Line listing / Mater Register maintained and updated.

2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counselling.

Not applicable

3. Registration of truckers from 2 service sources i.e. STI clinics and counselling.

Not applicable

4. Micro planning in place and the same is reflected in Quality and documentation.

- Micro planning and outreach plans done during weekly and monthly meetings.

- Micro plan for each hotspot available and tracking of commodity distribution and referral to ICTC and syphilis testing done.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 269 (1 expired) | 268 |
| Line listed HRGs | 268 | 268 |
| Nos. of active HRG | 268 | 268 |
| Regular contact (20 days in every month) | Nil | Nil |
| New HRGs registered | Nil | Nil |

6. Outreach planning – quality, documentation and reflection in implementation

- Monthly plan for outreach in place.

- Work plan is done on a weekly basis. Program Manager conducts two field visits in a month (New formats has been developed to capture details of his field visit). ORW conduct 4-5 field visits weekly and Nurse Conduct field visit once in a week.

- Coordination meeting between Nurse, ORWs and PEs done on a weekly basis and actions are taken based on gaps and achievements.

- ORW provide supportive supervision to their respective PEs. Based on PE needs, ORW conducts FGDs at the hotspot level.

- Weekly and monthly meeting minutes/ details are documented and updated regularly. More details required on numbers of HRG participants, review details of last week’s outreach target, feedbacks from PD and staffs, action taken, etc.

7. PE: HRG ratio:

- Ratio of PE to HRG is 1:30 for IDU as per contract agreements

8. Regular contacts

- None of the registered HRGs could be contacted 20 days in every month for delivery of any project related services as daily distribution for commodity is required by HRGs. However all line listed HRGs has been provided with project services.

9. Documentation of the peer education

- Peer field dairies and Form B in use by PEs to capture their field activities.

- Peer dairies reflect nature of outreach: topic discussed and number of HRGs contacted. Quantity of N/S and condom distributed, numbers of HRGs referred for HIV and Syphilis testing is also reflected.

10. Quality of peer education- messages, skills and reflection in the community

- Hotspot level meetings are conducted at least 2-4 times in a month to increase the knowledge level among the community members. A total of 75 FGDs were conducted at the hotspot and DIC level.

- Formats developed to capture details/ minutes of discussion. More details required- Topics, feedback by community members and attendance of HRG participant in the group meeting.

- Community members have basic knowledge of HIV, proper condom usage and safe injecting practices.

- Community members have availed project services from the TI DIC and other health care service providers.

11. Supervision- mechanism, process, follow-up in action taken etc

- Supportive supervision is carried out by the Program Manager two times on a monthly basis. Supervisory visit details- nature of supervision, topic discussed and actions taken were captured in a new formats developed by the PM. ORWs and each PE’s are oriented on outreach skills, rapport building, etc., whenever field visits are conducted.

- PE’s are supervised by their respective ORWs at the field level and in documentation.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- Static STI clinic established at TI DIC and all STI cases are handled by part time Doctor and Nurse from the clinic.

- Part time Doctor visit’s STI clinic on a weekly basis and is on call whenever need arises. Doctor is from a drug using background and understands the needs and problems of HRGs.

- Nurse/ ANM newly appointed on February 2016 and is yet to be trained on Syndromic case Management and Counselling skills.

- No STI medicine Kits were available at the clinic.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Separate room for STI Clinic cum counselling has been established at TI DIC.

- Basic clinical equipment’s and furniture in place.

- Waste Disposal bins, abscess prevention and management materials are available at the clinic.

- Network Clinic Formats in place.

- No STI medicine Kits available. Stock out of STI medicines observed. No reactive case of syphilis reported during assessment period.

- Buffer stock of commodities and medicines not maintained.

- Waste Disposal mechanism in place but collection and final disposal is not done as per NACO guidelines. Instances of PEs returning used N/S in poly bags or wrapped in newspaper were reported. Disposal of used N/S in septic tanks were also reported by PEs.

- Final disposal of used N/S after disinfection is done at CHC which has incinerator facility.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not applicable

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- Nurse/ ANM not yet trained on Syndromic case Management and basic Counselling skills.

- Syndromic case Management chart in place at the clinic.

- Network Clinic Format available at the STI Clinic.

- Information about individual HRGs to be followed-up (ICTC, RMC, Syphilis) is shared during weekly review meetings and action plans are developed based on it. Weekly field reports are used for follow up on referrals.

- HIV testing is referred to Mobile ICTC (which visits TI coverage area 1-2 times in a month) or CHC Chuchuyimlang (5-8 Kms. away).

- Linkages have been established at IMDH, Mokokchung Town for ART referrals and all positive HRGs are referred to this ART Centre.

- HIV testing is referred to Mobile ICTC and CHC Changtongya.

- Linkages have been established with RNTCP centre at CHC for DOTs

- Abscess prevention and management materials are available at the STI clinic..

5. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- Network Clinic Formats/ Registers used by TI NGO. All clinic registers in place and used.

- Standard Referral slips in use and properly tracked.

- Stock registers of medicines are maintained and updated regularly.

- STI medicines and Syphilis testing kits are procured from NSACS. Indent Register are maintained for requisitioning STI medicines and Syphilis kits from NSACS.

- Stock registers of condom, N/S and medicines are maintained.

- TI NGO purchase STI medicines Kits from NSACS. Indent Register are also maintained for requisitioning STI medicines and syphilis testing kits from NSACS.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Free condoms are distributed by PE’s, ORWs and from TI DIC.

- Community members expressed that they get condom as and whenever they require/demand.

- Stock out reported due to non- availability of stock at source (DAPCU/CMO).

- Condom Social Marketing has also been initiated by the TI project.

7.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

- Free condom:

A total of 39531 free condoms were distributed against a requirement of 40014 condoms (99% distribution achieved against requirement).

- Condom Social Marketing:

A total of 475 branded condoms were sold to community members through social marketing.

8. No. of Needles / Syringes distributed through outreach / DIC.

- A total of 62850 N/S was distributed against a requirement of 63813 N/S during the assessment period (April 2015- January 2016).

- A total of 47825 used N/S were returned (76% return rate achieved).

9. Information on linkages for ICTC, DOT, ART, STI clinics.

- Static clinic is established at TI DIC.

- Referral Directory is maintained with service providers and contact details of ICTC, OST, ART and CHC.

- The project has linkages with both static and mobile ICTC and HIV testing is done both at CHC Chuchuyimlang and Mobile ICTC.

10. Referrals and follows up

- All HIV and syphilis testing are referred toCHC Chuchuyimlang and Mobile ICTC. Follow up actions are initiated by the Nurse during every weekly and monthly review meetings.

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- Crisis Management Team (CMT) established with project staff members and representation from paralegal body (advocate) and Village Council Chairman.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members involved in the project as PEs and ORWs. Activities include outreach, commodity distribution, referrals and conduct of FGD.

- All activities documented in their respective field diaries and formats.

- 44% of registered HRGs participated in 25 awareness program. Awareness programs conducted once a month. Two important events were observed but numbers of HRG participants was not documented.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- Static clinic is established at TI DIC.

- Referral Directory is maintained with service providers and contact details of ICTC, OST, ART and CHC.

- 260 out of 268 registered HRGs underwent Syphilis testing. (97%)

- The project has established linkages with both static and mobile ICTC and all HIV and Syphilis testing is done both at CHC Chuchuyimlang and Mobile ICTC.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

- 260 out of 268 registered HRGs underwent HIV testing at least once during the last one year (97%).

- On an average, 99% of line listed HRGs were referred for HIV testing and 64% had undergone HIV testing twice in a year.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

The Organisation has a good visibility in the target coverage areas as a result of extensive advocacy activity carried out since inception of project in the area. Stakeholders participated in awareness programs and are familiar about project related activities and services available at the TI project site.

VII. Financial systems and procedures

1. Systems of planning:

- All the Planning & decision making is done by the Director, accountant and executive Members of the Organization. Planning is also done according to the prescribed system endorsed by SACS & NACO.

- Budget Utilization is more than 60% against the released fund and all expenditures are within approved budget in all budget head.

- NGO has taken adequate measures to comply to audit observations.

2. Systems of payments:

- The NGO is practising a system of getting approval from PD before any transaction/ payments.

- All payments are made with proper bills and vouchers, but majority of bills are ‘katcha’.

- All cash payments beyond ₹ 5000/- was done through cheques.

- Cash in hand sometimes exceeds the limit of ₹ 5000/-

3. Systems of procurement:

- Purchase of drugs is done as per GMP guide line.

- Quotations were taken for procurement of assets and commodities.

4. Systems of documentation:

- No banking facility available in project site. Separate bank A/c is maintained at Mokokchung Town.

- Vouchers are printed and machine numbered, but ledger is not maintained for vouchers.

- Cash book is updated on a daily basis.

- SOE is submitted in time.

- No mismatch found in physical and financial reporting. Audit report is in place.

- Assets register is properly maintained and all assets are marked and codified.

VIII. Competency of the project staff

VIII a. Project Manager

- Program Manager was appointed as ORW in the TI project in 2005 and continued till 2008. He graduated to Accountant in 2008-09 project years and was promoted to Program in 2009.

- The PM is familiar with the proposal and Quarterly Plan and program performance indicators. Conducts Weekly & Monthly review meetings and prepares Weekly &Monthly Plan for the Project along with all the staff.

- Has basic knowledge on financial management and is skilled in computerization and management of data.

- PM undertakes field visit twice monthly for Supervision and Monitoring: Supervisory field visit details captured in new formats.

VIII b. ANM/ Counsellor in IDU TI

- Nurse newly appointed in February 2016. In-house orientation on data collection tools given by Program Manager.

VIII c. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

| Name of ORW | Training organised by | Topics Covered |
| --- | --- | --- |
| MOATOSHI | LS_MKG-CSS | Harm Reduction |
|  | LS_MKG-CSS | ORW Refresher Training |
| TEMSHI | LS_MKG-CSS | Harm Reduction |
|  | LS_MKG-CSS | ORW Refresher Training |

- Monitoring of PEs is done by the ORW. Outreach planning is done in consultation with their respective PEs or as per need based.

- Understands hotspot analysis and able to explain it.

- ORWs have basic knowledge of STI symptoms.

- Supportive supervision is done based on needs and ORWs conducts FGD meetings at the hotspots.

- Capacity building on rapport building, condom demonstration, safer injecting practise, abstinence, OST and overdose prevention are imparted.

VIII d. Peer educators in IDU TI

- Prioritisation is done as per demand for commodities by HRGs and referral for HIV testing.

- Possesses fair condom demonstration skills and have basic knowledge on common symptomatic STI.

- Has basic awareness on the importance of blood testing for HIV and STI.

- Have a fair knowledge about various health care service provider and centres

IX. a. Outreach activity in Core TI project

Services are given to HRGs based on commodity distribution, referrals and HIV and Syphilis testing.

Micro plans in place for each hotspots and prioritisation of outreach is done based on demand for commodity and uptake for referrals services. Individual HRGs are tracked for ICTC and syphilis testing. Micro plans are updated on a quarterly basis.

X. Services

Overall uptake of Project service and quality of service delivery (Free Condom & N/S) was well accepted by the HRGs.

| Services | Apr 2014- March 2015 | April 2015- Jan. 2016 |
| --- | --- | --- |
| Nos. of HRGs provided Counselling | 269 | 268 |
| Total nos. of HRGs referred for HIV testing | 267 | 266 |
| HIV Testing (Twice in a year) | 220 | 129 |
| Syphilis Testing (Twice in a year) | 255 | 128 |
| Abscess | 5 | 5 |
| Condom distributed | 21078 | 18453 |
| CSM |  | 475 |
| N/S distributed | 35971 | 26879 |
| Used N/S returned | 26960 | 20865 |

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- Two [n=2] ORWs on board and both are from user background. They are also involved during project planning and development of project proposal.

- Advocacies are conducted as per needs. None conducted during assessment period as general community and stakeholders were already sensitized about project activities since inception of TI project in the area..

XII. Commodities

- Planning for meeting the demand of condom and N/S done at the project level on a quarterly, monthly and weekly basis.

- Demand analysis done based on distribution during the previous month or quarter.

XIII. Enabling environment

- Advocacy done as per needs of the community when faced with crisis.

- Systematic planning for advocacy not in place and followed-up on advocacies are not done.

- Good networking with key stakeholders established.

- Linkages to various service providers have been established to help community members’ access basic health care.

- Community Members happy with the project for sensitising the public about the issues of HRGs and creating linkages to various service providers.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

None implemented.

Confidential                                      Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Kholi. A (Team Leader) | +91 9862797996 |
| Kivileme Visezuo (External Evaluator) | +91 9774978143 |
| Raju Gupta (Finance Evaluator) | +91 7085169800 |
| Officials from SACS/TSU (as facilitator) Ms. Imtisenla | +91 9856534957 |

| Name of the NGO: | Grace Society, Akhoya |
| --- | --- |
| Typology of target population | Core(IDU) |
| Total population being covered against target: | April 2014- March 2015:; April 2015 - Jan. 2016. Target; 269 (1 expired); 268. Achievement; 268; 268. |
| Dates of Visit: | 27th-28th February 2016 |
| Place of Visit: | Grace Society DIC, Akhoya |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 78.5% | B | Good | Recommended for Continuation |

Specific Recommendations:

Organizational capacity: - TI NGO can include signature of staffs in contract/ appointment/ renewal letters. - Nurse appointed on February 2016 and needs to be trained. In-house orientation has been provided by Program Manager. - 3 PEs yet to be called for training from Learning Sites (Care and Support Society). In-house orientation given. - Involvement of Project Director / Management Body required during Monthly Staff Review meeting to monitor project activities. Constructive feedbacks could be reflected in meeting minutes. - TI NGO/ NSACS should ensure that Form B is made available for PEs which is out of stock. PEs currently using Form C to capture field related data. - Involve stakeholders in project planning and implementation. - Organisation can try to link up community members to welfare schemes. - Insurance policy provision for TI staffs would be an added advantage. Financial management: - Bank Account should be opened at the nearest facility available to cut time and cost on transportation. - Cash transaction above ₹ 5000/- should be done with cheques as far as possible. - Maintain a separate ledger for vouchers. - Cash-in-hand should be less than ₹ 5000. Program Delivery: - Proper Advocacy plan at all level needs to be in place and followed-up. - Regular contact to be scaled up as 1 PE is covering only 30 HRGs. - Encourage scaling up of HIV testing.Ensure that all referrals for RMC, STI and HIV are followed-up. - Encourage HRGs to return back used N/S for proper disinfection and for final disposal as per guideline. - Ensure that all PEs collect and bring back used N/S in puncture proof containers as incidence of PE s bring back used N/S wrapped in papers or disposing it in septic tank was reported. - More detail needs to be capturedin staff review meeting: numbers of HRG participants, review details of last week’s outreach target, feedbacks from PD and staffs, action taken, etc. - Group meeting at DIC/ hotspot level need to capture details on agenda, topic covered, feedbacks from community members and attendance of HRG participant in the group meetings. - TI NGO should ensure that all STI medicines are available at Clinic and no stock out should occur. - Buffer stock of commodities and medicines should be ensured. - Encourage HRGs to join in OST program. - Encourage collectivisation and formation of support groups to empower community member.

Name of the Evaluators				Signature

| Kholi. A |  |
| --- | --- |
| Kevileme Visezuo |  |
| Raju Gupta |  |