Nagaland State AIDS Control Society

Targeted Intervention - Evaluation Report

April 2014- January 2016

Grace Society

MSM

Guardian Angel

Mokokchung District

Evaluation team:

- Mr. Kholi. A		: Team Leader, External Evaluator

- Mr.Kevileme Visezuo : External Evaluator

- Mr. Raju Gupta	: Finance Evaluator

Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

OBackground of Project and Organisation

Guardian Angel, was established in the year 1991, with its head office at Dimapur. The organization is also registered under the Societies Registration Act 1860 as amended vide Registation of Societies Act 1969; and is also registered under the Foreign Contribution Regualtion Act (FCRA). The organization is also a member of the N-Naga Dao, an apex body of NGOs working in the field of HIV and AIDS in Nagaland. With its head office in Dimapur, the organization has extended it working capabilities in the other district of Kohima and Mokokchung.

The organization focuses on working with the high risk groups of men having sex with men (MSM) in the three districts of Dimapur, Kohima and Mokokchung, with the support from Nagaland State AIDS Control Society. Since 2009, the organization have been working in this area and providing the MSM community with service and commodities from the TI Project.

O Name and address of the Organization

Guardian Angel

Post Box 428,

Dimapur- 797112,

Nagaland

OR

Guardian Angel,

2nd Floor, Above Indian Airlines Office,

Opp. State Bank of India (Main Branch),

Dimapur – 797112, Nagaland

O Chief Functionary:Mrs.Inatoli Choppy

O Year of establishment:1991

O Year and month of project initiation:

2004-2008 (Project Orchid)

September 2009 (Transitioned to NSACS)

OEvaluation team:

- Kholi. A (External Evaluator)

- Kevileme Visezuo(External Evaluator)

- Raju Gupta (External Finance Evaluator)

OTime frame:

Date of evaluation: 	23-24th February 2016

Assessment Period: 	April 2014- January 2016 [22 months]

Profile of TI

(Information to be captured)

OTarget Population Profile:Men having Sex with Men (MSM)

OType of Project:Core Group (MSM)

OSize of Target Group(s)

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 350 | 350 |
| Achievement | 350 | 351 |

O Sub-Groups and their Size: Not applicable

OTarget Area:

| Sl. No. | Name of the Coverage area |
| --- | --- |
| 1 | Artang Ward |
| 2 | Majakong Ward |
| 3 | Penli Ward |
| 4 | Sangtemla Ward |
| 5 | Arkong&Salangtem |
| 6 | Mongsenbai |
| 7 | Kumlong Ward |
| 8 | Aongza Ward |
| 9 | Kichutip&Yimyu |
| 10 | Other village (west) |
| 11 | Longmisa Village |
| 12 | Alempang Ward |
| 13 | Dilong Ward |
| 14 | Mobiles |
| 15 | Tongdentsiiyong Ward |
| 16 | Alongmen Ward |
| 17 | Mokokchung Compound |
| 18 | Other Villages (East) |
| 19 | Sungkomen Ward |
| 20 | Tsiisapang Ward |
| 21 | Chuchuyimlang Village |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

The overall organizational support of “Guardian Angel” towards the TI Project in Mokokchung, is very supportive and cooperative towards the MSM community and also those community members living with HIV and AIDS.  The organziation’s chief functionary is very much commited to the cause and issues faced by the MSM community in Mokokchung, Dimapur and Kohima as a whole. The organization have been working for and propagating the rights of the MSM communities in various platforms and aspects.

Although committed to the cause of the target population (MSM) the overall organizational support to the project in Mokokchung, is not available; The Board / Organization members involvement in any of the the Project’s activities in the TI Project at Mokokchung is not visible in the Project. The TI Project’s activities is being managed and implemented by the PM, Nurse, Accountant and Outreach Team based on their understanding and capacity, without the supervision or monitoring of the TI Project Director.

The overall management, accounting and control of the TI Project are being done at Dimapur, where the head office is based.

II. Organizational Capacity

1. Human resources:

- Appointments of staffs aredone by the Governing Body.

- PEs and ORWs belongs to MSM community.

- Peer progression mechanism followed. PE graduated to ORW.

- Weekly and monthly reporting structure in place and monitored. Performance of each staffs and PEs is assessed on a weekly and monthly basis.

- 42.8% PE turnover [n=3 out of 7]witnessed during the project year (April 2014-Jan. 2016).

- Project Director attended only 1 meeting during the assessment period.

| Sl. No | Name | Designation | Date of Appointment. |
| --- | --- | --- | --- |
| 1. | Ms. Inatoli Choppy | Project Director | Since the beginning of the TI Project [ 2009] |
| 2. | Tiakala | Programme Manager | 1st August 2013 |
| 3. | Tiasunep | Accountant cum M&E | 1st April 2013 |
| 4. | Koramenla | Nurse | 1st August 2013 |
| 5. | Moasenup | ORW | 1st April 2013 |
| 6. | Alikaba | ORW | 1st April 2013 |
| 7. | Dr.Bendang | Doctor [ Part Time] | Not available, only verbally from the doctor himself, that he was involved since August 2013. |
| 8. | Moaramok | PE | 1st Sept. 2009 |
| 9. | Moachuba | PE | 1st Feb 2013 |
| 10. | S. Yanger | PE | 1st April 2014 |
| 11. | Moatenzuk | PE | 1st Nov. 2014 |
| 12. | Wangshi | PE | 1st March 2015 |
| 13. | Pibeto | PE | 1st Jan. 2016 |
| 14. | Zuluba | PE | 1st Feb 2016 |

2. Capacity building:

List of training details-

| Name | Designation | Topics Covered | Training given by |
| --- | --- | --- | --- |
| Tiakala | Program Manager | Program Management | STRC |
|  |  | Data Collection Tools | STRC |
|  |  | Capacity Building Training for MSM CBO Staff | Humsafar Trust |
|  |  | NACO Operational Guideline for MSM Tis | Humsafar Trust |
| Tiasunep | Accountant cum M&E | SIMS Training | NSACS |
|  |  | Financial Management | STRC |
|  |  | Program Management and Financial Management | Humsafar Trust |
|  |  | NACO Operational Guideline for MSM Tis | Humsafar Trust |
| Koramenla | Nurse | SIMS Training | NSACS |
|  |  | Counselling & SCM- STI | STRC |
|  |  | Orientation Training on STI/ RTI | NSACS |
|  |  | Capacity Building Training for MSM CBO Staff | Humsafar Trust |
|  |  | NACO Operational Guideline for MSM Tis | Humsafar Trust |
| Moasunep | ORW | Positive Prevention for MSM | Humsafar Trust |
|  |  | Capacity Building Training for MSM CBO Staff | Humsafar Trust |
|  |  | Program Management and Financial Management | Humsafar Trust |
|  |  | NACO Operational Guideline for MSM Tis | Humsafar Trust |
| Alikaba | ORW | Capacity Building Training for MSM CBO Staff | Humsafar Trust |
| Moachuba | PE | Capacity Building Training for MSM CBO Staff | Humsafar Trust |
| Maramok | PE |  |  |
| Moatenzuk | PE |  |  |
| Wangshi | PE |  |  |
| S. Yanger | PE |  |  |

- Two PEs recently appointed and missed training but given in-house orientation.

3. Infrastructure of the organization:

- The TI DIC has 3 rooms (PM cum Accountant’s room, STI clinic observation cum counselling room, ORWs reporting room cum recreation room.

- Basic office furniture’s are in place.

- Computer, laptops, TV &DVD Player, printer and lockers in place.

- Static STI clinic set up and in place. Clinical equipment’s, weighing machines, STI medicines, disinfectants, gloves and colour coded waste disposal bins in place.

- Adequate IEC and BCC materials, Condom demo-models available at TI DIC.

- Board games (carom) and TV sets available for recreation.

- Documentation and Reporting:

- All 17 formats for data collection in use.

- PE’s submit their reports to their respective ORW on a weekly basis.

- Review meeting done on a weekly and monthly basis and actions are taken as per the gaps and achievements for each staffs and PEs.

- Review mechanism partially witnessed. Regular follow up mechanism and ORWs monitoring and supportive supervision systems not in place.

- Action plans are developed for each staffs and PEs after every review meetings.

- Mismatch found  from Form B and Form C

- Feedback and compliances to audit observations were not witnessed.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 350 | 350 |
| Achievement | 350 (1 expired) | 351 |

O Sub-Groups and their Size: Not Applicable

2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counselling.

Not applicable

3. Registration of truckers from 2 service sources i.e. STI clinics and counselling.

Not applicable

4. Micro planning in place and the same is reflected in Quality and documentation.

- Micro planning and outreach plans done during weekly and monthly meetings but use and implementation of micro plan are not reflected in the activities of the ORWs or in their documentation.

- Risk assessment and prioritization of HRGs have also not been done by the TI project

5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 350 | 350 |
| Achievement | 350 (1 expired) | 351 |
| Nos. of New HRGs | 0 | 1 |
| Nos. of active HRGs | 331 | 333 |
| Nos. of active HRGs who underwent RMC twice | 330 | 322 |
| Nos. of active HRGs who underwent RMC Three times | 273 | 268 |
| Four times | 141 | 102 |

- Active HRGs were provided with project services on a regular basis.

6. Outreach planning

- Work plan for PE done on a weekly basis.

- Monthly plan for outreach in place.

- Tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization and proper planning.

- Coordination meeting between Nurse and ORWs done on a weekly basis and actions are taken based on gaps or achievements.

7. PE: HRG ratio:

- Ratio of PE to HRG is 1:50 as per contract agreement. Target is 350 MSM and 7 PEs are on board.

8. Regular contacts

- On an average, 326 out of 332 active HRGs [96%] were contacted twice and provided Regular Medical Check-up and other project services.

9. Documentation of the peer education

- Peer field dairies and Form B in use by PEs to capture their field activities. However, most of the PE’s are illiterate and not maintaining their log book properly. ORW assists them in data entries in Form B.

- The level of understanding among the PEs in terms of risk assessment, vulnerability and prioritization of the HRGs is limited.

10. Quality of peer education- messages, skills and reflection in the community

- Hotspot level meetings are conductedat least twice in a month to increase the knowledge level among the community members. Community members have basic knowledge of HIV, and proper and consistent usage of condom and lubes.

- Community members are also aware of services available at the TI DIC and other health care service providers.

11. Supervision- mechanism, process, follow-up in action taken etc

Supportive supervision is carried out by the ORWs and each PE’s are oriented on outreach skills, rapport building, etc., whenever field visits are conducted. Overall supervision of outreach is done by the Program Manager.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- Static STI has been established managed by the Nurse and has established linkage to one visiting Doctor, who is available on call. The clinic has adequate infrastructure and clinic equipment’s in place and has provision for handling STIs. The TI is linked with Mobile ICTC for HIV testing, however the follow up mechanism is weak.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Separate room for STI Clinic established at TI DIC.

- Basic clinical equipment’s and furniture in place.

- Clinic Network Formats in place and updated regularly.

- Stock out of STI medicines observed. Only Kit-I available.

- Buffer stock of commodities and medicines not maintained.

- Clinic information’s are kept confidential by the nurse.

- Colour coded Waste Disposal bins are in place as per NACO guidelines.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not applicable

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- TI’s STI clinic has a separate room which is partitioned into counselling room cum observation room. Privacy is being maintained.

- Clinical equipment’s are available in the STI Clinic, with adequate supply of medicines. The TI is also linked to a private clinic run by the visiting Doctor of the TI Clinic, where tests and linkages for syndromic cases are being treated.

- HIV testing is referred to Mobile ICTC and IMDH, Mokokchung.

- Mechanism of follow -up on ICTC, RMC and STIs are done as perORWs and PEs reports.

- 97% of the HRGs were provided counselling.

- 96% of the active HRGs were given RMC.

- 63% underwent syphilis testing twice is the last one year.

- 93.42% underwent Syphilis testing at least one during the last one year.

- 39.5% underwent HIV testing twice.

- 93.42% tested at least once during the last one year.

- One positive case of HIV was linked to ART.

5. Documentation-

- All Clinic Network Formats/ Registers used by TI NGO.

- Standard Referral slips in use and properly tracked.

- Stock registers of condom, Lubes and medicines are maintained.

- TI NGO receives STI medicines Kits from NACO/SACS. Indent Register also maintained for requisitioning STI medicines from NSACS.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Free condoms and lubes are distributed by PE’s and staffs of TI DIC. No secondary distribution outlets have been created.

- Social Condom Marketing (SCM) was initiated to cater to the needs of the community members.

- Community members reported that they get free condoms as and when they demand.  No shortage has been reported during the assessment period.

7.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

| Distribution of Commodity | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| Free Condom | 60122 | 56553 |
| Lubes | 40572 | 38568 |
| Social Marketing of condom | 500 | 690 |

8. No. of Needles / Syringes distributed through outreach / DIC.

Not applicable

9. Information on linkages for ICTC, DOT, ART, STI clinics.

- Linkages for Syndromic STI treatment from project STI Clinic and the Mobile ICTC has been effective with 63% of HRGs havingundergone Syphilis testing and 39.5% HRGs having undergone HIV testing out of which 1 HIV+vecase was detected and linked to ART Centre.

- RNTCP referrals and awareness among the HRGs have not been done by the TI Project; however it may be noted that no cases were detected for TB during the assessment period.

10. Referrals and follows up

- All HIV and syphilis testing are referred to mobile ICTC and fixed ICTC at IMDH, Mokokchung. Follow up actions are initiated by the Nurse during every weekly and monthly review meetings.

V. Community participation

1. Collectivization activities:

- Crisis Management Team has been established with Program Manager, 2 ORWs   and 7 PEs as members.

- One DIC Committee formed with 10 HRGs, 4 PEs and 1 ORW.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members involved in the project as PEs and ORWs. Activities include outreach, commodity distribution, referrals and conduct of FGD.

- All activities documented in their respective formats.

- 2 community events [picnic] was organised during the assessment period and a total of 38 HRGs participated.

- The overall community participation in the Project is low. Although all the PEs and ORWsare from the community, they have not been able to involve the MSM community at large in various activities and events of the TI Project.  The issue of Stigma and discrimination is very prominent in the societyand therefore, it is difficult for the MSM community to openly talk or discussed about their issues and concerns.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- The TI Project has established links with Mobile ICTC, STI clinic (Private) ,ART Centre and RNTCP Centre. More emphasis needs to be done to create and establish linkages with the CHC and the static ICTC centre.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

- 92.43% of the total registered HRGs were referred for HIV testing out of which 39.5% have undergone HIV testing.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- The TI Project has created support system only on clinical service delivery with the Mobile ICTC and ART centre.

- Linkages and advocacy initiative with other stakeholders is limited with only 5 advocacy conducted during assessment period.

VII. Financial systems and procedures

1. Systems of planning:

- The organization/management is allowing the Project Office to prepare the books of accounts every month as per the budget allotment and schedule provided by NSACS.Budget Utilization is more than 60% against the released fund and all expenditures are within approved budget in all budget head.

- NGO has not taken any measures to comply to audit observations.

2. Systems of payments-

- The NGO is practising a system of getting approval from PD before any transaction/ payments.

- All payments are made with proper bills and vouchers, but majority of bills are ‘katcha’.

- Cash payments beyond ₹ 5000/- was witnessed.

- Cash in hand sometimes exceeds the limit of ₹ 5000/-

3. Systems of procurement-

- Purchase of drugs is done as per GMP guide line.

- Quotations were not taken for procurement of assets.

4. Systems of documentation-

- Separate bank A/c is in place for TI project in the project area.

- Vouchers are printed and machine numbered, but ledger is not maintained for vouchers.

- Cash book is not updated on a daily basis.

- SOE is submitted in time.

- Mismatch found between physical and financial reporting. Many at time cash balance is showing negative value/ amount.

- Audit report is in place.

- Assets register is not properly maintained and assets are marked without proper codification.

VIII. Competency of the project staff

VIII a. Project Manager

- Program Manager graduated from Nurse and took over responsibility from 1st August 2013.

- Program Manager has been trained on Program Management, Data Collection Tools, NACO Operational Guideline and Capacity Building Training for MSM.

- The capacity, skill and knowledge of the Program Manager in planning, financial management, computerization and management of data are limited.

VIII b. Counsellor/ ANM

- Nurse is an ANM and has been working at TI Project since 1st of August 2013.

- Nurse has been trained onSIMS, Counselling & SCM- STI/ RTI, Capacity Building Training for MSM and NACO Operational Guideline.

- Is able to explain risk assessment and risk reduction processes.

- Is able to give basic counselling on HIV and STI.

- All registers and clinic formats maintained and updated.

- Conducts field visit as per needs from the community member: accompanied referrals and for taking CD4 counting.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

- Two ORWs on board and belongs to MSM community.  Both have been working in TI project for more than 2 years. One has graduated from PE.

- ORW has attended trainings on: Positive Prevention for MSM, Capacity Building Training for MSM CBO Staff, Program Management and Financial Management, NACO Operational Guideline for MSM TI’s and Capacity Building Training for MSM CBO Staff.

- Monitoring of PEs is done by the ORW and key performance indicators are closely checked. Outreach planning is done in consultation with their respective PEs or as per need based.

- Has limited understanding on hotspot analysis.

- ORWs have basic knowledge of STI symptoms.

- Supportive supervision is done based on needs and ORWs conducts FGD meetings at the hotspots.

- Mentoring and message on rapport building, condom demonstration and safe sex practise are imparted.

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

- Some of the Peer Educators have been trained by Humsafar Trust; however due to frequent turnover of PEs in the TI Project of some of the PEs have not been trained. In-house training has been given by the project staffs.

- Prioritisation of outreach is done based on demand for commodities by HRGs and referral for RMC, Syphilis and HIV testing.

- Possesses fair condom demonstration skills and have basic knowledge on common symptomatic STI.

- Have a fair knowledge about various health care service provider and centres.

VIII f. Peer educators in IDU TI

Not applicable

VIII h. Peer Educators in Truckers Project

Not Applicable

VIII i. M&E officer

Not applicable

IX. a. Outreach activity in Core TI project

- Project services are given to HRGs based on commodity distribution, referrals for RMC and HIV/ Syphilis testing. Outreach activities have not been prioritised in a planned manner: it has been set to achieve specific targets (commodity distribution and referral targets).

- Individual HRGs are tracked for ICTC and syphilis testing. Micro plans are based on these parameters and updated on a quarterly basis.

IX. b. Outreach activity in Truckers and Migrant Project

Not applicable

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

Overall uptake of Project servicesand quality of service delivery (Free Condom & Lubes)was well accepted by the HRGs. Linkage to private clinic for STI and Mobile ICTC for referrals was also preferred by the HRG, as they do not have to visit the hospital and exposetheir identity

Organising medical camp at hotspot/ sites was appreciated by the HRGs.

| Services | Apr 2014- March 2015 | April 2015- Jan. 2016 |
| --- | --- | --- |
| Nos. of HRGs provided Counselling | 331 | 333 |
| Total nos. of HRGs referred for HIV testing | 340 | 430 |
| HIV Testing (Twice in a year) | 156 | 121 |
| Syphilis Testing (Twice in a year) | 331 | 322 |
| RMC | 330 | 322 |
| Presumptive Treatment | 1 | None |
| Condom distributed | 60122 | 56553 |
| Jelly | 40572 | 38568 |
| CSM | 500 | 690 |

XI. Community involvement

- Two [n=2] ORWs are from the HRG background. They are also involved during project planning and development of project proposal.

- Advocacies are conducted as per needs. Supporting documents are maintained.

- A total of five [n=5] advocacies were conducted to address issues of community members.

XII. Commodities

- Planning for meeting the demand of condom and N/S done at the project level on a quarterly, monthly and weekly basis.

- Demand analysis done based on distribution of previous month or quarter.

XIII. Enabling environment

- Advocacy done as per needs of the community when faced with crisis.

- Community Members happy with the project for sensitising the general community about the project activities and creating linkages to various service providers.

- Systematic plan and involvement of the community in advocacy, networking and linkages is not witness.

- Advocacy on the issues of MSMs, among the stakeholders in Mokokchung under the TI project have been done with only a few of the Ward Chairman where the TI Office cum DIC is situated, and a few of the neighbouring shopkeepers / people living within and around the project office. The Project / Organization have not expanded their Advocacy programmes in creating awareness or making the community at large understand the issues of MSMs.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- None initiated. Project Director stated that bankers are not willing to accept proposal of insurance policy for small amount (₹ 500/-).

Confidential                                      Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Kholi. A | +91 9862797996 |
| Kevileme Visezuo | +91 9774978143 |
| Raju Gupta | +91 7085169800 |
| Officials from SACS/TSU (as facilitator) Ms. Imtisenla | +91 9856534957 |

| Name of the NGO: | Guardian Angel, Mokokchung. |
| --- | --- |
| Typology of target population | CoreGroup (MSM) |
| Total population being covered against target: | April 2014- March 2015:; April 2015 - Jan. 2016. Target; 350; 350. Achievement; 350; 351. |
| Dates of Visit: | 23rd- 24th February 2016 |
| Place of Visit: | Project office of Guardian Angel, Mokokchung. |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 74.6% | B | Good | Recommended for |

Specific Recommendations:

Organizational capacity: - The organization must relook on their program implementation and capacitate, empower and sensitized the MSM community and also advocate on their behalf. - The capacity, skill and knowledge of the Program Manager need to be enhancedon financial management, computerization and management of data, review of meetings, advocacy and mentoring skill. - PEs who cannot read or write needs to be capacitated on data collection using pictorial means. - Project Director should ensure his presence during monthly staffs review meetings to monitor progress of project activities. - All fixed assets need to be codified and accordingly tally with asset register. Financial management: - Cash payment should not exceed ₹ 5000/- as per NACO’ directive. - All Vouchers should be supported by a ledger. - Cash book should be updated on a daily basis. - Minimize mismatch between physical and financial reporting. - NGO should take adequate measures and comply to audit observation and recommendations. - Cash in hand should not exceed ₹ 5000/- as per NACO’s directive. - Proper quotations should be taken for purchase of commodity or assets to ensure quality and cost effectiveness. Program Delivery: - Outreach activities in the TI level needs to be re-evaluated and Micro plans for all hotspots/ sites should be in place. Risk and vulnerability assessment needs to be updated periodically and should be prioritised. - ORWs need to be in the field at least 4-5 days in a week. - ORW should ensure that at least all hotspots are covered every month and conduct at least 2 FGDs monthly. - Buffer stock of commodities needs to be maintained. - Involvement of the Nurse at the field level and frequency needs to be increased to scale up intake of project services and referrals. - ICTC and STI referrals need to be scaled up, and ensure that actual testing is being done. - The Project / Organization need to expand their Advocacy programmes in creating awareness or making the community at large understand the issues of MSMs. - The organisation may endeavour to link community members to Welfare Schemes as many of them are creative and has potentials to expand their creativity into household brand.

Name of the Evaluators				Signature

| Kholi. A |  |
| --- | --- |
| Kevileme Visezuo |  |
| Raju Gupta |  |