Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organisation	:

Integrated Development Society (IDS), established in 2013 is a community based organization working in Tuensang district is implementing TI Projects in Tuensang Town and NAP areas since September 2010 with support from NSACS/DAC-NACO.

| Name and address of the Organization | : | Integrated Development Society (IDS) |
| --- | --- | --- |
| Chief Functionary | : | Mr. N. James Chang |
| Year of establishment | : | 2003 |
| Year and month of project initiation | : | September, 2010 |
| Evaluation team | : | - Mr. Jongpongciten, Team Leader - Mr. Kenyulo, 2nd Evaluator - Mr. Akhumtong Jamir, Finance Evaluator - Mr. Visheto Mekro, NSACS |
| Time frame | : | April 2014 – January 2016 |

| Profile of TI |  |  |
| --- | --- | --- |
| Target Population Profile | : | IDU |
| Type of Project | : | Core |
| Size of Target Group(s) | : | 330 IDUs and 240 SPs in 2014-15. 310 IDUs and 217 SPs in 2015-16. |
| Target Area | : | 11 interventions sites in 3rd NAP Camp area in Tuensang including Ngangpong Village. |

Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The NGO has a board and is accountable of making sure that the NGO has appropriately qualified, experienced, committed and motivated leaders.

There is significant involvement of the members of Governing Body in the project. All relevant stakeholders in the project areas, including decision-makers, influential individuals and groups, has been identified by the NGO and advocacy activities have been carried out held to facilitate enabling environment for the project. They are well aware of the issues of HRGs and are involved in resource mobilization, addressing crises and advocacy activities of the project.

The NGO has a very good coordination with Government Departments, Churches and Community groups in Tuensang district. NGO is also the facilitating agency for Building and Construction Workers Scheme under Department of Labour and Employment. The NGO has facilitated eligible HRGs linked to welfare schemes, registration in North East Rural Livelihood Project for vocational training, and imparted practical skills trainings in baking and flower making.

Project activities, finances and documentations of the staff and PEs are reviewed in the weekly and monthly meetings by the Project Director.

II. Organizational Capacity

1. 	Human resources

While all the project staff and PEs positions are filled as per the approved project there were repeated turnovers of staff and PEs witnessed in the project period. In 2014-15, positions M&E cum Accountant and an ORW was switched in June 2014 and the vacant position of ORW was filled. The visiting Doctor was also replaced in September 2014 since the doctor got transferred. In 2015-16, Nurse resigned on health and the visiting doctor replaced in 2014-15 was again replaced in July 2015 since the doctor went for higher study. Repeated turnovers and appointment of ORWs was reported in the same year. Most of them got other job and had to leave the town and 1 ORW who joined in June 2015 was affected by the communal tension in Tuensang Town and left the project in November 2015. 1 PE was promoted and filled vacancy of ORW position. In 2014-15, 3 PEs were replaced - 1 got married and moved to different location and 2 had to leave on health related grounds. In 2015-16 repeated turnovers and appointment of PEs was reported in the same year. Some got other job and had to leave the town and most were affected by the communal tension in Tuensang Town in 2015 which has affected PEs and HRGs of a community group in the project located in NAP than the other TIs in Tuensang district.

Defined job descriptions, signed contract & appointment agreement, attendance sheet and leave applications are properly maintained and available in DIC for all categories of staff and PEs.

Regular meetings are held (weekly/monthly) to report and review activities carried out and plan for project and site levels activities. Meeting minutes are well documented and available in DIC.

2. 	Capacity building

In-house induction has been completed for all the new PEs and ORWs and onsite mentoring is ongoing.

3. 	Infrastructure of the organization

Adequate physical infrastructure for the current and future needs of the project is located in 3rd NAP Camp. Separate rooms are available well-maintained for counseling and clinic services, M&E cum accountant and project manager, outreach team and recreational hall with table tennis, Carom. The drug dispensing counter is well maintained by the nurse.

4. 	Documentation and Reporting

The TI project adheres to forms, formats and registers prescribed by NACO/SACS and available in the project office.

Monthly review meetings held at the project level whereby activities of each staff and PEs are reviewed, provide feedbacks on the activities carried out and plan for the subsequent month.

Project activities and SOE reports are submitted in SIMS to NSACS through DAPCU in the first week of succeeding month.

Sharing of project reports and technical inputs takes place during the quarterly review meeting at DAPCU level and half-yearly and annual review meetings at NSACS level.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

Updated line list of registered HRGs available for all PEs.

- Micro planning in place and the same is reflected in Quality and documentation.

Micro plans in place for each hotspot and prioritization of each HRG are done by ORWs and nurse based on risk, vulnerability, due for clinic services and N/S and condom demand. Micro plans are updated on a quarterly basis.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

330 IDUs were registered against the target of 324 in 2014-15 and 315 against the target of 310 in 2015-16. 6 new HRGs registered in 2014-15 and 5 in 2015-16.

100% of 324 in 2014-15 and (92.39% (n=287) 311 in 2015-16 active population coverage by NSEP. Drop out of HRGs in 2014-15 was due to communal tensions occurred in Tuensang in 2015 which made HRGs to leave the town and in 2015-16 it was the death of 3 HRGs and transfer of 1 HRGs to other TI.

- Outreach planning

Outreach planning is done by the ORWs along with the PEs. Monthly plan for outreach is in place at the project level for all staff and PEs. Coordination meeting of Nurse and PEs is held on a weekly basis.

- PE: HRG ratio

There are 10 PEs in both the years for the target of 324 and 310 respectively as per approved project.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

While there are no daily or medium-high volume injectors among the HRGs, more than 80% of active HRGs have been contacted at least 4 times every month and provided N/S as per their requirement.

- Documentation of the peer education

Peer field dairies and Form B-1 is use by PEs to capture their field activities. However, most of the PEs are not maintaining their log book properly as they are unable to understand the indicators for referral (due and overdue).

- Quality of peer education- messages, skills and reflection in the community

The quality of outreach work has been found to be satisfactory as reported during interaction with community members. But PEs needs orientation on outreach planning and documentation.

- Supervision- mechanism, process, follow-up in action taken etc

As per the records all the three ORWs visiting their respective fields four to five times and have met all the PEs in the field. Since most of the PEs are new, onsite mentoring is ongoing.

IV. Services

- Availability of STI services

Clinic is set up in the project office at 3rd NAP Camp.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Clinic is well maintained with all the requisite formats and registers are maintained by the nurse and documentations are up-to-date. 3rd NAP Unit Doctor is available in the clinic twice a week. Essential drugs and testing kits are available. The drug dispensing counter is very well maintained. Privacy is maintained, the same was reported by HRGs during FDG. They reported feeling safe and comfortable visiting the clinic for availing services.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

82.27% (n=195) of 237 HRGs who have attended clinic were counselled in 2014-15 and 87.90% (n=189) of 215 in 2015-16. 6 HRGs were treated for STI. 72.72% (n=240) of 330 in 2014-15 and 68.88% (n=217) of 315 in 2015-16 were counselled at project level.

- Documentation

All the prescribed formats and registers are maintained by the nurse in the clinic.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Condoms are distributed for free as well through social marketing. It is made available at DIC and through outreach. No stock out of condoms was reported.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

92.32% (13408) against the annual cumulative demand of 14522 pcs of condoms in 2014-15 and 76.97% (11466) of 14895 in 2015-16

330 pcs of condoms in 2014-15 and 316 in 2015-16 were distributed through CSM.

- No. of Needles / Syringes distributed through outreach / DIC.

95.80% (23626) of 24660 N/D demand were distributed in 2014-15 and 81.39% (17977) of 22086 demand in 2015-16. 81.55% (19267) of 23626 distributed were exchanged in 2014-15 and 85.62% (15393) of 17977 in 2015-16. Waste disposal is being done as per NACO guidelines.

- Information on linkages for ICTC, DOT, ART, STI clinics.

MICTC is available on Tuesday during the doctor’s day. The TI has very good linkage with the 3rd NAP health unit which has also made its doctor available to the TI. For DOT and ART, all referrals are made to Tuensang District Hospital.

- Referrals and follows up

55.75% (n=184) of 330 HRGs line listed underwent the biannual Syphilis screenings and 77.27% (n=255) have tested once in 2014-15. 48.57% (n=153) of 315 HRGs line listed underwent the biannual screenings and 64.44% (n=203) have tested once.   All were tested non-reactive in both the years.

55.75% (n=184) of 330 HRGs line listed underwent the biannual HIV testing and 88.78% (n=293) have tested once in 2014-15. 1 tested positive. 48.72% (n=153) of 314 HRGs line listed underwent the biannual testing and 64.12% (n=202) have tested once. 1 tested positive. 100% of HIV positive detected were linked to ART Centre.

5 abscess cases treated for extended time in 2014-15. (18 times)

V. 	Community participation

1. 	Collectivization activities

18% (n=56) of 311 active HRGs population are part of 3 support groups and DIC Committee.

2. 	Community participation in project activities

Events organized in both the years were not specifically targeted at HRGs. While events organized had significant participations of key stakeholders and general public, the participation of HRGs organized has been less than 10% of the HRGs line listed.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

The TI maintains a directory of all referrals units along with contact details and it is updated regularly.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

No gaps between referred and testing since all the testing have been done at MICTC.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

Significant involving of the stakeholders was reported. They have been part of the crisis intervention team of the TI project. Apart from participation in the programs of TI, they have also advocated the project activities to larger community.

VII. Financial System and Procedures

- Systems of planning

The NGO adheres to the system of financial planning and budgeting endorsed by NACO/SACS. There was re-appropriation of fund, but it was in line with decision taken during AAP discussions

- Systems of payments

All vouchers are preprinted with machine made serial numbers. Bills, Cash Memos, Vouchers, were kept in order according to the Cash Book. Quotations were collected for purchase of N/S in 2014-15 but the same was not done in 2015-16. Stock register is maintained and records were found for distribution of N/S, condoms and medicines. Except for the salary to staff, all other transactions of more than Rs.5000/- were settled with cash. Cash of more than Rs.5000/- was available with the accountant most of the months.

- Systems of procurement

Quotations were collected for purchase of N/S only for 2014-15 but the same was not done in 2015-16.

- Systems of documentation

Except for non-indication of temporary loans taken and repayments in the SOEs, there was no mismatch between books of account maintained and progress reports. Separate bank account is being maintained in the local bank. Audit reports are available at DIC. Bank Reconciliation Statement is prepared as and when it is required.

VIII. Competency of the project staff

VIII a. Project Manager

Program Manager is a Graduate and has been working in the TI Project under various capacities: as support staff, accountant and promoted to Program Manager. He has adequate knowledge about project proposal planning and on performance indicators. Monthly and quarterly work plan in place at the project level and has some knowledge about financial management. SIMS data are entered by the Program Manager and he has good knowledge of computer and data entry. Conducts in-house orientation and field visits are done as per needs. Conduct the weekly staff and monthly review meetings. There is clarity on advocacy and the same has been observed in the advocacy activities carried out and documentation available.

VIII b. Nurse

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

VIII i. M&E officer cum Accountant

He lacks even the basics of accounting.

IX. a. Outreach activity in Core TI project

All the participants reported their satisfaction with privacy in the DIC and confidentiality maintain by the staff and PEs. They also reported their satisfaction with clinic services like, sincerity of staff, availability of nurse and doctor and cleanliness maintained. They report receiving N/S and condoms as and when they need. They are delivered to them by PEs or either collects them from DIC. They also reported visiting clinic and receiving clinic services and counselling from the nurse. Some of them reported positive feedbacks which they received were one of the reasons for attending clinic services.

Most of the outreach team members are newly inducted and thus lack the understanding of various planning tools and reporting formats used was observed. While onsite mentoring is ongoing, plans are in place, outreach activities are being carried out, coordination of nurse and the outreach team is taking place, strengthening of linkage between the outreach and clinic services need to strengthen to increase uptake of services by HRGs regularly.

X. 	Services

While satisfaction on privacy and confidentiality by the project team was acknowledged by most, some of them were not sure about privacy and confidentiality being maintained.

All the participants reported that the nurse is known to them and recollected being counselled by the nurse. Some reported the need for more involvement of the nurse.

XI. 	Community involvement

18% (n=56) of 311 active HRGs population are part of 3 support groups and DIC Committee.

XII. Commodities

All the participants reported that they are receiving N/S and condoms from the project as and when they need.

Condom demand is calculated for each individual HRGs based on their client load and requirement of condoms. The demand for N/S is calculated based on the injecting frequency and number of injecting days or days in a week/month.

XIII. Enabling environment

8 meetings in 2014-15 and 8 meetings 2015-16. Proper documentation available and follow-up done through one-to-one meeting during field visits by outreach team and program manager. Advocacy meetings were also planned and conducted as follow-ups of crises intervention of a harassment case and discrimination towards a HIV positive HRG.

Crisis Management constituted comprising of 8 meetings and 2 meetings each were held in both the years. Proper documentation of meetings held maintained in the project office. 1 crisis reported in 2014-15 was timely intervened by the team along with members of GB of TI but could not be resolved. While the crisis was reported by the police department, the TI was also advised not to attempt to bail the HRG out and allow him to complete a week term in jail for his repeated crimes.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

XV. Best Practices if any