# Nagaland State AIDS Control Society

Targeted Intervention- Evaluation Report

- 2016-

# Jiremmen Youth Society

IDUs

# Longchem, Mokokchung District

Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eiliakim Sorhie – External Evaluator

- Mr. Sanjay Paul– Finance Evaluator

- Ms. Abonuo Khatso – NSACS Observer

# Introduction

- Background ofProject and Organisation

The Jiremmen Youth Society (JYS) with its headquarter at Tsuremmen Village, under Mokokchung district is a non governmental, registerd under the Society Act, (Regd. No. RS – 1363 Dtd. 21/08/1990) formed for the sole purpose of uplifting the lives of the rural population. Since its inception in 1990, the organization have been actively engaged in social development at the community level on voluntary service. The organization also acts as a civil defence in times of natural calamities and other epidemic and social disasters.

The mission / aims and objectives of the organization is to create social awareness towards human resource development, leadership building and self support system so that the community is empowered for better choices and options in their lives.

The organization is implementing TI project under NSACS at Mangkolemba for IDU and FSWs, Longchem for IDUs and their spouses and in Tsuremmen for IDUs, FSWs and spouses of IDUs.

- Name and address of the Organization: Jiremmen Youth Society, Tsuremmen Village, P.O. Mangkolemba, B.P.O Longchem, Mokokchung – 798604, Nagaland

# Contact:+91 9436260013

email:jiremmen_ys@yahoo.com

- Chief Functionary:Ms. Watila Longkumer

- Year of establishment: 1990

- Year and month of project initiation:2005

- Evaluation team:

- Mr. Romeo Myrchiang – Team Leader, External Evaluator

- Mr.Eiliakim Sorhie – External Evaluator

- Mr. Sanjay Paul– Finance Evaluator

- Time frame:April 2014 – January 2016 [ 22 Months]

# Profile of TI

- Target Population Profile: IDU

- Typeof Project:IDU

- Sizeof Target Group(s): 323 IDUs & 45 SPs [2014- 2015] ; 318 IDUs & 45 SPs [2015 – 2016]

- Target Area:Longchem

IDU SITES: Changdang, Nokpu Yimpang, Nokpu Yimlang, Liangmen (Longchem), Sentep (Longchem), Vety (Longchem), Medical & Wajen (Longchem) Aonokpu, Lirmen Yimpang, Lirmen Yimlang.

[ Total of 9 major sites]

# I.Organizational support to the programme

The overall organizational support of “Jiremmen Youth Society” towards the TI Project in Tsuremmen, is  very supportive and cooperative towards the IDU and FSWcommunity.

Although committed to the cause of the target population the overall organizatonal support to the project in Tsuremmen, is not available; The Board / Organization members involvement in any of the the Project’s activities in the TI Project at Tsuremmen is not visible in the Project. The TI Project’s activites is being managed and implemented by the PM, ANM, Accountant and Outreach Team based on their understanding and capacity, without the supervision or monitoring of the TI Project Director.

| Oganization’s Board of Members |  |  |
| --- | --- | --- |
| Sl. No | Name | Designation |
| 1. | Mr. Meren | President |
| 2. | Mr K.Tsulak Longchar | Vice President |
| 3. | Mr. T Medem | Secretary |
| 4. | Mrs. Moamen | Assistant Secretary |
| 5. | Ms. Amenla | Member |
| 6. | Dr Apong Lcr | Member |
| 7. | Mr Jongpong | Member |
| 8. | Mr Toshimongba | Member |
| 9. | Ms. Watila Longkumer | Member |

# II.OrganizationalCapacity

- Human resources:The Staffing pattern in the TI Project have been implemented as per the NACO guidelines and as per the Project proposal and Budget approved by NSACS. PM, Accountant, ANM and ORWs have been provided with appointment letter without their roles and responsibilities in the TI project; However, it is noticed that the overall project staff could not define their roles and responsibilities within the TI project.

PEs are not given any appointment letters nor provided with any roles or responsibllities in the TI project. They are appointed through verbal conversations only and a single register was maintained. The project staffs are cooperative and helpful towards each other.

- Capacitybuilding:The TI staffs have been trained by State Training and Resource Centre, Identified Learning Sites for training of Peer Educators, and in-house orientation for the Peer Educators; covering topics on Proposal Development, Orientation, Harm Reduction, Data Collection Tools, Finance Management, OST, SIMS, Crisis Management, Advocacy, Refresher, Counselling & STI Counselling, Referrals, Community Moblization, Outreach Trainings.

The various trainings organized have been attended by the Program Manager, ANM, Accountant, Outreach Workers and Peed Educators accordingly. In house training by the TI Project has not been conducted.

- Infrastructure of the organization: The Project Office is equipped with a 5 roomed infrastructure which includes STI Clinic, Counselling room, separate rooms for the Drop in Centre, PM & Accountant room and ORWs room. The office location is well located and is easily accessible by the community for their needs and accessibilty to services provided by the TI Project.

4. Documentation and Reporting:The TI project staff’s are maintaining documents and procedures as per the NACO Guidelines to a certain limitation without proper checking and monitoring. Adherance to SACS protocol is not being witness in the TI Proejct. Feedbacks and suggestions by NSACS officials and past evaluations have not been followed or carried out by the TI project.

The Overall project planning, outreach as well as micro planning is not properly implemented or followed by the Outreach team to track HRGs for services provided by the Project such as ICTC Testing, STI Testing, Syphilis Testing etc..

Performance review mechanism is not witnessed in the project. ORWs monitoring and supportive supervision systems is not in place.

CMIS and SOEs are being sent to NSACS on a regular manner indicating the monthly project performance

# II.ProgramDeliverables

# Outreach

- Line listingof theHRG bycategory: Sitewise Line Listing and registration of all the HRG have been done and completed as per the Project proposal and as per the Targeted Project population coverage (ie. a target of 323 IDUs &  318 IDUs). The active HRGs are being covered and reached out with services provided by the project, such as Needle & Syringes and Condoms, ICTC referrals, STI treatment etc.

- Micro planning in place and the same is reflected in Quality and documentation: Planning has not been introduced by the TI project for service delivery (N/S and condoms) and the use and implementaton of micro plan is not reflected in the activities and documents of the PE &ORWs. Risk assessment and prioritization of HRGs have also not been done by the TI project.Linkages between the Outreach team and the ANM for clinical services and follow up mechanismis in place and is being cordinated at the field level.

- Coverage of target population (sub-group wise): As per the Targeted population of 318 IDUs [2014-2015-2016], more than 80% of targeted population are being provided with services by the TI project on a regular basis or as and when needed by the HRGs.

4.  Outreach planning: Quality of Outreach planning and its implementation as well as documentation is not properly implemented by the TI Project. Activities and tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization or proper planning.

Activities such as FGD, Hotspot Level meeting, Field Visits, Clinical services and other services provided by the TI Project are being done in an unplanned and unsystamatic way. Outreach Team [ORWs & PEs] needs to properly implement the planned activities at the TI level along with the PM, ANM and members of the community to effectively increase the services and meet the needs and requirement of the HRGs.

5.   PE: HRG Ratio: The TI Project have a total of 9 PEs for IDUs and 1 PEs for SPs who are looking after 9 major sites under the TI Project.

6. Regular contacts: Regular contacts for IDUs are also being maintained by the PEs who are providing N/S and Condoms to the HRGs which is <80% out of the active HRGs.

However, PEs are not being able to categorized or prioritized the HRGs under them. Linkages for clinical services and ICTC referrals or follow ups are being coordinated with the TI clinical ANM.

7. Documentation ofthe peer education: Peer Educator document’s which is the backbone of the TI Project are being maintained as per NACO’s data collection tool, but not maintained properly were available at the TI project office. However, the level of understanding of the PEs in terms of risk assessment, vulnerability and prioritization of the HRGs is still lacking among the Peer Educators. Also, the flow of distribution of commodities remains to be constant throughout the project period, which is reflected in the “Form B1 – PE Weekly Planning and Activity Sheet”, which could not be verified or authenticated.

PEs also maintains their own PE dairies, for their distribution of Commodities for their respective clients. However little information was available as the PEs dairy were not properly maintained and also the old dairies of the PEs were not maintained at the TI Project Office.

7. Quality of peer education : Interacting with the Peer Educators who came to the Project office during the Evaluation, their quality on peer education, knowledge and communication skills is not very clear to address the issues of HIV and AIDs, STI, Risk Behaviour, Harm Reductionand other related basic issues was being witnessed;

The Peer Educators are selected from respective areas and are not from the community background;

Peer Educator’s skill and capacity needs to be enhanced and capacitated with regular and effective orientation at the TI Project level, with proper assessment, mentoring and monitoring.

8. Supervision: The overall supervision and monitoring of TI Project by the PM is witnessed in the project. Although documents on follow up are being maintained, proactive measure and assistance needs to be taken up to further enhance the outreach activities by the Outreach Team for proper follow up on Risk Behaviour and reduction Counselling, ICTC, STI referrals and other services as well as behavioural change.

# IV. Services

- Availabilityof STIservices: The TI Project have a STI clinic managed by the ANM and is linked to one visiting Doctor; The clinic have adequate supply of STI drugs and testing kits which is being supplied by NSACS and also purchased by the TI project; The TI is linked to the Mobile ICTC and STI Clinic; Follow up mechanism is also in place which is reflecting in the number of referrals for HIV and Syphilis testing.

2. Quality of the services: The TI’s STI clinic is attached with the Counselling room which have privacy and is being maintained by the ANM. Clinical equipments are available in the STI Clinic, with adequate supply of medicines. The TI is also linked to a Mobile Clinic, where tests and linkages for syndromic cases are being treated.

3.  Qualityof treatment in the service provisioning : The STI clinic have provided services and treatment to the HRGs with STI treatment, Abscess management, Counselling and linkages for ICTC testing; with 1901 episodes of STI Counselling for IDUs; 1901 episodes of counselling for IDUs.

4.  Documentation: The TI Clinic is maintaining registers related to services delivery maintained by the ANM which includes Network Clinic Register, Clinic Daily Summary Sheet, Medicine Stock Register, Referral Slips, Counselling Register, and RMC Register. The system of procurement of medicines is not witness in the project.

The Needle Syringes and Condom stock and distribution registers is maintained by the ORWs.

5.  Availabilityof Condoms and Needle & Syringes: The TI project is distributing free condoms which are being acquired from SACS. Social marketing of condoms have been initiated, which is being done on a need based. The TI is maintaing stock in hand, while buffer stock for 3 months is not being maintained at the TI Project level.  The Needle Syringes and condoms are being distributed by the PEs and ORWs in the field level, while at the DIC level it is through the ANM.

The purchase of N/S by the TI project without proper planning or assessment for 3 months buffer stock; N/S are being purchased at an interval of 15 days gap to 2 months gaps. The Needle Syringes and condoms are being distributed by the PEs and ORWs in the field level, while at the DIC level it is through the ANM.

Condom and N/S demand and gap analysis have not been done / implemented at the TI Project level.

6.   No. Of Condoms distributed: A total of 43,642 numbers of free condoms were distributed through the Outreach Team and ANM; during the period of April 2014 to January 2016;

7.  No. of  Needles /Syringes Distributed: A total of 74,578 number of free Needle /Syringes were distributed during the period of April 2014 to January 2016 through the Outreach Workers, Peer Educators, ANM and DIC with a returned of 57,100 number of Needle Syringes through the NSE programme which is 76%.

Waste Disposal Management is in place and disinfection of Needle / Syringes is being performed in the DIC or Project Office by the ANM with the support of Outreach Worker; while the final disposal is being done at the PHC, Longchem.

8. Information on linkages for ICTC, DOT, ART, STI clinics: Linkages for STI testing and syndromic cases with the mobile ICTC has been effective with 40% having undergone Syphilis testing; and 77% having undergone HIV testing.

RNTCP referrals and awareness among the HRGs have not been done by the TI Project; however it may also be noted that no cases were detected for TB during the Project period.

9. Referrals and followsup: Referral mechanism is being maintained by the TI and follow up mechanism has also been maintainedand followed up by the ANM.

V. Community participation

- Collectivization activities: Collectivization or formation of groups has not been initiated by the TI Project.

2. Community participation in project activities: The overall community participation in the Project is low with none of the outreach team belonging to the community; they have not been able to involve the IDU and FSW community at large in various activities and events of the TI Project. Although the communities are taking part in the FGDs at the field level.

VI. Linkages

- Assess thelinkages establishedwith thevarious services providers like STI, ICTC, TB clinics etc : The TI Project have established links with the Mobile ICTC, and STI clinic.

- Percentages of HRGs tested in ICTC: 77% of the registered / active HRGs have undergone HIV testing during the project period [ April 2014 – January 2016]

- Support system: The TI Project have support system only on clincal service delivery with the ICTC, Mobile ICTC and STI centre;  The TI have developed a good rapport with different stakeholders and advocacy along with sensitization to the stakeholder is being done from time to time.;

VII. Financial systems and procedures

- Systems of planning: The organization/management is allowing the Project Office  to prepare the books of accounts every months as per the budget allotment and schedule provided by NSACS, without planning (either quarterly or yearly). Expenses are being made randomly without proper or system of planning.

The TI have spend almost the whole amount of funds released from NSACS. The Project also does not have any approval system endorsed by the NGO or management before incurring any expenses or expenditure.

2.  Systems of payments: Generally all the non salary payments, are being made by cash.  The Project is maintaining printed vouchres which are machine numbered and are being countersigned by the Accountant and PM. There is no approval systems found for payments. Most of the all the expenses are related with puchasing of foodstuffs or stationaries and supported by hand written /kachcha bills.

The TI has taken huge amount of loan during the year through cash and payment is also being made through cash only. Both Stock and assets registers are in place and updated; assets were not properly codified.

3.  Systems of procurement: There is a system for collecting quatations before purchasing in bulk, however there is no proper apporval system for purchases. Stock & issue registers is being maintained but not tallied properly. There is no system for quality checking of the product purchased.

- Systems of documentation: The project is maintaining Cash Books, ledgers, bank pass book, payment and receipt vouchers, salary register, PE honorarium register etc, Loan register are being maintained by the Accountant but which are not verified by the project director or competant authority.

VIII. Competency of the project staff

VIII a. Program Manager: The Program Manager, have been working with the TI project since 2011;

The PM have been trained on Programme management and implementation, Data collection Tools, Finance Management, harm Reduction, SIMS management. Monthly CMIS is being prepared and sent ontime by the PM, as well as SOEs are being sent monthly to NSACS.

Although, being trained and capacitated with skill and knowledge, due to lack of supervision and mentoring the PM lacks in the performance and upscalling the TI Project. The PM will need close monitoring and supervision by the PD to enhance and upscale his performance and morale.

VIII b. ANM:The ANM in the TI have been working in the project since July 2012 and have been trained for Counselling, Harm Reduction, Advocacy, referrals, community mobilization, STI management, OST. The ANM is efficient with ther roles and responsibiites and in dealing with the HRGs.

Record maintenance, updating of data and maintaining of registers at the Project clinic is being maintained by the ANM; Due to lack of supervision and monitoring from the Organizational and also at the NSACS level, the ANMs capacity and performace could not be nurtured.

VIIIc.ORW: Both the ORWs have been with the project for more than three years;. ORWs in the TI Project have been trained under NSACS and STRC, on various outreach and data collection tools and Harm Reduction.

Their knowledge about the target population and on various indicators for their PEs, Hotspot analysis, outreach plan, importance of RMC, importance of ICTC testing and well as STI testing is not very clear, and have not been able to implement in the field level due to lack of proactive involvvement of the PM in overalll planning, monitoring and supervision.

Field level activities and PEs support is visible at the TI Project, with a visit of 4 times a month; due to the vastness of the coverage area it is only possible to meet once or twice per PE per site per week.

VIIId. Peer Educators: Peer educators have been trained by STRC, learning sites, with no inhouse trainings.

With many of the PEs interacted, their knowldege on hotspot or site prioritization and on prioritization of HRGs is not very clear; while theimportance of ICTC and STI testing, condom demonstration skills and knowledge is clear.

Peer Educators knowledge and skills on report maintenance and documentation needs to be increased though capacity and trainings.

# Peer educator; usually meet at the DIC every Friday for a weekly meeting.

IX. a. Outreach activity in Core TI project: The Outreach activities are not being documented properly, nor are it being done as per the sitewise or hotspot with prioritization. The outreach team are doing these activities only to achieve their targets and deliver the commodities to the HRGs without proper understanding

X. Services: Overall service uptake in the Project and quality of service and service delivery of (Free Condom, N/S and N/SE) is very well accepted and satisfied by the HRGs met during the FGD.Linkage for STI to the clinic and ICTC referrals to the Mobile and Static ICTC is also prefferred by the HRG.

XI. Community involvement:The HRGs involvement in the TI Project for commodities have been since the beginning of TI project; However the community’s participation in the TI Project’s events, activiites, programmes and uptake of service delivery is still lacking with minimal involvement of the communities at various levels of the TI Project.  The community have never been involved in the process ofplanning process, monitoring or advocacy level, of the TI Project.

XII. Commodities: Hotspot Planning, Condom Demand and Gap Analysis risk and vulnerability factors has not been done or implemented in the TI Project. However the demand and distribution of condoms and N/Scalculation method is being done as per demand of the HRGs on a day to day basis and as and when required by the HRGs.

XIII. Enabling environment: Systematic plan and involvement of the community in advocacy, networking and linkages is not visible in TI Project.

The stakeholders met (community leaders) were not able to speek openly regarding and of the project, and also shared about their involvement with the TI Project and the services that the Project have been providing to the community..

# Annexure C

# Confidential:				Reporting Form C

# EXECUTIVE SUMMARY OF THE EVALUATION

( Submitted to SACS for each TI evaluated with a copy to NACO)

# Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| - Mr. Romeo Myrchiang – Team Leader, External Evaluator | Ch. No. 30, Rngi Jynriew, Near Iaikyntiew College, Upper Nongthymmai, Shillong – 793014, Meghalaya Email: rameses2605@gmail.com Contact: +91 9436101106 / 9862034762 |
| - Mr. Eliakim Sorhie – External Evaluator | Electrical Colony, House No. ECB-14 Kohima – 797001, Nagaland Email: eliakim_sorhie@yahoo.co.in Contact: +91 8575735801 |
| - Mr. Sanjay Paul – Finance Evaluator | Office: C/o. Ajit K. Jain & Associates, Circular Road, Dimapur, 797112 Nagaland Email: spaul936@gmail.com Contact: +91 9862762587 |
| Officials from SACS/TSU (as facilitator) | Ms. Abonuo Khatso NSACS Kohima – 797001, Nagaland Email: abonuoangami1@gmail.com Contact: +91 9436011474 |

| Nameofthe NGO: | Jiremmen Youth Society _Longchem |
| --- | --- |
| Typology of the target population: | IDU |
| Total population being covered against target: | 318 IDU against 318 IDUs; and 45 SPs against 45 SPs |
| Dates of Visit: | 28th& 29th February 2016 |
| Place of Visit: | Project Office; DIC; Field Visit for FGD: Longchem |

OverallRating based programmedelivery score:

| Total Score Obtained (in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 61%-80% | B | Good | [60.5 %] Recommended for continuation with specific recommendation for improvement. |

# Specific Recommendations:

- Change of Organization in leading and implementing the TI Project, with the appointment of a different PD while retain the same project staffs. - All Project Staffs (PM, ANM, Accountant, ORWs & PEs) must be provided with appointment letters along with their roles and responsibilites which must be explained. - Project Director needs take active participation in the TI Project implementation and must ensure that the PD is in TI Project site at least a minimun of 2 to 3 days during the month to provide support, Monitoring and mentoring the Project staffs. - Minutes of monthly / weekly / DIC meetings needs to be properly documented and maintained, along with names, designation and signature of the respected persons. - Regular meetings with HRGs for service delivery needs to be upscale and intensified at the DIC level. - Re Orientation on Data Collection and outreach tools for Outreach Team (ORWs & PE), and authentication of data with the PE Dairy that is being used in the field. - Outreach & Micro planning and activities needs to be introduced and intensified with prioritization of site wise and HRG wise. - Condom andNeedle Syringes gap analysis needs to the implemented by the Project staff. - Risk and vulnerability assessment need to be updated and done periodically at the TI level. - Involvement of communities at all levels of the TI Project is a must and needs to be increased - Motivation and collectivization of HRG needs to be implemented and followed up at the TI Level - Movement register of all the TI staff needs to be maintained and recorded accordingly. - Organization / Project must ensure that all the Documents, Data Collection Tools are being maintian, updated and systematicall / chronologically stored; including previous years documents at the Project Office. - Bank Account must be at the area where the project is implemented, ie. Mangkolemba SBI Branch, with the PD as on the signatories. - All the expenditure must be according to the approved Budget with supporting documents, and approve by PD. - Temporary Loan must be through bank transaction or A/c Payee, and the same returned via Bank Transaction, A/c Payee, and not by Cash. - Cash in hand should always be less than 5000. - Transaction for any amount above Rs 5000 should be done through cheque only. - TA must always have supporting voucher and must coordinate with the movement of the TI Staff, and also properly documented. - Books of account must be updated regularly. - BRS must be prepared month wise. - Expenditure for Every Budget head must have supporting documents and with proper supporting voucher. - Budget relocation of any budget heads must be with supporting approval from SACS or competant authority. - Regarding the payment of Honr. to Doctor, the same should be made by cheque only . In case of cash payment the acknowledgement should be in written by the particular doctor on his/her own commercial pad. - More training is required for accounts and record maintenance. - The Use of Tally must be implemented and practices by the Accountant.