Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organisation	:

Under Khiamniungan Baptist Church Tuensang Town, we have NGO TI, (Targeted Intervention) was also started under the aegis of Eleutheros Christian Society in March 2009 which is funded by Nagaland State AIDS Control Society (NSACS).

The project is implementing the TI among 200 IDUs, 30 FSWs and 100 SPs in 10 intervention sites in Thonoknyu sub-division.

| Name and address of the Organization | : | Khiamniungan Baptist Church (Thonoknyu) KBC Tuensang (Thonoknyu TI) Post Box No-09 Email: kbctsg@gmail.com |
| --- | --- | --- |
| Chief Functionary | : | Mr. Lusang |
| Year of establishment | : | March 2009 |
| Year and month of project initiation | : | April 2011 |
| Evaluation team | : | - Mr. Jongpongciten, Team Leader - Mr. Kenyulo, 2nd Evaluator - Mr. Akhumtong Jamir, Finance Evaluator - Mr. Visheto Mekro, NSACS |
| Time frame | : | April 2014 – January 2016 |

| Profile of TI |  |  |
| --- | --- | --- |
| Target Population Profile | : | IDU & FSW |
| Type of Project | : | Core Composite |
| Size of Target Group(s) | : | 200 IDUs, 30 FSWs and 100 SPs in both the project years of 2014-15 & 2015-16. |
| Target Area | : | Thonoknyu Area |

Key Findings and recommendations on Various Project Components

- Organizational support to the programme

The Organization has an Advisory Board comprising of members from the church body who forms the core committee. Representatives from the Advisory Board attend the monthly staff meetings and give their feedback/ encouragement. However, they are not involved in monitoring of project related activities.

II. Organizational Capacity

1. 	Human resources

All staff and PE positions have been filled as per the approved project in both the years. With the organization's structure change in 2015, the PM was elected by the Governing Board to hold the Project Director's Office. The ORW was promoted to PM and 1 PE to ORW.

There was no staff turnover witnessed in 2014-15. There was a change in the leadership both at Organization and project level in 2015-16. The PM was assigned the position of Project Director, the ORW was promoted to PM and 1 PE was promoted to ORW.

Only 1 PE (less than 20%) of 10 PEs turnover was witnessed in 2015. The vacant position of PE who was promoted to ORW was also filled within a week.

2. 	Capacity building

Except for 1 PE, all the categories of project staff and PEs have completed the trainings conducted by NSACS, STRC and Learning Sites.

3. 	Infrastructure of the organization

The TI project has adequate office space, basic required equipments and furniture to operate the project. Separate room available for clinic requisite equipments and consumables.

4. 	Documentation and Reporting

The entire prescribed registers and formats are maintained in use in the project. Review meeting done on a weekly and monthly basis and actions are taken as per the gaps and achievements. Project activity and SOE reports are submitted in SIMS to NSACS through DAPCU.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

Updated line lists of 197 IDUs and 30 FSWs by site wise available.

- Micro planning in place and the same is reflected in Quality and documentation.

Micro plans in place for each hotspots and prioritization of outreach is done based on demand for commodity and uptake for referrals services. Individual HRGs are tracked for RMC, ICTC and syphilis testing. Some of the PEs were not able to explain properly and the same was found in their documentation.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

100% achieved against the target of 200 IDUs and 30 FSWs in 2014-15. 98.5% (n=197) of 200 IDUs and 100% of 30 FSW target achieved in 2015-16.

- Outreach planning

Monthly plans in place at the project level for each ORW. Outreach is done based on monthly plan and all activities are captured in their respective formats.

- PE: HRG ratio

There are 8 PEs for 200 IDUs, 1 PE for 30 FSW and 1 PE for SPs as per the approved project in both the project years.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

There are no daily or medium-high volumes injectors among the HRGs. 100% of HRGs line listed are low volume injectors and the services were provided as per their requirement.

- Documentation of the peer education

Peer field dairies and Form B/B-1 used by PEs to capture their field activities. However, some of the PEs are not maintaining their log book properly as they are unable to understand some of the indicators- due and over-due for referrals.

- Quality of peer education- messages, skills and reflection in the community

PEs outreach activities are confined to commodity distribution and making ICTC and RMC referrals. Level of understanding on harm reduction and risk and vulnerability assessment is limited. Community members have basic knowledge of HIV, proper condom usage and safe injecting practices.

- Supervision- mechanism, process, follow-up in action taken etc

ORWs are not able to monitor their respective PEs on a regular basis due distance factor and transportation problems during monsoon. The TI has 10 intervention sites. Those sites within periphery of 2-5kms the ORW have visited 3 to 4 times and those within 15-42kms have been visited 1 or 2 times in a month. ORW for FSW conducts 3-4 field visits in a week and spends about 15-16 days in the field.

IV. Services

- Availability of STI services

Static STI clinic established at DIC and all STI cases handled by nurse. Clinic Network Formats in place and updated regularly. There is no doctor at Thonoknyu PHC and TI has therefore, not appointed any doctor. Nurse has established network with a doctor from Tuensang for tele-consulting on STI related cases and dispensing of drugs for the same.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Separate room available for Clinic at DIC. Basic clinical equipment’s and furniture are available.

Shortage of drugs observed. Privacy of information is maintained by the nurse. Waste Disposal mechanism in place. Collection and final disposal is done as per guidelines however, used N/S are not disinfected before final disposal. No doctor since March 2012. In 2014-15, a health camp was conducted with a doctor from Tuensang.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

For treating of STI related cases, the TI contacts a doctor in Tuensang on phone. A Doctor’s name has been indicated in the clinic registers but the doctor has visited only once in 2014-15 for the purpose of health camp.

77.08% (n=148) of 192 IDUs, 73.07% (n=19) of 26 FSWs and 67% (n=67) of 85 SPs who have attended clinic in 2015-16 were counselled.

83.24% (n=164) of 197 IDUs, 76.66% (n=23) of 30 FSWs and 74% (n=74) of 100 SPs line listed were counselled by the nurse at project level in 2015-16.

100% in 2014-15 and 16.66% (n=5) of 30 FSWs have underwent RMC in 2015-16. Doctor at PHC Thonokyu is on study leave since last two years. It been many years the TI has been making effort to established network with a doctor who is willing to travel to Thonokyu even once to TI Clinic in a month and they are still in search. In 2014-15 the TI brought a Doctor from Tuensang for a health camp. The same doctor is consulted by the nurse through telephone for STI related treatment.

No new HRG registered in both the years. 100% of targets achieved in both the years were follow-up of HRGs. Presence of new HRG/s were not known to the HRGs who participated in the FGDs during the evaluation of TI.

61% (n=122) of 200 IDUs registered in 2014-15 and 17.25% (n=34) of 197 IDUs registered in 2015-16 have underwent both the biannual Syphilis screenings. 53.33% (n=16) of 30 FSWs in 2014-15 and 23.33% (n=7) 30 in 2015-16. 61% (n=61) of 100 SPs in 2014-15 and 20% (n=20) of 100 in 2015-16.

61% (n=122) of 200 IDUs registered in 2014-15 and 17.25% (n=34) of 197 IDUs registered in 2015-16 have underwent both the biannual HIV tests.53.33% (n=16) of 30 FSWs in 2014-15 and 23.33% (n=7) of 30 in 2015-16.61% (n=61) of 100 SPs in 2014-15 and 20% (n=20) of 100 in 2015-16. No HIV positive case detected in both the years.

7 IDUs were provided aseptic abscess management services by nurse and ORW in the field for extended time in 2014-15. There was no abscess reported or identified in 2015-16.

No TB suspect cases reported in both the project years. The nurse was able to explain the TB related signs and symptoms, and where to refer.

- Documentation

All Clinic Network Formats/ Registers used by TI NGO. Standard Referral slips in use and properly tracked. Stock registers of condom, N/S and medicines maintained. Procurement process as endorsed by NACO/SACS is not followed.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

Free distribution as well CSM of condoms are made available to HRGs in DIC and through outreach by PEs and ORWs.

- No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

100% of the condom requirements were distributed to all target HRG typologies (IDU & FSW) in 2014-15. In 2015-16, the distribution of condoms to IDUs accounts to 72.59% (10105 pcs) of 13920 requirement, for FSWs 71.75% (3875 pcs) of 13920, and for SPs it was 64.30% (926 pcs) of 1440.

745 pcs of condoms to IDUs, 465 to FSWs and 32 to SPs were distributed through CSM in 2014-15. 365 pcs to IDUs, 36 to FSWs and 20 to SPs in 2015-16.

- No. of Needles / Syringes distributed through outreach / DIC.

100% of 15000 in 2014-15 and 68.18% (10296 Nos.) of 15100 N/S in 2015-16 forecasted in the approved project were distributed to HRGs.

66.48% (9991 Nos.) of 15028 in 2014-15 and 97.66% (10056 Nos.) of 10296 N/S distributed in 2015-16 were returned / collected for safe disposal.

Used N/S are being collected by PEs from IDUs in puncture proof containers and further disinfections and final disposal system functional as per NACO guidelines.

- Information on linkages for ICTC, DOT, ART, STI clinics.

While there is no Doctor in PHC Thonoknyu there was counsellor and Lab. Tech in ICTC. ICTC counsellor resigned in December 2015 and during the time of evaluation there was no counsellor.

For DOT and ART all referrals are made to CHC Noklak or DH Tuensang. For STI related cases nurse consults a doctor in Tuensang on phone.

While the MICTC van could not reach the TI since the van could not be driven on such a dreadful road, the MICTC Team visited the TI in 2014-15 for the purposes of HIV and Syphilis testing.

- Referrals and follows up

62% (n=122) of 194 IDUs who have underwent the 1st HIV and Syphilis test were followed up with the 2nd test in 2014-15. 66.66% (n=16) of 24 FSWs. All were tested non-reactive.

Only 20.60% (n=34) of 164 IDUs were followed up with the 2nd test for HIV and Syphilis and 35% (n=7) of 20 FSW in 2015-16.

100% of 30 FSWs has undergone RMC twice in 2014-15 and only 16.66% (n=5) has undergone once in 2015-16. Doctor at PHC Thonokyu is on study leave since last two years. It been many years the TI has been making effort to established network with a doctor who is willing to travel to Thonokyu even once to TI Clinic in a month and they are still in search. In 2014-15 the TI brought a Doctor from Tuensang for a health camp. The same doctor is consulted by the nurse through telephone for STI related treatment.

V. 	Community participation

1. 	Collectivization activities

Only 10 SPs are part of a support group formed in 2013 and functional.

2. 	Community participation in project activities

Community members are involved in the project as ORW and PEs. While they are not in leadership positions in the project, they are central to the planning and delivery of harm reduction services and prevention messages to their larger community. 52% of HRGs followed-up have attended at least 3 hotspot level meetings in both the years.

Community participation in events was 62.17% (n=102) of 230 HRGs registered (IDUs & FSW) in 2014-15 and 44.93% (n=102) of 227 HRGs registered (IDUs & FSW) in 2015-16.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

The TI is still faced with challenges to establish linkages to offer HRGs  with options to avail clinic services in the absence of doctor in PHC Thonoknyu since the other health centres are located very far from the TI.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

No gaps have been observed between HRGs referred and tested in ICTC. The TI ensures the available of ICTC counsellor and lab.technician while referring to ICTC.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

Good support established with the Church community and village headmen of target areas. Church community members involved in project planning and management board. Members of Adhoc Town Committee, Police and Students Union aware of project activities.

VII. Financial System and Procedures

- Systems of planning

- Expenses are made as per the SACS/ NACO approved budget.

- Financial system as per the SACS/NACO guide line is followed. (Cash book, ledger is prepared with a brief and clear narration given for each expense.)

- Systems of payments

- Printed and machine numbered with serialized vouchers are in place.

- Systems of approval by PD are followed.

- Three quotations available for 2014-15 from Stockiest/ whole seller/ chemist shop are in place for purchase of N/S and other required drugs for abscess prevention/ management.

- Huge amount of cash withdrawal. The same was not available for 2015-16.

- Cash of more than Rs 5000/- is available with the accountant most of the time since there is no banking services in the project location. Since there is no banking services in the project location, the TI had to keep cash in office to meet operational and programme costs as and when required. TI bank account is maintained in Tuensang Town which is about 117 kms from the TI. It takes about 6 hrs travel time and requires overnight stay in Tuensang.

- Systems of procurement

- System is followed as per the GMP guide line for procurement of STI drugs

- Systems of documentation

- Bank account is in place and maintained Jointly (Joint Signatory)

- Reconciliation process is followed on the monthly basis.

- Audit report is in place.

- Vouchers are in place with the bills attached.

- Stock and N/S registers are in place, having a Stock received and issue columns.

- Assets register is maintained properly.

VIII. Competency of the project staff

VIII a. Project Manager

- Program Manager is promoted from ORW in 2015 and has adequate knowledge about project proposal.

- Monthly and quarterly plan developed based on need and in place at the project level.

- Program Manager has limited knowledge about the budget components under various heads.

- Fair knowledge about program performance indicators.

- SIMS data are entered by the Program Manager and he has good knowledge of computer and data entry.

- Weekly and monthly review system in place and actions are taken as per reports from staffs and PEs.

VIII c. ANM/Counselor in IDU TI

- Has a fair knowledge about risk assessment and risk reduction.

- Is able to give basic counselling on HIV and STI.

- Has adequate knowledge about local drug use scenario and counselling techniques.

VIII d. ORW

- ORWs have fair knowledge about key performance indicator and targets for their PEs.

- Were able to explain monthly outreach plan, demand for condoms and N/S.

- Supportive supervision is done based on needs.

- Conducts FGD meetings but reports are brief.

- Follow up actions on referrals and commodity distribution is disseminated during the review meetings.

VIII f. Peer educators in IDU TI

- More emphasis is given on commodity distribution and referrals for ICTC, during field visits and no prioritisation is done based on risk and vulnerability assessment.

- Lacking adequate knowledge on importance of RMC and ICTC & syphilis testing.

- Adequate knowledge on proper condom usage.

- Level of understanding on STI symptoms is limited.

- PEs has basic working knowledge on abscess prevention and management.

- Some of the PEs are from drug using background and are aware of local drug use scenario and availability/ location of de-addiction facilities and centres.

- Community members also have basic knowledge of HIV and safe injecting practices and proper usage of condoms

IX. a. Outreach activity in Core TI project

Uptake of service is limited to HIV and Syphilis testing, and demand for commodity. Hotspot wise micro plan in place but PEs are not able prioritized outreach based on risk and vulnerability. Outreach is focused more on achieving commodity distribution and making referrals.

X. 	Services

For treating of STI related cases, the TI contacts a doctor in Tuensang on phone. A Doctor’s name has been indicated in the clinic registers but the doctor has visited only once in 2014-15 for the purpose of health camp.

77.08% (n=148) of 192 IDUs, 73.07% (n=19) of 26 FSWs and 67% (n=67) of 85 SPs who have attended clinic in 2015-16 were counselled.

83.24% (n=164) of 197 IDUs, 76.66% (n=23) of 30 FSWs and 74% (n=74) of 100 SPs line listed were counselled by the nurse at project level in 2015-16.

100% in 2014-15 and 16.66% (n=5) of 30 FSWs have underwent RMC in 2015-16. Doctor at PHC Thonokyu is on study leave since last two years. It been many years the TI has been making effort to established network with a doctor who is willing to travel to Thonokyu even once to TI Clinic in a month and they are still in search. In 2014-15 the TI brought a Doctor from Tuensang for a health camp. The same doctor is consulted by the nurse through telephone for STI related treatment.

No new HRG registered in both the years. 100% of targets achieved in both the years were follow-up of HRGs. Presence of new HRG/s were not known to the HRGs who participated in the FGDs during the evaluation of TI.

61% (n=122) of 200 IDUs registered in 2014-15 and 17.25% (n=34) of 197 IDUs registered in 2015-16 have underwent both the biannual Syphilis screenings. 53.33% (n=16) of 30 FSWs in 2014-15 and 23.33% (n=7) 30 in 2015-16. 61% (n=61) of 100 SPs in 2014-15 and 20% (n=20) of 100 in 2015-16.

61% (n=122) of 200 IDUs registered in 2014-15 and 17.25% (n=34) of 197 IDUs registered in 2015-16 have underwent both the biannual HIV tests.53.33% (n=16) of 30 FSWs in 2014-15 and 23.33% (n=7) of 30 in 2015-16.61% (n=61) of 100 SPs in 2014-15 and 20% (n=20) of 100 in 2015-16. No HIV positive case detected in both the years.

7 IDUs were provided aseptic abscess management services by nurse and ORW in the field for extended time in 2014-15. There was no abscess reported or identified in 2015-16.

No TB suspect cases reported in both the project years. The nurse was able to explain the TB related signs and symptoms, and where to refer.

XI. 	Community involvement

Community members are involved in the project as ORW and PEs. While they are not in leadership positions in the project, they are central to the planning and delivery of harm reduction services and prevention messages to their larger community. 52% of HRGs followed-up have attended at least 3 hotspot level meetings in both the years.

Community participation in events was 62.17% (n=102) of 230 HRGs registered (IDUs & FSW) in 2014-15 and 44.93% (n=102) of 227 HRGs registered (IDUs & FSW) in 2015-16.

XII. Commodities

100% of the condom requirements were distributed to all target HRG typologies (IDU & FSW) in 2014-15. In 2015-16, the distribution of condoms to IDUs accounts to 72.59% (10105 pcs) of 13920 requirement, for FSWs 71.75% (3875 pcs) of 13920, and for SPs it was 64.30% (926 pcs) of 1440.

745 pcs of condoms to IDUs, 465 to FSWs and 32 to SPs were distributed through CSM in 2014-15. 365 pcs to IDUs, 36 to FSWs and 20 to SPs in 2015-16.

100% of 15000 in 2014-15 and 68.18% (10296 Nos.) of 15100 N/S in 2015-16 forecasted in the approved project were distributed to HRGs.

66.48% (9991 Nos.) of 15028 in 2014-15 and 97.66% (10056 Nos.) of 10296 N/S distributed in 2015-16 were returned / collected for safe disposal.

XIII. Enabling environment

6 meetings in 2014-15 and 12 meetings in 2015-16 were conducted with various stakeholders. The same were reflected in Form-J and was reported by the stakeholders during interview by the evaluation team.

While no formal team has been constituted, the TI has functional system in place to address when a crisis is reported. The project team with members of the Governing Board and Council does the intervention. 1 crisis (altercation with police personnel) reported in 2015-16 was timely addressed by them.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

3 IDUs were registered in Building & Construction Workers Schemes under Department of Labour and Employment.

XV. Best Practices if any