Nagaland State AIDS Control Society

Targeted Intervention - Evaluation Report

April 2014- January 2016

Kripa Foundation

IDU & FSW

Tseminyu

Kohima District

Evaluation team:

- Mr. Kholi. A		: Team Leader, External Evaluator

- Mr.KevilemeVisezuo : External Evaluator

- Mr. Raju Gupta	: Finance Evaluator

Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy DAC)

Introduction

OBackground of Project and Organisation

Kripa is derived from a Sanskrit work meaning ‘Grace’ which highlights the need to study risk perception effectively to assist in harm minimization and train the effected individuals to monitor life as an on-going process of spiritual growth.

Kripa foundation is a Non-Governmental Organisation in India helping people suffering from chemical dependency and HIV infection. The organisation has a humble beginning at Mt. Carmel Church at Bandra (Mumbai), in 1981, with 3 patients, a priest, a doctor and a recovering alcoholic as a role model for recovery and sobriety. This public charitable has 33 facility in different locations spread all over the country, viz., Mumbai, Vasai, Delhi, Baroda, Goa, Pune, Mangalore, Kolkotta, Ranchi, Darjeeling, Imphal, Shillong, Guwahati, Kohima in addition, the organisation have international centres in Switzerland, Canada and Germany.

Kripa ventured into Nagaland at the request of Naga Mother’s Association in 1989. In their joint effort they have helped to decrease denial in the community, hence, opening the door for the suffering substance abusers to access help through the Rehabilitation Centre where the people in recovery themselves serve as mentors.

Later in the year 1999-2000 the Organisation took a Targeted intervention project from NACO through NSACS to create an enabling environment among Injecting Drug Users (IDU) in order to prevent transmission of HIV/AIDS through sharing of N/S.

O Name and address of the Organization

Kripa Foundation, Nagaland (Tseminyu DIC)

O Chief Functionary:

Abou Mere

O Year of establishment:

1989

O Year and month of project initiation:

June 2003

OEvaluation team:

- Kholi. A (External Evaluator- Team Leader)

- Kevileme Visezuo(External Evaluator)

- Raju Gupta (External Finance Evaluator)

OTime frame:

Assessment Period		: April 2014- January 2016

Date of Evaluation		: 17th February – 18th February 2016

Profile of TI

OTarget Population Profile:

Injecting Drug User (IDU) & Female Sex Worker (FSW).

OType of Project:

Core Composite (IDU & FSW)

OSize of Target Group(s)

|  | April 2014- March 2015: |  | April 2015 - Jan. 2016 |  |
| --- | --- | --- | --- | --- |
|  | IDU | FSW | IDU | FSW |
| Target | 330 | 100 | 330 | 100 |
| Achievement | 324 | 98 | 327 | 100 |

OSub-Groups and their Size

Not Applicable as per contact agreement with SACS.

OTarget Area:

| Sl. No. | Name of the Coverage area |
| --- | --- |
| 1 | Tseminyu New Town |
| 2 | Tseminyu Old Town |
| 3 | Zisunyu Village |
| 4 | Tseminyu Village |
| 5 | Tsokeda |
| 6 | PKR |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

- Office bearers are actively involved in AIDS control and other health programs.

- KRIPA Foundation is implementing 3 TI Projects in Kohima District.

- Office bearers have been making efforts to ensure strong linkages are built with service providers, DAPCU and stakeholders at a higher level.

- Review of project staffs are conducted monthly with all 3 projects at the head office with the Project Director.

II. Organizational Capacity

1. Human resources:

- All appointments are done with the approval of the Governing Body.

- System of peer progression observed with 1 PE graduating to ORW.

- Weekly and monthly reporting structure in place and monitored. Performance of each staffs and PEs is assessedduring weekly and monthly meetings.

- The organisation adheres to its policy of Human Resource and staffing. Project staffs and PEs are terminated ifthey do not perform their duty.

- Turnover of community members due to relapse, non-performance or better opportunity.

- 16.66% [n=1 out of 6] staffs turnover witnessed during the assessment period. Turnover of ORW.

- 30% [n=3 out of 10] PE turnover witnessed during the assessment period

- A total of 13 PEs has been approved for the project: position of 3 PEs has not been filled.

- Post of Counsellor has been created through internally adjustment.

2. Capacity building:

- Staffs and PE’s attended various trainings conducted by SACS, STRC, RRTC, NEIGRIMS and Learning Sites (BYWS) on Programme Management, SIMS management, OST, Harm Reduction, Co-morbidity, STI/ RTI Management, Finance & Accounting Management.

- ORW of FSW attended FSW Training organised by Prodigals Home in February 2014.

- Name of staffs and PEs who attended respective trainings properly documented at project level.

- Accountant needs more training in financial management and Book Keeping.

3. Infrastructure of the organization:

- Kripa TseminyuDIC has 4 rooms (1 room for PM, 1 for STI clinic observation,1 room partitioned into 2 rooms for Counsellor and ORW and a Recreation cum meeting room. Aseparate kitchen is also attached inside the premises.

- Basic office furniture’s and steel lockers in place.

- 1 desktop computer with printer and TV in working order.

- Laptop under repair during evaluation period.

- Digital camera not made available for physical verification.

- Static STI clinic set up and in place. Clinical equipment’s, medicines, disinfectants, gloves and colour coded waste disposal bins in place.

- Adequate IEC and BCC materials, Condom demo-models, puncture proof container available at TI DIC.

- Board games (carom) and TV sets available for recreation.

- Documentation and Reporting:

- TI is adhering to the reporting protocols and all 17 formats for data collection is in use.

- Timely submission of SIMS done regularly.

- Submission of PE’s reports done on weekly basis.

- Review meetings are done on a weekly and monthly basis and actions are taken based on achievements/ gaps.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

|  | April 2014- March 2015: |  | April 2015 - Jan. 2016 |  |
| --- | --- | --- | --- | --- |
|  | IDU | FSW | IDU | FSW |
| Target | 330 | 100 | 330 | 100 |
| Achievement | 324 | 98 | 327 | 100 |

OSub-Groups and their Size

Not applicable

2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counselling.

Not applicable

3. Registration of truckers from 2 service sources i.e. STI clinics and counselling.

Not applicable

4. Micro planning in place and the same is reflected in Quality and documentation.

Micro plans and outreach plans are done on a weekly and monthly basis, based on need for achieving target or gaps in commodity distribution, referrals and follow- ups on uptake of project services.

5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- March 2015: |  | April 2015- Jan. 2016 |  |
| --- | --- | --- | --- | --- |
|  | IDU | FSW | IDU | FSW |
| Target | 330 | 100 | 330 | 100 |
| Achievement | 324 | 98 | 327 | 100 |
| Active HRGs regularly contacted | 35 | 60 | 55 | 32 |

6. Outreach planning – quality, documentation and reflection in implementation

- Work plan for PE done on a weekly basis.

- Monthly plan for outreach in place.

- Coordination meeting between Nurse and ORWs done on a weekly basis and actions are taken up based on gaps or achievements.

- ORW provide supportive supervision to their respective PEs. Based on PE needs, ORW conducts FGDs at the hotspot level.

- The process of reviewing staffs and PEs, nature of actions taken are reflected in meeting minutes.

7. PE: HRG ratio:

|  | Ratio of PE to HRG |  |
| --- | --- | --- |
|  | April 2014- March 2015: | April 2015- Jan. 2016 |
| IDU | 1: 25 | 1: 25 |
| FSW | 1: 50 | 1: 50 |

8. Regular contacts

|  | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| IDU | 100 | 120 |
| FSW | 45 | 20 |

9. Documentation of the peer education

- Peer field dairies and Form B in use.

- Peer dairies reflect nature of outreach: topic discussed and number of HRGs contacted. Quantity of N/S and condom distribution is also reflected.

10. Quality of peer education- messages, skills and reflection in the community

- On an average at least 2 hotspot level meetings are conducted in a month to increase the knowledge level among the community members.

- Peer dairies reflect nature of outreach: topic discussed and number of HRGs contacted. Quantity of N/S and condom distribution is also reflected.

- Community members are also aware of services provided in the DIC and haveknowledge about presence of other health care service providers.

- During FGD (conducted by the evaluation team) it was observed that Community members have basic knowledge of HIV, proper condom usage and safe injecting practices.

- Demand for service also observed: to create an extension OST Centre at Tseminyu New Town.

- Demand for linkage to governmental schemes was also discussed by community members.

11. Supervision- mechanism, process, follow-up in action taken etc

Supportive supervision is carried out by the ORWs and each PE’s are oriented on outreach skills, rapport building, etc., whenever field visits are conducted. Overall supervision of outreach is done by the Program Manager.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- Static STI clinic established at DIC and all STI cases handled by Nurse from the clinic.

- Part time Doctor has not been appointed and had never attended TI STI clinic during the assessment period.

- Nurse has been working in the TI project as nurse since 2004 and has attended/ received various trainings.

- STI medicine Kits 1, 2 and 6 available but stock out of Kit 3, 4, 5 & 7 reported since Oct. 2014. These KITS were not indented because no related STI case has been detected so far during the assessment period.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Static STI Clinic established at DIC with separate room for examination.

- Basic clinical equipment, furniture and observation bed in place.

- Network Clinic Formats in place and updated regularly.

- Stock out of STI medicines observed.

- STI medicine Kits 1, 2 and 6 available but stock out of Kit 3, 4, 5 & 7 reported since Oct. 2014. These KITS were not indented because no related STI case has been detected so far during the assessment period.

- Buffer stock of STI medicines not maintained.

- All Clinical information’s are kept confidential by the nurse.

- Waste Disposal mechanism and Collection is done as per NACO guidelines. Final disposal is done at CHC Tseminyu Old Town.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not applicable

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- Nurse has been working in the TI project as nurse since 2004 and has attended/ received various trainings.

- Syndromic case Management chart in place at the clinic and Nurse follow standard protocol in dispensing STI Kits accordingly.

- HIV testing is referred to Mobile ICTC and ICTC at CHC Tseminyu Old Town.

- Follow up on ICTC, RMC and STI done as perORWs and PEs reports.

- Linkages established at NHK, Kohima for ART referrals and all positive HRGs are referred to ART Centre, NHK, Kohima.

- Linkages also established with RNTCP centre at CHC Tseminyu Old Town.

- Abscess management / prevention services available at DIC and overseen by the Nurse.Few incidences on shortage of abscess management kit/ medicines reported by community members.

- ICTC Counsellor very irregular at CHC Tseminyu.

- Doctor comes only once or twice weekly at DOTS Centre, CHC Tseminyu Old Town.

5. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- All Clinic Network Formats/ Registers in use by Nurse.

- Standard Referral slips in use and properly tracked.

- Stock registers of medicines maintained and updated on a regular basis.

- STI medicines Kits are procured from NSACS. Indent Register also maintained for requisitioning STI medicines from NSACS.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Free condoms are distributed by PE’s and staffs of TI DIC. No secondary distribution outlets created.

- Community members reported that they get free condoms as and when they demand.  No shortage reported during the assessment period.

7.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

| Total nos. of free condom distributed to | April 2014- March 2015: |  | April 2015- Jan. 2016 |  |
| --- | --- | --- | --- | --- |
|  | IDU | FSW | IDU | FSW |
| Requirement | 15700 | 15930 | 13600 | 13000 |
| Distribution | 17929 | 16104 | 13270 | 13042 |
| Achievement | 114% | 101% | 97% | 100.32% |

8. No. of Needles / Syringes distributed through outreach / DIC.

| Total nos. of N/S distributed | April 2014- March 2015: | April 2015- Jan. 2016 | Achievement (April 2014- Jan 2016) |
| --- | --- | --- | --- |
| Requirement | 28950 | 24700 |  |
| Distribution | 29827 | 26059 | 97% |
| Returned | 23888 | 20276 | 78.94% |

9. Information on linkages for ICTC, DOT, ART, STI clinics.

- Static STI clinic has been established at TI Project site at Tseminyu New Town and all STI cases are handled by the Nurse.

- Linkage has been created at ICTC at CHC Tseminyu Old Town for HIV testing.Linkages havealso been established with mobile ICTC.

- Referral linkages have been established at RNTCP in CHC Tseminyu Old Town for DOTS.

- All HIV positive cases are referred to ART centre in NHK Kohima, KNP+, NNP+

10. Referrals and follows up

- On an average, only 2.47% underwent RMC.

- 100% of the newly registered HRGs were provided PT.

- On an average, 54.06% underwent Syphilis testing twice.

- 320 (IDU) and 98 (FSW) underwent HIV testing at least once in the last one year (97.89%).

- On an average, 30% underwent HIV testing twice

- HIV testing: None tested positive during assessment period.

- Difficulty faced in motivating clients to go for second HIV or syphilis testing because of several reasons:

- Majority of the HRGs are old clients and have tested yearly for several years now and know about their status and practise less risk behaviour.

- Distance to testing centres and lack of transportation deters clients from going to ICTC.

- 11 cases of abscess were provided dressing and followed-up.

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- A Crisis Response Team has been set up with representation from community members and staffs of TI.

- SHG formed by FSW along with staffs of TI.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members involved in the project as PEs and ORWs. They take active part in outreach activities like commodity distribution, providing referrals and organising FGD with their peers.

- All activities documented in their respective field diaries/ formats.

- Community member participated in events organised by the project. Four (4) community events wereobserved during the assessment period and a total of 339 HRGs participated.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- Static STI clinic has been established at TI Project site at Tseminyu New Town and all STI cases are handled by the Nurse.

- Linkage has been created at ICTC at CHC Tseminyu Old Town for HIV testing. Linkages have also been established with mobile ICTC.

- Referral linkages have been established at RNTCP in CHC Tseminyu Old Town for DOTS.

- All HIV positive cases are referred to ART centre in NHK, Kohima, KNP+, NNP+

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

|  | April 2014- March 2015 |  | April 2015- Jan. 2016 |  |
| --- | --- | --- | --- | --- |
|  | IDU | FSW | IDU | FSW |
| Referred for HIV testing | 237 | 94 | 321 | 98 |
| Nos. of HRGs who tested at least once during the last one year (Actual tested) | 237 | 94 | 321 | 98 |
| Nos. of HRGs who tested twice during the last one year | 09 | 07 | 60 | 30 |

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- TI project in the area was initiated in the year 2003 and since then support system had been established with the local leaders, Church community, colony/ ward leaders, NGOs and student’s organizations.

- Advocacies with various key stakeholders had been done since the inception of the project in 2003.

- However, during the assessment period (April 2014 till Jan 2016), involvement of stakeholders in the project has not been observed nor documented.

- The TI Project has also established linkage with CHC Tseminyu for final disposal of disinfected waste.

VII. Financial systems and procedures

1. Systems of planning:

- System of planning is as per the NGO-CBO guideline.

- Financial system as per the SACS/NACO guide line is partially followed.

- Adequate measures were taken by NGO to audit observations and action has been taken as per recommendations. However, there were lapses in some areas.

2. Systems of payments-

- PD’s approval is taken before every transaction or payments.

- Payments are made with proper bills and vouchers, but majority of the bills are ‘katcha’.

- Cash transaction above NACO’s directive observed. Cash in hand also exceeds more than ₹5000/- in some cases.

- Budget Utilization is more than 60% against the released fund.

- Expenditure is made as per approved budget in each head

3. Systems of procurement-

- Procurement system and GMP guidelines is followed for purchase of assets and medicines. STI medicines and Syphilis testing kits are procured from NSACS.

- No quotations were found, as the procurement is centralized from Kohima.

- As per organisational policy - all procurement of medicines and assets are done from head office in Kohima. The TI DIC placed monthly/quarterly indents and these are issued as per requirements by head office.

4. Systems of documentation-

- Separate bank A/c is in place for TI project in the project area.

- Vouchers are printed and machine numbered, but ledger is not maintained for vouchers.

- Cash book is updated on daily basis and SOE is submitted on time.

- Negligible mismatch observed in financial reporting.

- Audit report is in place. Compliance to audit observation is followed but lapses observed in some areas.

- Stock and issue register for STI medicines, condoms and Needles & Syringes are maintained.

- Assets register properly maintained andall fixed assets are marked/ codified.

VIII. Competency of the project staff

VIII a. Project Manager

- PM was appointed in the month of June, 2013 and attended several trainings organised by NSACS.

- Is aware of his roles and responsibilities and was able to describe the various performance indicator of the TI project.

- PM takes a major part in developing project proposal after conducting a Need Assessment with the community members.

- Outreach work (advocacy, visitation to service provider/ centres, supportive supervision and monitoring at the field level) are done based on needs of the staffs and community members.

- Reviewing of staffs is done based on performance and achievements.

VIII b. Counsellor

Clarity on risk assessment and risk reduction, knowledge on basic counselling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

- Counsellor has been working in the TI Project since 2003.

- Has attended many trainings and workshops in the last 12 years from NSACS and other organisations.

- Has adequate understanding on risk assessment and possesses basic counselling skills.

- All counselling register are properly updated and documented on a daily basis.

- On an average, Counsellor conducts 20- 24 days of field visit in a month.

NURSE: (A separate Nurse has been allotted to the TI as per contract agreement with NSACS).

- Nurse has been working with the TI Project since 2004 and has attended several trainings conducted by NSACS.

- Is able to explain risk assessment and risk reduction processes.

- Is able to give basic counselling on HIV and STI.

- Has adequate knowledge about local drug use scenario.

- All registers and clinic formats are maintained and updated regularly.

- Conducts field visit as per needs from the community member.

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

- 3 ORWs on board as per contract agreement [n=2 for IDU & 1 for FSW].

- 2 ORWs [IDU & FSW] able to explain various indicators for their respective PEs.

- 1 ORW of IDU not very regular (poor health and from user background).

- Monitoring of PEs is done by the ORW and key performance indicators are closely checked. Outreach planning is done in consultation with Program Manager, Nurse and Counsellor.

- Understands hotspot analysis and is able to explain it.

- ORWs have basic knowledge of STI symptoms.

- Supportive supervision is done based on needs and assists PEs in conducting FGD meetings at the hotspots level.

- Capacity building on rapport building, condom demonstration, safer injecting practise, abstinence, OST and overdose prevention are imparted.

VIII e. Peer educators in FSW TI

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

- Prioritisation is done as per demand for commodities by HRGs and referral for HIV testing.

- Have adequate understanding about importance of RMC and HIV testing.

- Possesses fair condom demonstration skills and have basic knowledge on common symptomatic STI.

- Have a fair knowledge about various health care service provider and centres.

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

- Prioritisation is done as per demand for commodities by HRGs and referral for HIV testing.

- Have adequate understanding about importance of RMC and HIV testing.

- Possesses fair condom demonstration skills and have basic knowledge on common symptomatic STI.

- Have a fair knowledge about various health care service provider and centres.

VIII h. Peer Educators in Truckers Project

Not Applicable

VIII i. M&E officer

Not applicable

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- Project related services are given to HRGs on a regular basis and follow-up mechanism is in place.

- Prioritisation of service delivery is based on demand for commodity, uptake of referrals services and follow-ups. Individual HRGs are tracked for ICTC and syphilis testing.

- Micro plans are updated on a quarterly basis and outreach plans are developed on a weekly basis.

IX. b. Outreach activity in Truckers and Migrant Project

Not applicable

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

| Services | Apr 2014- March 2015 |  | April 2015- Jan. 2016 |  |
| --- | --- | --- | --- | --- |
|  | IDU | FSW | IDU | FSW |
| Nos. of HRGs provided Counselling | 330 | 100 | 330 | 100 |
| HIV Testing (Twice in a year) | 09 | 07 | 60 | 30 |
| RMC (Twice in a year) | 01 | 04 | 01 | 01 |
| Referred to DOTS | Nil |  | 01 |  |
| Abscess Treated | 11 |  | 11 |  |
| Condom distributed | 17929 | 16104 | 13270 | 13042 |
| N/S distributed | 29827 |  | 26059 |  |
| N/S Returned | 23888 |  | 20276 |  |

Linkage Referrals to Service Providers:

- ICTC: Linkages established at CHC Tseminyu Old Town and Mobile ICTC

- ART: Linkage established at ART Centre in NHK, Kohima, KNP+ and NNP+

- DOT: Linkage established at RNTCP in CHC Tseminyu Old Town

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- Three [n=3] ORWs on board and came from HRG background. One ORW has graduated from PE. They are involved during project planning and development of project proposal.

- Community members frequent the DIC for recreational and clinic services.

- HRGs are part of the Crisis response Team and DIC Committee.

- Community members participated in Free Liver Health Camp, World AIDS Day, Annual Picnic and Annual Sports Meet. A total of 339 community members participate in these events.

XII. Commodities

- Planning for meeting the demand of condom and N/S are done at the project level only after conducting Need Assessment with the community members.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc.

- None conducted during assessment period.

- No systematic advocacy plan in place. Advocacy is usually done only when a need arises.

- Community Members happy with the project for sensitising the public about the issues of HRGs and creating linkages to various service providers.

- Good networking with key stakeholders established.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- TI NGO donated food materials to PLHIV

- TI NGO tried to linked community members to ‘Viyan Project’ (a Drug Users Group) in 2014 but did not materialize..

XV. Best Practices if any

- Presence of a good number of community members in Crisis Response Team.

- Community members actively taking part and registering themselves in OST program.

- Regular field visit by Counsellor: 20-24 days of field visit monthly.

Confidential                                      Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Kholi. A(External Evaluator) | +91 9862797996 |
| Kivileme Viseyno (External Evaluator) | +91 9774978143 |
| Raju Gupta (Finance Evaluator) | +91 7085169800 |
| Officials from SACS/TSU (as facilitator) Ms. Imtisenla | +91 9856534957 |

| Name of the NGO: | Kripa Foundation Tseminyu |
| --- | --- |
| Typology of target population | Core Composite (IDU/ FSW) |
| Total population being covered against target: | April 2014- March 2015:; April 2015 - Jan. 2016. IDU; FSW; IDU; FSW. Target; 330; 100; 330; 100. Achievement; 324; 98; 327; 100. |
| Dates of Visit: | 17 & 18th February 2016 |
| Place of Visit: | Kripa Foundation DIC, Tseminyu New Town. |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 79.2% | B | Good | Recommended for Continuation |

Specific Recommendations:

Organizational capacity: - TI NGO needs to ensure that part time Doctor attend STI Clinic regularly. (Staffs reported that part time Doctor never visited clinic during assessment period). - All PE positions to be filled as per contract with NSACS (only 10 PEs on board as against contract agreement of 13 PEs with SACS). - Attendance, leave and movement registers needs to be updated properly. - Capacitate Accountant in Financial Management and Book Keeping. - Systematic advocacy plan needs to be put in place and followed- up. - Involve stakeholders in monitoring project activities. - Endeavour to link-up community members to various Government Welfare Schemes. Financial management: - Minimize cash transaction above ₹ 5000/- - Maintain a separate ledger for vouchers. - Continue to comply with Audit observation and ensure that all recommendations are followed. - Cash in hand should be less than ₹5000/- as per NACO’s directive. - Separate quotations for purchase of assets and commodities should be available for the Tseminyu TI project. Program Delivery: Outreach: - PM to strengthen advocacy initiative and overall monitoring – outreach planning, targets, reports maintained by field workers. Analyse field reports for prioritizationof HRG based on risk assessment. - Capacitate ORW & PE on documentation and prioritization based on risk assessment. - Hot spot level group meeting needs to be scaled up and documented properly. Commodity: - Ensure maintenance of buffer stock for commodities (N/S & Condom) and STI medicines. Stock out witnessed during assessment period. - Requires restructuring of demand gap analysis for N/S needs since there are very few injectors. Clinic Service: - Ensure that all referrals for RMC, Syphilis and HIV testing are followed-up. - STI medicine Kit 3, 4, 5 & 7 to be made available for the all the TI clinics. Stock out reported since Oct. 2014. - Increase second time testing for syphilis and HIV testing as per target. - Capture information on abscess dressing services provided in the field/ home level. Enabling Environment: - Involve stakeholders in monitoring project activities. They can be included in Crisis Management Team for effective response to issues related to HRGs. - Systematic advocacy plan needs to be put in place and followed- up. - Continue to observe/ organise community events. Encourage formation of support groups for empowering HRGs.

Name of the Evaluators				Signature

| Kholi. A |  |
| --- | --- |
| Kivileme Visezuo |  |
| Raju Gupta |  |