Annexure: B

Reporting Format-B

Introduction

O Background of Project and Organisation

Prodigals Home (PH) has been working on the issues of HIV/AIDS for more than a decade. It has been concentrating on education on prevention, control & referral focusing on the FSWs, Drug Users, Street Children and school drop outs in the field of HIV/AIDS. The organization run a Drop-In-Centre (DIC) each for Female Sex workers and Migrant population vulnerable to HIV, rehabilitation Centre for male drug users and a Short stay home for vulnerable girls/women. PH provides treatment for STI and referrals for STI, HIV/AIDS and related health problems.

O Name and address of the Organization

Prodigals’ Home

NSCB Complex, 4th Floor

PB-148, Khermahal, Circular Road

Dimapur 797112

Nagaland

O Chief Functionary			:  Ms. Ela

O Year of establishment			: 1990

O Year and month of project initiation	: 1st April, 2011

O Evaluation team:

- NiloloChisho (External Evaluator)

- Nukshinaro (External Evaluator)

- Debashis (External Finance Evaluator)

- Haing        (SACs Observer)

O Time frame:

Assessment Period: 	April 2014- January 2016 [22 months]

Profile of TI

O Target Population Profile:Migrants

O Type of Project:Core Group(Bridge Population).

O Size of Target Group(s)

|  | April 2014- March 2015: | April 2015- Jan. 2016: |
| --- | --- | --- |
| Target | 3000 | 3000 |
| Achievement | 3230 | 2739 |

O Target Area:Dimapur

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

The Organization provides strong direction, support, and accountability to programmatic leadership and engaged as a strategic resource to the TI-Migrant Project. Communication between head office and project reflects mutual respect, appreciation for roles and responsibilities, shared commitment and valuing of collective wisdom.

II. Organizational Capacity

1. Human resources:

- All appointment /contract letters in placed but Renewal system not in practised.

- 2 ORW turnover witnessed in 2014-15 but position filled in the same month.

- 1 PE in 2014-15 and 2 PEs in 2015-16 turnover witnessed, position filled within the time frame.

- Program Manager, Nurse cum counsellor, M&E/ Accountant, ORW [n=3] part time doctor and 7 VPL on board.

- Project is adhering to supervision and reporting structures

- Potential peers are identified and are immediately absorbed in to the project activities whenever turnover occurs.

2. Capacity building:

All staff and PEs are trained by STRC/SACs.

- Infrastructure of the organization:

- One main TI DIC in place and project has a sub-DIC with one room which has been donated by migrant stakeholder.

- Project DIC has 2 rooms and partitioned with space for recreation, office work and has accessibility of conference room of the organization.

- Basic office furniture and stationeries in place.

- Laptop, Computer and peripherals in place.

Documentation and Reporting:

- Project is using standard data collection tools/ reporting formats provided by NACO with other additional register.

- Weekly/ monthly reporting system in place.

- Review for necessary actions/ feedbacks being taken during weekly and monthly meetings.

- ORWs assist respective VPLs in filling up formats.

- All formats filled, compiled and submitted to Program Manager for further reporting to SACs.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

Updated line-list is available and used for tracking all the project level services

2. Micro planning in place and the same is reflected in Quality and documentation.

Outreach and micro plan in place and the same is used by ORW, PE and ANM.

3. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- Mar. 2015: | April 2015 – Jan. 2016 |
| --- | --- | --- |
|  | Migrants | Migrants |
| Target | 3000 | 3000 |
| Achievement | 3230 | 2739 |

6. Outreach planning – quality, documentation and reflection in implementation

- Micro planning in place at ORW level and used for all outreach activities.

- VPLs are illiterates and therefore ORWs assists their respective PEs in data collection and report writing.

- 3230 migrants in 2014-15 and 2739 migrants contacted and line listed at project level. Monthly and weekly plan in place and all referrals and contact through outreach sessions are documented but challenges faced on follow up on referrals due to high mobility.

7. PE: HRG ratio:

Ratio of PE to HRGs is 1:569 (6 PEs working with project more than one year, 5 PEs are from the source.)

8. Regular contacts

April 2014 to March 2015:

STI:8% (419) of migrants reached           DIC: 43% (2248) of migrants reached           Counselling: 62% (3239) of migrants reached                                              April 2015 to January 2016:

STI: 4% (185) of migrants reached          DIC: 37% (1691) of migrants reached           Counselling: 61% (2744) of migrants reached

April 2014 to March 2015:      No. tested HIV positive: 7

April 2015 to January 2016:   Nos. tested HIV positive: 4. All HIV tested positive are contacted regularly and provides services).

9. Documentation of the peer education

- Peer field dairies and Form B, Form B-1in use by PEs to capture their field activities.

- Peers are illiterate and hence ORWs assist them in documentation.

10. Quality of peer education- messages, skills and reflection in the community

- Target population has basic knowledge on HIV, STI and proper condom usage

- Community members are satisfied with the project services.

- Community members requested if free condoms can be made available.

11. Supervision- mechanism, process, follow-up in action taken etc

- Supportive supervision is been provided to all PEs by their respective ORWs who also assist them during their field visits.

- On-site supervision is being carried out by the ORW whenever a new PE has been appointed.

- Overall supervision of outreach plan and field activity is done by Program Manager.

- Follow up actions are taken during the weekly/monthly meetings.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- TI project has two STI delivery points: TI project sites and mobile clinic. Basic clinic equipments and instruments available.

- On an average, 3-4 health camps were conducted and mobile ICTC accompany them.

- A total of 50 health camps has been conducted with 3036 migrants attendance in 2014-15 and 49 health camps conducted  with 2872 migrants in attendance in 2015-16.

- Different doctors are engaged for Health Camps as per availability.

- In most cases target population do not visit project site clinic because they do not get time or they do not want to bear the cost of travelling to Project clinic.

- Target population attendance is also poor unless there is a free distribution of general medicines during the health camp.

- General medicines procured from funds generated through free will donations and use during health camp.

- A total number of 5983 (3239+ 2744) target population were counselled by Nurse in two project year.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Basic clinic equipments and instruments available.

- TI project uses only KIT 1 & 2 as per requirement/ cases reported.

- No stock out of STI medicines reported.

- Referrals are also linked to District Civil Hospital.

3. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- Syndromic treatment protocols followed.

- A total of 419 STI cases were treated out of which 11 at Govt Clinic and 408 at NGO Clinic in 2014-15.

During 2015-16, a total of 185 cases were treated,4 at Govt clinic and 181 cases at NGO clinic.

- Followed up on STI cases not done due to mobility and engagement in wage labour activities with achievement of below 20%.

- ICTC referrals done at two delivery points: Mobile ICTC and District Civil Hospital.

- 10 out of 11 targeted population who tested positive in two project years linked to ART, District Civil Hospital, Dimapur

- Organization has been contracted by RNTCP to dispense DOTS and all TB cases are referred to the TI project.

- During the project year 2014-15, 24migrants were referred and 23 tested TB and 9 are on DOTS.

And in the year 2015-16, 24 migrants were referred and 15 tested and 3 are on DOTS.

5. Documentation-

- Standard clinic data collection tools in use. Referral slips are provided for every referral.

- 2 STI KITs (KIT 1& 2) used by project as per the frequency of cases reported.

- No stock out of STI medicines reported during the project year.

- System for procurement of medicines in place and supporting documents in place.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- 58 outlets (11 traditional+ 47 non-traditional)established.

- 3 new outlets established as per contract in 2015-2016

- 45 non-traditional outlets established between April 2014-March 2015.

- 47 non-traditional outlets established between April 2015-16 Jan.

- 13644 pc of condom sold between April15-Jan16(7218 sold from non-traditional, 2416 from traditional and 4010 on field.)

7.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

13644 pc of condom sold between April15-Jan 2016 (7218 sold from non-traditional, 2416 from traditional and 4010 on field.)

8. Information on linkages for ICTC, DOT, ART, STI clinics.

- HIV testing done during health camps with Mobile ICTC.

- Targeted population are also referred to District Civil Hospital for STI, ICTC and ART.

- All TB cases referred to project clinic (Organization contracted by RNTCP to dispense DOTS)

- TI project also handles STI cases and provides medicine KITs

9. Referrals and follows up

a. Health Camps:

- 50 Health Camp conducted with 3036 participants between 2014-2015.

- 49 health camps conducted with 2872 participants between 2015-2016 along with doctors and counsellor/nurse.

- Multiple (different) doctors engaged for health camp as per availability.

- Referral for ICTC and STI are also sent to district hospital.

b. STI:

- 419 STI cases treated (11 at Govt. Clinic +408 at NGO clinic) in between 2014-15.

- 185 cases treated (4 at Govt.clinic+181 NGO Clinic) between 2015-16.

- Achievement   less 20% is due to high mobility of migrants.

c. HIV Testing:

- 3230 referred and 1369 HRGs (MICTC 966, Dist. Hospital 325, PPTC 76, and RNTCP 2) tested HIV in 2014-15.

- 2739 referred and 973 HRGs (MICTC 757, Dist. Hospital 151, PPTC 56, and RNTCP 9) tested HIV in 2014-16.

- 7 tested Positive and 6 linked to ART, 3 dropped out in between 2014-15.

- 4 tested positive and all linked to ART in between 2015-16.

d. TB:

- A total of 23 migrants in 2014-15 and15 migrants in 2015-16 suspected of TB symptoms were referred and linked to TB programme at the TI project (Project contacted to provide DOT by RNTCP).

- Out of which 9 tested positive and on DOT in between 2014-2015.

- 3 migrants tested positive and on DOT between 2015-Jan 2016.

V. Community participation

1. Collectivization activities:

No SHG or CBO till date.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members involved in the project as Peer Educators and VPL.

- Stakeholders also involved in project activities by coordinating with outreach/ health camp teams.

- Stakeholders also involved in project activities by giving referrals to the TI project.

- Stake holders are part of Crisis Management and Program Management board.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- TI project provides STI treatment and DOTS from project clinic.

- Complicated cases are referred to District Civil Hospital at Dimapur.

- Health camp/ melas done in collaboration with Mobile ICTC.

Target populations are also referred to District Civil Hospital at Dimapur for HIV testing.

- Linkage established with RNTCP,PPTC and DOT at District Hospital, Dimapur.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

- 3230 referred and 1369 HRGs (MICTC 966, Dist. Hospital 325, PPTC 76, and RNTCP 2) tested HIV in between 2014-15.

- 2739 referred and 973 HRGs (MICTC 757 Dist. Hospital 151, PPTC 5, and RNTCP 9) tested HIV in between 2014-16.

- 7 tested Positive and 6 linked to ART, 3 dropped out in between 2014-15.

- 4 tested positive and all linked to ART in between 2015-16.

Support system developed with various stakeholders and involvement of various stakeholders in the project.

- Networking with various stakeholders done and contact numbers and address available at project level.

- Stake holders are also part of Crisis and Program Committee.

- Stakeholders involved in project activities by referring target population to the project services, mobilization during health camps and advocacy.

VII. Financial systems and procedures

1. Systems of planning:

- Systematic planning not in place.

- Utilization of fund according to the budget allocated by SACs.

- Temporary Loans are taken for expenditure during shortage of fund.

2. Systems of payments-

- Most of the payments are made through bank.

- Some payment of above Rs 5000/-in cash are also found

- Separate Bank Account maintain for TI.

- Bank Account opened at IDBI Dimapur Branch.

- Vouchers are not machine numbered.

- Vouchers and bills in place supported with kacha bill and cash memo.

- Approval system practiced and all approval is done by the Director & Asst. Director.

- Before making any payment a prior approval is required from the Director

- Some mismatch found in cash book, ledger & other registers.

- More than Rs 5000/- cash in hand.

3. Systems of procurement-

- There is no proper system is in place.

- Three quotation systems is not followed.

- Buffer stock is not maintained for STI med and Kit.

- Some mismatch found between expenditure & events register.

.

4. Systems of documentation-

- Bank Reconciliation Statement is practiced.

- Assets register is maintained and codified and same is marked on the asset.

- Audit reports are available at DIC. Some compliance of Audit observations is taken.

- Submission of SOE is done on regular basis.

- Cash book is updated only till 31th 1Dec 15.

- Voucher’s are not machine numbered & using common vouchers for all branches of the NGO.

- The TI is using TALLY Accounting software for accounting but they are creating different organisation in Tally for different period.

- The TI is having many pass book for Bank Account for the same period.

- The following books of accounts and register are maintained :

a)  Cash book

b)  Ledger

c)  Stock register for STI Medicines & Kit.

d)  Attendance Register.

- Salary Register

- Bank pass book.

VIII. Competency of the project staff

VIII a. Project Manager

- Bachelor in Divinity and entry point in TI project as ORW. Project proposal are drafted by PM and final proposal done worked out with PD and submitted to SACS. Yearly and monthly plan in place and all outreach activities based on these plans.

- PM has a fair knowledge about the financial management of the TI project and co-ordinate with accountant on monthly budget requirements and submission of SOE.

- Program Manager takes responsibility in CMIS entry and familiar with CMIS software and computer basics.

- Performance of staffs is assessed during weekly and monthly review meetings for scaling up of outreach activities.

- ORWs are in the field 4 times in a week and supervise their PEs during each field visits.

VIII b. Counsellor

- Nurse able to explain assessment on risk and risk reduction.

- Nurses attended trainings on counselling and HIV from STRC and have basic knowledge on HIV and STI.

- Standard formats of clinic data collection tools is used and maintained on a regular basis.

- On an average 3 health camps are conducted in month and both the Nurse and Doctor involved in all health camp/ melas.

- Counselling and referrals are also provided to target population for HIV testing, STI and TB during health camps.

VIII c. ORW

- ORW aware about various indicators for their respective PEs and also assist them in their outreach.

- Supervisory visits done 4 times in a week by each ORW based on weekly review meetings and documentation available and updated in staffs weekly and monthly meetings.

- Outreach plan in place for the ORWs and displayed at the project level.

- Possess basic knowledge on HIV &AIDS,STI symptoms, and condom usage

- Conducts sessions at the congressional sites.

- Provide and assist PEs in filling up formats.

VIII d. Peer educators

- Difficulty faced on prioritizing outreach because target population moves to source state and is seasonal in nature. Outreach plans based on availability of free time of target population.

- PEs not very clear on importance of going for RMC and ICTC testing.

- Basic skills in place for proper usage of condoms and able to explain basic symptomatic STI’s.

- PEs able to identify condom outlets and referral centres and availability of basic services provided from TI project.

VIII e. M&E cum Accountant

- The TI has an M&E cum Accountant whose qualification is B.Com and has been working for few years in the project. The M&E cum Accountant has good knowledge in computer. The M&E cum Accountant has received trainings from NSACS still lacks in accounting knowledge. The accountant was also not able to provide proper justification in some areas of expenditures.

IX. a. Outreach activity in Core TI project

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- 99 Health Camps conducted during two project years and project part time doctor and nurse/ counsellor attended all health camps.

- Referrals  services also provided

- During the two project years a total of 3230 and 2739 migrants were provided with project services.

- In the last 3 months 431 target population attended project health camp.

- 604 STI cases detected during the two project years and provided treatment. Follow-up cannot be achieved due to mobility.

- Out of 84 Syphilis testing done, 14 tested at Govt .Clinic and 70 tested at NGO clinic (MICTC) during two project years.

- A total of 5969 migrants referred and 2342 got tested for HIV during the two project year.

- 7 tested positive in 2014-15, 6 linked and 4 tested positive all 4 migrants on ART in 2015-16.

- Stakeholders are informed in advance about outreach for respective congregational sites by PEs or ORWs.

- Target population reported that they are very happy with the project initiatives in caring and providing services to them.

- Target population requested for avail of free condom.

XI. Community involvement

- Target population involved in the project as VPL and as stakeholder. Referrals are also done by stakeholders to the project.

- Health camps are conducted as per PE’s and stakeholder’s approval.

- Stakeholders and target population involved in all project activities: IPC sessions, street plays, congregational meetings, mid-media campaigns, advocacies and awareness programs.

XII. Commodities

Condom:

- 58 outlets (11 traditional+ 47 non-traditional) established.

- 3 new outlets established as per contract in 2015-2016

- 45 non-traditional outlets established in between April 2014-March 2015.

- 47 non-traditional outlets established in between April 2015-16 Jan.

- 13644 pc of condom sold between April15- Jan 16(7218 sold from non-traditional, 2416 from traditional and 4010 on field.)

XIII. Enabling environment

- 76 Advocacies conducted between April 2014-March 2015 and 53 in between April 2015-Jan 2016.

- Advocacies held at all levels and documentation in place.

- Programme Management Team set up with representation of 2 GBs, 4 employers of migrants and TI staff in placed but Meeting minutes not available. However, documentation on Advocacies held with these stakeholders and Employers are available and maintained.

Best Practise if any;

- The organisation supports the project program financially when there is a delay in fund release

- The organisation generates fund for procuring general medicines  for Health Camps through free will  donations from well wishers.

Confidential			Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Niloli Chisho (Team Leader) | 9612750950 |
| Nukshinaro (External Evaluator) | 9863817888 |
| Debashish (External Finance Evaluator) | 8415829714 |
| Officials from SACS/TSU (as facilitator) Haing | 9774419215 |

| Name of the NGO: | Prodigal’s Home, Dimapur |
| --- | --- |
| Typology of target population | Migrants |
| Total population being covered against target: | April 2014- Mar. 2015:; April 2015 – Jan. 2016. Target; 3000; 3000. Achievement; 3230; 2739. |
| Dates of Visit: | 6th & 7th March 2016 |
| Place of Visit: | Dimapur. |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 80.9% | A | Good | Recommended for continuation. |

Specific Recommendations:

- Ensure that Contract Renewal of all the staff appointed is in place. - Ensure follow-up of STI services whenever possible- high mobility. - Project should ensure that meeting minutes of Programme Management Committee is in place. - Project should ensure buffer stock of commodity such as Syphilis kit and STI drugs. - All transaction of above Rs5000/- are to be made by cheque. - Ensure Vouchers are Machine numbered. - Cash book are updated on daily basis. - Ensure that financial expenditures tallies with the events conducted. - The project adheres to the Compliance of Audit Observation. - Quotation system to be followed. - Should not have more than one Bank Pass Book for the same period. - Should not create different organisation for the different period.

Name of the Evaluators				                                                       Signature

| Nilolo Chisho |  |
| --- | --- |
| Nukshinaro |  |
| Debashish |  |
| Haing |  |