Nagaland State AIDS Control Society

Targeted Intervention- Evaluation Report

- 2016-

Shansham Organization

Typology: IDUs, FSWs & SPs

Mon Town, Mon District

Nagaland

Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eiliakim Sorhie – External Evaluator

- Mr. Sanjay Paul– Finance Evaluator

- Ms. Abonuo Khatso – NSACS Observer

Introduction

- Background of Project and Organisation

# The “Shansham Organization” with its head office at Mon town, was formed by a group of like minded youth to address the social issues in the district in the year 2000, and registered Societies Registration Act of 1860, State of Nagaland. The organizations mission is “to work for and with the people and facilitate participatory approach in articulating the communities’ problem and development”. Its vision is to provide a platform for everyone’s participation towards enlightenment and social development. 

The organization have a large number of volunteers who participates in the organizations activities and various programes. The organization is currently implementing 2 Targeted Intervention project under NSACS; One being in Mon town and the other at Naginimora, Mon district; and also runs a Rehabilitation center for Drugs affected people.

# The Targeted Intervention project at Mon town is core composite for IDUs, FSWs and SPs and have been continuing this project for 15 years since the project inception in 2001.

- Name and addressof the Organization: Shansham Organization, Post Box No.9, Mon - 798621 Nagaland

Contacts: 9436015493/8131091247

email:shansham_06@yahoo.co.in.

- Chief Functionary: Mr. L. Shakai Konyak (Secretary, Shansham Organization)

- Year of establishment: 2000

- Year and month of project initiation:2001 [2001 – 2005 under a Mother NGO – Prodigals Home, and from 2006 onwards became independently implemented]

- Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eiliakim Sorhie– External Evaluator

- Mr. Sanjay Paul – Finance Evaluator

- Time frame:April 2014 – January 2016 [ 22 Months]

Profile of TI

- Target Population Profile: Core Composite (IDU& FSWs, SPs)

- Typeof Project:  IDUs, FSWs and SPs.

- Sizeof Target Group(s): 500 IDUs& 150 FSWs,  150 SPs [2014- 2015 – 2016]

- Target Area: Mon Town

Project SITES:Walo ward, Shamnyu, Zuklom, Tanlao, Wagiem, Techa, Jahjong, Chingai, Shantham, Tompang, Thamnan, OST.

I.Organizational support to theprogramme

The overall organizational support of “Shansham Organization” towards the TI project at Mon, is supportive and cooperative towards the IDU community as well as to the other target groups. The organization have also intitiated as part of its initiative towards the community behaviourial change by running / opening a rehabilitation center for the community which is being supported by the organization and the organization’s well wishers.  The organziationis very much commited to the cause and issues faced by the IDU community.

The oveall Board / Organization members involvement in any of the the Project’s activities in the TI Project at Mon is limited to a few areas of implementation and levels in the TI Project. The TI Project’s activites is being managed and implemented by the PM, ANM, Counsellor, Accountant and Outreach Team based on their understanding and capacity, without the active involvement  of the TI Project Director.

| Oganization’s Board of Members |  |  |
| --- | --- | --- |
| Sl. No | Name | Designation |
| 1. | Mr.H. Penjun Konyak | Chairman. |
| 2. | Mr. L. Shahkai Konyak | Secretary. |
| 3. | Mr. Joseph Chipa Konyak | Programme Manager |
| 4. | Mr. Anok Bangpen Konyak | Member |
| 5. | Mr. Longna Konyak | Member |
| 6. | Miss. Lijao | Member |
| 7. | Miss. Manli | Member |
| 8. | Mr. Popa | Member |
| 9. | Mr. Manging | Member |

II.OrganizationalCapacity

- Human resources:The Staffing pattern in the TI Project have been implemented as per the NACO guidelines and as per the Project proposal and Budget approved by NSACS. PM, Accountant, ANM, Counsellor and ORWs. The project staffs have been provided with appointment letter along with their roles and responsibilities of the organization as per the organization’s guidelines and also their roles and responsibilities is available in the TI project; While a few of the staffs appointment have not been renewed on a yearly basis while a few of the projects personnels appointment was missing for some part of the project period.  However, the overall project staffswere able to define their roles and responsibilities within the TI project.

On the other hand the PEs appoinment were not given individually but on the same and single appointment letter with extentions on a 6 months basis. The project staffs are cooperative and helpful towards each other, especially the  PEs and ORWs who are also from the IDU and FSW community respectively.

| Sl. No | Name | Designation | Date of Appointment. |
| --- | --- | --- | --- |
| 1. | Mr. L. Shahkai Konyak | Project Director | 2001 |
| 2. | Mr. Joseph Chipa | Programme Manager | 2001 |
| 3. | Chemba | Accountant cum M& E | 5th January 2010 |
| 4. | Sashimeren | Counselor | 05/01/10 |
| 5. | Esther | ANM | 01/09/14 |
| 6. | Apunu | ORW (IDU) | 01/02/16 |
| 7. | Longna | ORW (IDU) | 01/10/10 |
| 8. | Bannyan | ORW (IDU) | 01/09/14 |
| 9. | Stephen | ORW (IDU) | 01/04/12 |
| 10. | Wangyao | ORW (IDU) | 01/04/07 |
| 11. | Lijao | ORW (FSW) | 01/06/15 |
| 12. | Wangai | PE | 01/04/04 |
| 13. | Aphong | PE | 01/10/13 |
| 14. | Wanching | PE | 01/12/15 |
| 15. | Shangti | PE | 06/01/15 |
| 16. | Chingkhat | PE | 03/10/14 |
| 17. | Chuba | PE | 05/10/15 |
| 18. | Pongtok | PE | 07/04/14 |
| 19. | Lamwang | PE | 06/09/14 |
| 20. | Tuchu | PE | 02/09/14 |
| 21. | Thangwang | PE | 03/12/15 |
| 22. | Khongwang | PE | 03/10/15 |
| 23. | Manging | PE | 02/09/14 |
| 24. | Angela | PE | 06/09/14 |
| 25. | Limei | PE | 03/10/10 |
| 26. | Apon | PE | 04/07/15 |
| 27. | Moya | PE | 01/06/15 |
| 28. | Anok | PE | 01/07/14 |
| 29. | Nyulong | PE | 01/08/10 |

- Capacity building:The TI staffs have been trained by State Training and Resource Centre,Identified Learning Site – Bethesda for various trainings of the project staff for the level of PM, ANM, ORWs, Accountant and PEs. Topics covered during the trainings wereon Orientation, Induction and Refresher, Harm Reduction, Data Collection Tools, OST, Finance Management, SIMS, Refresher, Counselling & STI Counselling.

At the Organization / Project level the project had only conducted a one time In-house training for the PEs during the month of September 2014, with no further follow up or continuety of the inhouse training for the new PEs or refresher for the project team.

- Infrastructure of the organization: The Project Office is equipped with a 6 roomed infrastructure which includes STI Clinic, Counselling room, separate rooms for the Drop in Centre for IDUs and FSWs, PM& Accountant room and ORWs room. The office locationis suited in the central part of the town and is easily accessible by the community for their needs and accessibilty to services provided by the TI Project.

4. Documentation and Reporting:The TI project staff’s are maintaining documents and procedures as per the NACO Guidelines to a certain limitation without proper verification and monitoring. Adherance to SACS protocol has not been witness to a certain limitation; however feedbacks and suggestions by NSACS officials have not been followed or carried out properly by the TI project.

Data collection tools formats: Form A, Form B& B_1, Form C, and Form D of the Data Collection Tools, have been maintained by the project, however proper authentication and cross verification of the Peer Educators Dairy and reports received form the field must be emphasised.

The Overall project planning, outreach as well as micro planning is not properly implemented or followed by the Outreach team to track HRGs for services provided by the Project such as ICTC Testing, STI Testing, Syphilis Testing etc.. Planing is being done by the PM alone and distributes targets to the Outreach team for their coverage with the Outreach team’s particiation in the planing.

Performance review mechanism is partially witnessed. TI needs to introduce intensive and regular follow up mechanism, ORWs monitoring and supportive supervision systems is not in place. Organizations internal project monitoring and supervision system needs to be strengthened to review regular project performance by the Project Director and Program Manager.

CMIS and SOEs are being sent to NSACS on a regular manner indicating the monthly project performance and expenses.

II.Program Deliverables

Outreach

- Line listing of the HRG by category: Sitewise Line Listing and registration of all the HRG have been done and completed as per the Project proposal and as per the Targeted Project population coverage (ie. a target of 500 IDUs &150 FSWs and 150 SPs). The active HRGs are being covered and reached out with services provided by the project, such as Needle & Syringes and Condoms, ICTC referrals, STI treatment etc.

- Micro planningin placeand the same is reflectedin Qualityand documentation:Planning has been introduced by the TI project for service delivery ( N/S and condoms) which is being done by the outreach team; however the use and implementaton of micro plan is not reflected in the activities and documents of the PE &ORWs for tracking individual HRGs. Risk assessment and prioritization of HRGs have not been compiled or identified by the Project. Proper implementation and use of Micro Planning by the Outreach team needs improvement for outreach activities and service deliveries. Regular field intervention, effective supportive supervision of ORWs and PEs at the hot spot and office level (documentations and record keeping) needs to be initiatedand verified by the PM.

3.Coverage of target population (sub-groupwise): As per the Targeted population of 500 IDUs, 150 FSWs& 150 SPs [2014-2014-2015], more than 80% of targeted population are being provided with services by the TI project on a regular basis or as and when needed by the HRGs.

4.  Outreach planning: Quality of Outreach planning and its implementation as well as documentation is not properly implementedby the TI Project. Activities and tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization and proper planning. Planing is being done by the PM alone without proper and active participation of the outreach team; targets and achievements are being given and provided to the Outreach team for their monthly coverage.

Activities such as FGD, Hotspot Level meeting, Field Visits, Clinical services and other services provided by the TI Project are being done in an unplanned and unsystamatic way.

5.   PE: HRG Ratio: The TI Project have a total of 15 PEs for IDUsan 3 PEs for FSWs who are looking after 13 project sites under the TI Project.

6. Regular contacts:Regular contact [ie 2 times / per month for the FSWs as per NACO guidelines] of the HRGs is being maintained by the Outreach staffs (PEs); and regular contacts for IDUs are also being maintained by the PEswho are providing N/S and Condoms to the HRGs which is >80% out of the active HRGs for FSWs; and <70% out of the active HRGs for IDUs.

However, PEs are not being able to categorized or prioritized the HRGs under them but have been able to to make aware the HRGs on the Risk and Vulnerabilities of their behaviour, Harm Reduction, Overdose etc. Linkages for clinical services and ICTC referrals or follow ups is being coordinated with the TI clinical ANM.

7. Documentation of the peer education: Peer Educator document’s which is the backbone of the TI Project are being maintained as per NACO’s data collection tool.However, the level of understanding of the PEs in terms of risk assessment, vulnerability and prioritization of the HRGs is still lacking among the Peer Educators. Also, the flow of distribution of commodities remains to be constant throughout the project period, which is reflected in the “Form B_1 – PE Weekly Planning and Activity Sheet”, which is not properly authenticated or verified by the ORWs with the Peer’s dairy.

PEs also maintains their own PE dairies, for their distribution of Commodities towards their respective clients. However little information was available as the PEs dairy were not properly maintained and also the old dairies of the PEs were not maintained at the TI Project Office or were missing.

7. Quality of peer education: Interacting with the Peer Educators who came to the Project office during the Evaluation, their qulaity of knowledge and communication skills is not very clear to address the issues of HIV and AIDS, STI, Risk Behaviour, Harm Reduction, drugs related issues and other related basic issues was being witnessed;

The Peer Educators are selected from respective areas and also belong to the community background; there is a need to make Peer Educators aware of the objectives, goal and planning process towards risk behaviour among the target population.

Peer Educator’s skill and capacity needs to be enhance and capacitated with regular and effective orientation at the TI Project level, with proper assessment, mentoring and monitoring.

8. Supervision: The overall supervision and monitoring of TI Project is overlooked by the PM and is being supported by the ANM, Counsellorand ORWs which is witnessed in the Project. Although documents on follow up are being maintained, proactive measure and assistance needs to be taken up to further enhance the outreachactivities by the Outreach Team for proper follow up on Risk Behaviour and reduction Counselling, ICTC, STI referrals and other services as well as behavioural change. Supervision by the Project Director in terms of the overall performance of the TI project is negligeble in the project.

IV. Services

- Availability of STI services: The TI Project have a STI clinic managed by the ANM and is linked to one visiting Doctor, who is available on call; The clinic have adequate and supply of STI drugs and testing kits which is being supplied by NSACSand also purchased by the TI project as per the norms; The TI is linked to the Static ICTC and STI Clinic as well as the Mobile ICTC unit; Follow up mechanism is also in place which is reflected in the number of referrals for HIV and Syphilis testing.

2. Qualityof theservices:The TI’sSTIclinc cum Counselling room as well as a separate Counselling room for the male counsellor which have privacy and is being maintained and managed by the ANM and counsellor. Clinical equipments are available in the STI Clinic, with adequate supply of medicines. The TI is also linked to a Government Clinic as well as Mobile Clinic, where tests and linkages for syndromic cases are being treated.

3.  Qualityof treatment in the serviceprovisioning:The STI clinic have provided services and treatment to the HRGs with STI treatment, Abscess management, Counselling and linkages for ICTC testing; with 2316 episodes of STI Counselling for IDUs and 653 episodes for FSW; 2316 episodes of counselling for IDUs and 653 FSW; and 176 registere FSWs with  Presumptive Treatment;

4.  Documentation:The TI Clinic as well as Counsellor is maintaining registers related to services delivery maintained by the ANM which includes Network Clinic Register, Clinic Daily Summary Sheet, Medicine Stock Register, Referral Slips, Counselling Register, and RMC Register. The system of procurement of medicines is not witness in the project.

The Needle Syringes and Condom stock and distribution registersarejointly maintained by the ORWs, ANM and PM.

5.  Availability of Condoms& Needle Syringes: The TI project is distributing free condomswhich are being acquired from NSACS or DAPCU.Social marketing of condoms have been initiated, which is being done on a need based. The TI is maintaing stock in hand,while buffer stock for 3 months is not being maintained at the TI Project level.

The distribution of free N/S is being purchased by the TI project and is being purchased without proper planing or assessment for 3 months buffer stock; N/S are being purchased at an interval of 15 days gap to 3 months gaps. The Needle Syringes and condoms are being distributed by the PEs and ORWs in the field level, while at the DIC level it is through the ANM and Counsellor.

Condom and N/S demand and gap analysis have not been done / implemented at the TI Project level.

6.   No. Of Condoms distributed: A total of 106,690 (52187 for IDUS + 54503 for FSWs) numbers of free condoms were distributed through the Outreach Team, ANM and Counsellor during the period of April 2014 to January 2016; while promotion of Social Marketing of Comdoms was done on a need based and registers and details were mainited only from 2nd February 2016.

7.  No. of  Needles /Syringes Distributed: A total of 100,423 number of free Needle /Syringes were distributed during the period of April 2014 to January 2016 through the Outreach Workers, Peer Educators, ANM, Counselor with a returned of83,436 number of Needle Syringes through the NSE programme which is 83%.

Waste Disposal Management is in place and disinfection of Needle / Syringes is being performed in the DIC or Project Office by the ANM or Counselor with the support of Outreach Worker; while the final disposal is being done at the PHC - Mon.

8. Information on linkages forICTC, DOT, ART, STI clinics:Linkages for STI testing and syndromic cases withthe Government Clinic, ICTC, mobile ICTChas been effective with 25% IDUs and 10% FSWs having undergone Syphilis testing; and 54.3% IDUs and 51% FSWs having undergone HIV testing.

RNTCP awareness among the HRGs have been done by the TI Project; however it may also be noted that no cases were detected for TB during the Project period.

9. Referrals and followsup: Referral mechanism is being maintained by the TI and follow up mechanism has also been maintainedand followed up by the ANM and counsellor along with the ORWs.

V. Community participation

- Collectivization activities: Collectivization or formation of groups have not been initiated by the TI Project during the project year.

2. Community participation in project activities: The overall community participation in the Project is  prominent with 4 ORWsbelonging from the community,  and all the PEs are also from the background. The overall communities particiation in the project is high with support and involvement of many HRGs at various level of the project activities, such as FGD, DIC level visits, events, OST referrals and rehabilitation.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc: The TI Project have established links with Static ICTC, Mobile ICTC, and STI clinic.

- Percentages of HRGs tested inICTC: 54.3% IDUs and  51% FSWs of the registered / active HRGs have undergone HIV testing during the project period [ April 2014 – January 2016]

- Support system:The TI Project have support system only on clincal service delivery with the ICTC, Mobile ICTC and STI centre;  The TI have developed a good rapport with different stakeholders and advocacy along with sensitization to the stakeholder is being done from time to time. The stakeholders met, has also reported of being invovled and participated with the projects actitives at various levels of intervention;

VII. Financial systemsand procedures

- Systems of planning: The organization/management is allowing the Project Office  to prepare the books of accounts every months as per the budget allotment and budgeted heads provided by NSACS, without planning (either quarterly or yearly) which should have been based on activity wise as well as release of funds. Expenses are being made randomly without proper or system of planning.

The TI have spend almost the whole amount of funds released from NSACS.

2.  Systems of payments:Generally all the non salary payments, are being made  partly by cheque and partly by cash.  The Project is maintaining printed vouchers which are machine numbered and with the  name of the organization and are being countersigned by the Accountant, PM and PD. There approval systems is made by the Project Director. Most of the program expenses related are made by Cash and in some cases bills / cash memos were not authentic.

The TI has taken loan during the year through cash and payment is also being made through cash and some via cheque. Both Stock and assets registers are in place and updated; assets were not properly codified.

3.  Systems of procurement: There is no system for collecting any quatations before purchasing of bulk commodities (Needle & Syringes, Syphilis Testing Kit, Abscess prevention etc).  Stock & issue registers is being maintained with a few cases of nontallying. There is no systems for quality checking of the product purchased.

- Systems of documentation: The project is maintaining separate books of accounts for separate project year 2014-2015-2016, such as Cash Book, Ledger, Separate bank pass book, salary register, attendence register, asset register etc which are being  updated regularly. BRS is not being prepard or maintained by the organization.  However record keeping of payment vouchers, bill and cash memos have not been systematized or kept in orderly manner. No minutes of financial planning or documents of approval for expenditure was available.

VIII. Competency of the project staff

VIII a. Program Manager:The Program Manager is a BA Graduate, and have been working with the TI project since 2001 when the project was under the mother NGO (Prodigals Home) and continued to lead the project when it became independent in 2006;

The PM have been trained on Proposal Development, Programme management and implementation, Data collection Tools, Finance Management, harm Reduction, SIMS, OST, Advocay, Crisis management and other topics and trainings organized. Monthly CMIS is being prepared and sent ontime by the PM, as well as SOEs are being sent monthly to NSACS.

Although, having had vast experience and being trained and capacitated with skill and knowledge, the lack of supervision and proper moitoring was witness with the outreach team.

VIII b. Nurse/ ANM/ Counsellor: The ANM in the TI have recently joined in February 2016; she had left the post in 2014 due to her health problem and now rejoined again after a gap of 2 years, and is a graduate and have completed her Diploma in nursing;  the ANM have been trained for Counselling, Harm Reduction, Advocacy, referrals, STI management, Abscess management, OST. The nurse is efficient with ther roles and responsibiites and in dealing with the HRGs.

The project’s male counsellor, was earlier working as a counsellor and had to drop as an ORW due to slash of budget and the post; when the post was again alloted for a counsellor he was then promted from ORW to counsellor in September 2014. The counsellor have received trainings on various topics of harm reduction, counselling, STI management etc.

Record maintenance, updating of data and maintaining of registers at the Project clinic is being maintained by the ANM and the counsellor;

VIIIc.ORWs: Majority of the the ORWs are from the IDUs background and have been with the project for more than a year with an exception of one ORW, and are educated with a range of Class VIII above to BA Graduates; while the ORW for FSWs have been with the TI for 12 years now and have been promoted from PE to ORW and have been as an ORW for 5 years now. ORWs in the TI Project have been trained under NSACS, STRC, Learning site on various outreach and data collection tools, induction, orientation and Harm Reduction.

Their knowledge about the target population and on various indicators for their PEs, Hotspot analysis, outreach plan, importance of RMC, importance of ICTC testing and well as STI testing is clear but have not been able to reflect or implement in their outreach activities. Outreach Team needs to proper implement the Outreach Planning as well as properly plan their activities accordingly.

Field level activities and PEs support is visible at the TI Project, with a visit of 3 to 4 times a month.

VIIId. Peer Educators:Peer educators have been trained by STRC, Learning sites  and have also been oriented at inhouse level by the project.

With many of the PEs interacted, their knowldege on hotspot or site prioritization and on prioritization of HRGs is not very clear; while theimportance of ICTC and STI testing, condom demonstration skills and knowledge is clear.

Peer Educators knowledge and skills on report maintenance and documentation needs to be increased though capacity and trainings.

Peer educator, usually meet at the DIC every Friday for a weekly meeting.

VIII e. Accountant cum M&E: The Accountant cum M&E is a BA Graduate and have been working with the project since May 2010, and have been trained on Accounting Management, SIMS, and DCT. The books of accounts are being maintained by the account and are being kept accordinly with the visible supervision of the PM and PD. However, on the knowledge of the Data Collection tools and the SIMS reporting management the skill and knowledge of the accountant cum M&E is limited.

IX. a. Outreach activity in Core TI project: Outreach activities in the TI level is still an area of concerns that needs to be relooked upon by the TI staffs with  proper planning  and implementation to be followed accordingly. Although a lot of activities are being carried out by the Outreach team in an unplanned manner, which have also reflected in the service uptake for clinical services and ICTC refferals.

The Outreach activites are not being documented properly, nor is it being done as per the sitewise or hotspot with prioritization. The outreach team are doing these activities without prior objective and or planning but to and deliver the commodities and services  to the HRGs without proper understanding the need of behavoiur change. However through the outreach activities many of the HRGs have also been referred and are on OST programme or are linked for rehabilitation.

X. Services: Overall service uptake in the Project and quality of service and service delivery of (Free Condom, N/S and N/SE) is very well accepted and satisfied by the HRGs met during the FGD. Linkage for STI to the clinic and ICTC referrals to the Mobile and Static ICTC is  also prefferred by the HRG, however the need and demand of more referrals for OST programme via the project is sought for by the community members.

XI. Community involvement:The HRGs involvement in the TI Project for commodities have been since the beginning of TI project and active involvment of the community’s participation in the TI Project’s events, activiites, programmes and uptake of service delivery is still witness at various levels of the TI Project.However the communitiesinvolvement in the process ofplanning, monitoring or advocacy in the TI Project was not witness.

Motivation, empowerment and collectivization is another area that the TI Project needs to impart to the HRGs, so as to enable them to be involved in a larger extent at all levels of the programme.

XII. Commodities: Hotspot Planning, Condom Demand and Gap Analysis risk and vulnerability factors has not beenproperly accessed or implemented in the TI Project. However the demand and distribution of condoms and N/Scalculation method is being done as per demand of the HRGs on a day to day basis and as and when required by the HRGs.

XIII. Enabling environment:Non Systematic planing and involvement of the community in advocacy, networking and linkages is witness in TI Project, however these too have brought in some good results. The concept of Advocacy is understood by the TI Project and is being done accordingly on a need based.

The stakeholders met (Youth Leaders, members of the Mon Users Network) were able to speek openly and accpet the importance of N/S and Condoms. They also understood the need and importance of the prevention of HIV and AIDS and of staying safe and the affects of Drug use. They have also worked closely with the TI Project and have addressed issues relating to the issue of Drug use in their own settings.

Annexure C

Confidential:				Reporting Form C

EXECUTIVE SUMMARY OF THE EVALUATION

( Submitted to SACS for each TI evaluated with a copy to NACO)

Profileofthe evaluator(s):

| Nameofthe evaluators | Contact Details with phone no. |
| --- | --- |
| - Mr. Romeo Myrchiang – Team Leader, External Evaluator | Ch. No. 30, Rngi Jynriew, Near Iaikyntiew College, Upper Nongthymmai, Shillong – 793014, Meghalaya Email: rameses2605@gmail.com Contact: +91 9436101106 / 9862034762 |
| - Mr. Eliakim Sorhie – External Evaluator | Electrical Colony, House No. ECB-14 Kohima – 797001, Nagaland Email: eliakim_sorhie@yahoo.co.in Contact: +91 8575735801 |
| - Mr. Sanjay Paul – Finance Evaluator | Office: C/o. Ajit K. Jain & Associates, Circular Road, Dimapur, 797112 Nagaland Email: spaul936@gmail.com Contact: +91 9862762587 |
| Officials from SACS/TSU (as facilitator) | Ms. Abonuo Khatso NSACS Kohima – 797001, Nagaland Email: abonuoangami1@gmail.com Contact: +91 9436011474 |

| Nameofthe NGO: | Youth Action for Social Service (YASS) |
| --- | --- |
| Typology ofthe target population: | 5000 IDU, 150 FSW, 150 SPs |
| Total population being covered against target: | 5000 IDU, 150 FSW, 150 SPs |
| Dates of Visit: | 20th&21st February 2016 |
| Place of Visit: | Project Office (DIC) at Mon Town Field Visit for FGD: 2 Hotspot in Mon town (1 for IDUs and 1 for FSWs) |

OverallRating based programmedelivery score:

| TotalScore Obtained(in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 61%-80% | B | Good | [65.3 %] Recommended for continuation with specific recommendation for improvement. |

Specific Recommendations:

- All Project Staffs (PM, Nurse, Accountant, ORWs & PEs) must be provided with appointment letters along with their roles and responsibilites. - Project Director needs take active participation in the TI Project implementation and must ensure that PD is at least a minimun of 2 to 3 days during the month to provide support, Monitoring and mentoring the Project staffs. - Minutes of monthly / weekly / DIC meetings needs to be properly documented and maintained, along with names, designation and signature of the respected persons. - Regular meetings with HRGs for service delivery needs to be upscale and intensified at the DIC level. - Re Orientation on Data Collection and outreach tools for Outreach Team (ORWs & PE) - Outreach & Micro planning and activities needs to be introduced and intensified with prioritization of site wise and HRG wise. - Condom and Needle Syringes gap analysis needs to the implemented by the Project staff. - Risk and vulnerability assessment need to be updated and done periodically at the TI level. - Involvement of communities at all levels of the TI Project is a must and needs to be increased - Mentoring and monitoring process needs to be intensified by the PM and PD. - DIC management team, Collectivization and formation of support groups or SHGs needs to be implemented - Movement register of all the TI staff needs to be maintained and recorded accordingly. - Organization / Project must ensure that all the Documents, Data Collection Tools are being maintian, updated and systematicall / chronologically stored; including previous years documents at the Project Office. - All receipts and vouchers should be serialised and machine numbered. - All the expenditure must be according to the approved Budget with supporting documents. - Temporary Loan must be through bank transaction or A/c Payee, and the same returned via Bank Transaction, A/c Payee, and not by Cash. - Cash in hand should always be less than 5000. - Transaction for any amount above Rs 5000 should be done through cheque only. - TA must always have supporting voucher and must coordinate with the movement of the TI Staff, and also properly documented. - Books of account must be updated regularly. - BRS must be prepared month wise. - Expenditure for Every Budget head must have supporting documents and with proper supporting voucher. - Re allocation of Budget heads must be supported with proper authorization. - Budget heads suc as Crisis Response, Advocacy, Documentation etc. should not be supported by the bills for purchasing of foodstuffs. - More training is required for accounts and record maintenance. - The Use of Tally must be implemented and practices by the Accountant.