Nagaland State AIDS Control Society

Targeted Intervention- Evaluation Report

- 2016-

Shansham Organization

Typology: IDUs& FSWs

Naginimora, Mon District

Nagaland

Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eiliakim Sorhie – External Evaluator

- Mr. Sanjay Paul– Finance Evaluator

- Ms. Abonuo Khatso – NSACS Observer

Introduction

- Background ofProject and Organisation

# The “Shansham Organization” with its head office at Mon town, was formed by a group of likeminded youth to address the social issues in the district in the year 2000, and registered Societies Registration Act of 1860, State of Nagaland. The organization’s mission is “to work for and with the people and facilitate participatory approach in articulating the communities’ problem and development”. Its vision is to provide a platform for everyone’s participation towards enlightenment and social development. 

The organization has a large number of volunteers who participates in the organizations activities and various programmes. The organization is currently implementing 2 Targeted Intervention project under NSACS; One being in Mon town and the other at Naginimora, Mon district; and also runs a Rehabilitation centre for Drugs affected people.

# The Targeted Intervention project at Mon town is core composite for IDUs, FSWs and SPs and have been continuing this project for 15 years since the project inception in 2001.

- Name and address of the Organization: Shansham Organization, Post Box No.9, Mon - 798621 Nagaland

email:shansham_06@yahoo.co.in.

- Chief Functionary: Mr. L. Shakai Konyak (Secretary, Shansham Organization)

- Year of establishment: 2000

- Year and month of project initiation:2001[2001 – 2005 under a Mother NGO – Prodigals Home, and from 2006 onwards became independently implemented]

- Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eiliakim Sorhie– External Evaluator

- Mr. Sanjay Paul – Finance Evaluator

- Time frame:April 2014 – January 2016 [ 22 Months]

ProfileofTI

- Target Population Profile: Core Composite (IDU& FSWs)

- Typeof Project:  IDUs, & FSWs.

- Sizeof Target Group(s): 128 IDUs& 148 FSWs,[2014- 2015 – 2016] ;

- Target Area: Naginimora

I.Organizational support to theprogramme

The overall organizational support of “Shansham Organization” towards the TI project at Mon, is supportive and cooperative towards the IDU community as well as to the other target groups. The organization have also initiated as part of its initiative towards the community behavioural change by running / opening a rehabilitation center for the community which is being supported by the organization and the organization’s well wishers.  The organization is very much committed to the cause and issues faced by the IDU community.

The overall Board / Organization member’s involvement in any of the Project’s activities in the TI Project at Mon is limited to a few areas of implementation and levels in the TI Project. The TI Project’s activities is being managed and implemented by the PM, ANM, Counsellor, Accountant and Outreach Team based on their understanding and capacity, without the active involvement of the TI Project Director.

| Organization’s Board of Members |  |  |
| --- | --- | --- |
| Sl. No | Name | Designation |
| 1. | Mr.H. Penjun Konyak | Chairman. |
| 2. | Mr. L. Shahkai Konyak | Secretary. |
| 3. | Mr. Joseph Chipa Konyak | Programme Manager |
| 4. | Mr. Anok Bangpen Konyak | Member |
| 5. | Mr. Longna Konyak | Member |
| 6. | Miss. Lijao | Member |
| 7. | Miss. Manli | Member |
| 8. | Mr. Popa | Member |
| 9. | Mr. Manging | Member |

II.OrganizationalCapacity

- Human resources: The Staffing pattern in the TI Project have been implemented as per the NACO guidelines and as per the Project proposal and Budget approved by NSACS. PM, Accountant, ANM, Counsellor and ORWs. The project staffs have been provided with appointment letter without their roles and responsibilities in the TI project.; While a few of the staffs appointment have not been renewed on a yearly basis while a few of the projects personnel’s appointment was missing for some part of the project period.  However, the overall project staff were able to define with certain limitation on their roles and responsibilities within the TI project.

On the other hand the PEs appointments were not given individually but on the same and single appointment letter with extensions on a 6 months basis. The project staffs are cooperative and helpful towards each other.

- Capacity building: The TI staffs have been trained by State Training and Resource Centre, Identified Learning Site – Bethesda for various trainings of the project staff for the level of PM, ANM, ORWs, Accountant and PEs. Topics covered during the trainings were on Orientation, Induction and Refresher, Harm Reduction, Data Collection Tools, Finance Management, SIMS, Refresher, Counselling & STI Counselling.

In house training for the outreach team have not been conducted by the organization.

- Infrastructure of the organization: The Project Office is equipped with a 3 roomed infrastructure which includes STI Clinic, Counselling room, separate rooms for the Drop in Centre both the community, PM& Accountant room and ORWs room. The office location is suited in the central part of the town and is not easily accessible by the community for their needs and accessibility to services provided by the TI Project.

4. Documentation and Reporting: The TI project staff’s are maintaining documents which are not as per the procedures or NACO Guidelines; although the project is maintaining documents to a certain limitation without proper verification and monitoring. Adherence to SACS protocol has not been witness by the project or the organization; feedbacks and suggestions by NSACS officials have not been followed or carried out properly by the TI project.

Data collection tools formats: Form B& B_1, have been maintained by the project; while Form A, Form C, and Form D of the Data Collection Tools were not maintained and were not documented properly by the project, and information was also written in pencil. Proper authentication and cross verification of the Peer Educators Dairy and reports received from the field could not be verified.

The Overall project planning, outreach as well as micro planning is not properly implemented or followed by the Outreach team to track HRGs for services provided by the Project such as ICTC Testing, STI Testing, Syphilis Testing etc.. Planning is being done by the PM alone and distributes targets to the Outreach team for their coverage with the Outreach team’s participation in the planning.

Performance review mechanism is not witnessed in the project. TI needs to introduce intensive and regular follow up mechanism, ORWs monitoring and supportive supervision systems is not in place. Organizations internal project monitoring and supervision system needs to be strengthened to review regular project performance by the Project Director and Program Manager.

CMIS and SOEs are being sent to NSACS on a regular and monthly manner.

II. Program Deliverables

Outreach

- Line listing of the HRG by category: Site wise Line Listing and registration of all the HRG have been done and completed as per the Project proposal and as per the Targeted Project population coverage (ie. a target of 128 IDUs &148 FSWs and 60 SPs). The active HRGs are being covered and reached out with services provided by the project, such as Needle & Syringes and Condoms, ICTC referrals, STI treatment etc.

- Micro planning in place and the same is reflected in Quality and documentation: Planning has not been introduced by the TI project for service delivery ( N/S and condoms) which is being done by the outreach team; the use and implementation of micro plan is not reflected in the activities and documents of the PE &ORWs for tracking individual HRGs. Risk assessment and prioritization of HRGs have not been compiled or identified by the Project.

- Coverage of target population (sub-group wise):As per the Targeted population of 128 IDUs, 148 FSWs [2014-2014-2015], less than 80% of targeted population are being provided with services by the TI project on a regular basis or as and when needed by the HRGs.

4.  Outreach planning: Quality of Outreach planning and its implementation as well as documentation is not properly implemented by the TI Project. Activities and tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization and proper planning. Planning is being done by the PM alone without proper and active participation of the outreach team; targets and achievements are being given and provided to the Outreach team for their monthly coverage.

Activities such as FGD, Hotspot Level meeting, Field Visits, Clinical services and other services provided by the TI Project are being done in an unplanned and unsystematic way.

5.   PE: HRG Ratio: The TI Project have a total of 5 PEs for IDUs and 3 PEs for FSWs who are looking after the project sites under the TI Project.

6. Regular contacts: Regular contact [ie 2 times / per month for the FSWs as per NACO guidelines] of the HRGs is being maintained by the Outreach staffs (PEs); and regular contacts for IDUs are also being maintained by the PEswho are providing N/S and Condoms to the HRGs which is >70% out of the active HRGs for FSWs; and <70% out of the active HRGs for IDUs.

PEs are not being able to categorized or prioritized the HRGs under them and have not been able to educated the HRGs on the Risk and Vulnerabilities of their behaviour, Harm Reduction, Overdose etc. Linkages for clinical services and ICTC referrals or follow ups is being coordinated with the TI clinical ANM.

7. Documentation of the peer education: Peer Educator document’s which is the backbone of the TI Project are not being maintained as per NACO’s data collection tool. However, the level of understanding of the PEs in terms of risk assessment, vulnerability and prioritization of the HRGs is still lacking among the Peer Educators. Also, the flow of distribution of commodities remains to be constant throughout the project period, which is reflected in the “Form B, B_1 – PE Weekly Planning and Activity Sheet”, which is not properly authenticated or verified by the ORWs with the Peer’s dairy.

PEs also maintains their own PE dairies, for their distribution of Commodities towards their respective clients. However little information was available as the PEs dairy were not properly maintained and also the old dairies of the PEs were not maintained at the TI Project Office or were missing.

7. Quality of peer education: Interacting with the Peer Educators who came to the Project office during the Evaluation, their quality of knowledge and communication skills is not very clear to address the issues of HIV and AIDS, STI, Risk Behaviour, Harm Reduction, drugs related issues and other related basic issues was being witnessed;

The Peer Educators selected from respective areas are not from the community background;

Peer Educator’s skill and capacity needs to be enhance and capacitated with regular and effective orientation at the TI Project level, with proper assessment, mentoring and monitoring.

8. Supervision: The overall supervision and monitoring of TI Project by the PM is not witnessed in the Project. Documents as per the NACO guidelines are not being maintained or verified by the PM or PD of the project.

IV. Services

- Availability of STI services: The TI Project have a STI clinic managed by the ANM; The clinic have supply of STI drugs and testing kits which is being supplied by NSACS and also purchased by the TI project as per the norms; The TI is linked to the Static ICTC and STI Clinic as well as the Mobile ICTC unit; Follow up mechanism is also in place which is reflected in the number of referrals for HIV and Syphilis testing.

2. Quality of the services: The TI’s STI clinic cum Counselling room have little privacy and is being maintained and managed by the ANM. Clinical equipments are available in the STI Clinic, with supply of medicines. The TI is also linked to a Government Clinic as well as Mobile Clinic, where tests and linkages for syndromic cases are being treated.

3.  Quality of treatment in the service provisioning: The STI clinic have provided services and treatment to the HRGs with STI treatment, Abscess management, Counselling and linkages for ICTC testing; with 529 episodes of STI Counselling for IDUs and 503 episodes for FSW, 529 episodes of counselling for IDUs and 503  FSW;

4.  Documentation: The TI Clinic as well as Counsellor is maintaining registers related to services delivery maintained by the ANM which includes Network Clinic Register, Clinic Daily Summary Sheet, Medicine Stock Register, Referral Slips, Counselling Register, and RMC Register. The system of procurement of medicines is not witness in the project; also the mentioned documents could not be verified, and the Doctor signature and seal is also not endorsed; and as per the information received the project is without a doctor since April 2014 till date.

The Needle Syringes and Condom stock and distribution registers are jointly maintained by the ORWs, ANM and PM.

5.  Availability of Condoms & Needle Syringes: The TI project is distributing free condoms which are being acquired from NSACS. Social marketing of condoms have been initiated, which is being done on a need based. The TI is maintaining stock in hand, while buffer stock for 3 months is not being maintained at the TI Project level.

The distribution of free N/S is being purchased by the TI project and is being purchased without proper planning or assessment for 3 months buffer stock; N/S are being purchased at an interval of one month to 3 months gaps. The Needle Syringes and condoms are being distributed by the PEs and ORWs in the field level, while at the DIC level it is by the ANM.

Condom and N/S demand and gap analysis have not been done / implemented at the TI Project level.

6.   No. Of Condoms distributed: A total of 96,842 (52187 for IDUS + 44655 for FSWs) numbers of free condoms were distributed through the Outreach Team, ANM and Counsellor during the period of April 2014 to January 2016; while promotion of Social Marketing of Condoms was done on a need based with no proper documentation.

7.  No. of  Needles /Syringes Distributed: A total of 37,723 number of free Needle /Syringes were distributed during the period of April 2014 to January 2016 through the Outreach Workers, Peer Educators, ANM with a returned of 30,287number of Needle Syringes through the NSE programme which is 80%.

Waste Disposal Management is in place and disinfection of Needle / Syringes is being performed in the DIC or Project Office by the ANM and ORWs with the support of Outreach Worker; while the final disposal is being done at the PHC.

8. Information on linkages for ICTC, DOT, ART, STI clinics: Linkages for STI testing and syndromic cases withthe Government Clinic, ICTC, mobile ICTChas been effective with 27% IDUs and 18% FSWs having undergone Syphilis testing; and 84% IDUs and 55% FSWs having undergone HIV testing.

RNTCP awareness among the HRGs have not been done by the TI Project; however it may also be noted that no cases were detected for TB during the Project period.

9. Referrals and follow up: Referral mechanism is being maintained by the TI and follow up mechanism has also been maintained and followed up by the ANM.

V. Community participation

- Collectivization activities: Collectivization or formation of groups has not been initiated by the TI Project during the project year.

2. Community participation in project activities: The overall community participation in the Project is negligible with none of the Outreach team belonging to the community. The overall communities participation in the project is low with little support and involvement of the HRGs at various level of the project activities, such as FGD, DIC level visits, events etc.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc: The TI Project have established links with Static ICTC, Mobile ICTC, and STI clinic.

- Percentages of HRGs tested in ICTC: 84% IDUs and  55% FSWs of the registered / active HRGs have undergone HIV testing during the project period [ April 2014 – January 2016]

- Support system: The TI Project have support system only on clinical service delivery with the ICTC, Mobile ICTC and STI centre;  The TI have not been able to developed rapport with different stakeholders as well as  advocate with stakeholder for the need of the project. However the stakeholders met, only reported of how the project have help the IDUs in decreasing their risk and vulnerability of HIV infection.

VII. Financial systems and procedures

- Systems of planning: The organization/management is allowing the Project Office  to prepare the books of accounts every months as per the budget allotment and budgeted heads provided by NSACS, without planning (either quarterly or yearly). Expenses are being made randomly without proper or system of planning.

The TI have spend almost the whole amount of funds released from NSACS.

- Systems of payments: Generally all the non salary payments are being made by cash. Most of the major payments (commodities like needle syringes, abscess prevention, office expenses etc) community based activities are being paid by cash with un authentic bills / cash memos, invoice were attached with improper or without the approval of the competent authority.

There is no approval systems by the Project Director or signatories. Most of the program expenses related are made by Cash and in some cases bills / cash memos were not authentic.

The TI has taken loan during the year through cash and payment is also being made through cash and cheque without proper verification or authenticity. Both Stock and assets registers are in place and updated; assets were not properly codified.

3.  Systems of procurement: There is no system for collecting any quotations before purchasing of bulk commodities (Needle & Syringes, Syphilis Testing Kit, Abscess prevention etc).  Stock & issue registers is being maintained with a few cases of non tallying. There is no systems for quality checking of the product purchased.

- Systems of documentation: The project is maintaining separate books of accounts for separate project year 2014-2015-2016, such as Cash Book, Ledger, Separate bank pass book, salary register, attendance register, asset register, loan document, SOEs, auditor’s report etc. BRS is not being prepared or maintained by the organization.  However record keeping of payment vouchers, bill and cash memos have not been systematized or kept in orderly manner. No minutes of financial planning or documents of approval for expenditure was available.

VIII. Competency of the project staff

VIII a. Program Manager: The Program Manager, have been working with the TI project since 2009 and have been trained on Proposal Development, Programme management and implementation, Data collection Tools, Finance Management, harm Reduction, SIMS, OST, Advocacy, Crisis management and other topics and trainings organized. Monthly CMIS is being prepared and sent on time by the PM, as well as SOEs are being sent monthly to NSACS.

Although, having had vast experience and being trained and capacitated with skill and knowledge, the lack of supervision and proper monitoring was witness with the outreach team. PM lack proactive participation in implementing and taking responsibilities of the TI project.

VIII b. ANM/ ANM/ Counsellor: The ANM in the TI have been working with the project since April 2010, and have completed her Diploma in nursing;  the ANM have been trained for Counselling, Harm Reduction, Advocacy, referrals, STI management, Abscess management, OST. The ANM is efficient with the roles and responsibilities and in dealing with the HRGs.

Record maintenance, updating of data and maintaining of registers at the Project clinic is being maintained by the ANM;

VIIIc. ORWs: The ORW for the FSWs has been working with the project since October 2013 while the ORW for IDUs have joined only in November 2015. ORW for have been trained under STRC, Learning site on various outreach and data collection tools, induction, orientation and Harm Reduction while the ORW for IDU have never received any training nor have he received any in house orientation.

Their knowledge about the target population and on various indicators for their PEs, Hotspot analysis, outreach plan, importance of RMC, importance of ICTC testing and well as STI testing is not clear and are not reflect or implement in their outreach activities.

Field level activities and PEs support is visible at the TI Project, with a visit of once to twice a month by the ORW for FSWs while the ORW for IDU have never been to the field.

VIIId. Peer Educators: Peer educators have been trained by the Learning site.

With many of the PEs interacted, their knowledge on hotspot or site prioritization and on prioritization of HRGs is not very clear; while the importance of ICTC and STI testing, condom demonstration skills and knowledge is clear.

Peer Educators knowledge and skills on report maintenance and documentation needs to be increased though capacity building and trainings.

Peer educator, usually meet at the DIC every Friday and Saturday for a weekly meeting and reporting.

VIII e. Accountant cum M&E: The accountant cum M&E have been working with the project since September 2011, and have been trained on Accounting Management, SIMS, and DCT. The books of accounts are being maintained by the account and are being kept accordingly to the capacity of the Accountant. However, on the knowledge of the Data Collection tools and the SIMS reporting management the skill and knowledge of the accountant cum M&E is limited, and his book keeping knowledge and capacity is limited.

IX. a. Outreach activity in Core TI project: Outreach activities in the TI level is still an area of concerns that needs to be relooked upon by the TI staffs with  proper planning  and implementation to be followed accordingly.

The Outreach activities are not being documented properly, nor is it being done as per the site wise or hotspot with prioritization. The outreach team are doing these activities without prior objective and or planning but to deliver the commodities and services  to the HRGs without proper understanding the need of behaviour change.

X. Services: Overall service uptake in the Project and quality of service and service delivery of (Free Condom, N/S and N/SE) is very well accepted and satisfied by the HRGs met during the FGD. Linkage for STI to the clinic and ICTC referrals to the Mobile and Static ICTC is  also preferred by the HRG.

XI. Community involvement: The HRGs involvement in the TI Project for commodities have been since the beginning of TI project , while involvement of the community’s participation in the TI Project’s events, activities, programmes and uptake of service delivery not witness.

XII. Commodities: Hotspot Planning, Condom Demand and Gap Analysis risk and vulnerability factors has not been properly accessed or implemented in the TI Project. However the demand and distribution of condoms and N/S calculation method is being done as per demand of the HRGs on a day to day basis and as and when required by the HRGs.

XIII. Enabling environment: The project have not been able to create a rapport with the other stakeholders in the area and advocacy and linkages are being done without plan or on a need based.

The stakeholders met (Youth Leaders,) were able to speak openly and accept the importance of N/S and how it have help many of the youth in the area and preventing the spread of HIV and AIDS.

Annexure C

Confidential:				Reporting Form C

EXECUTIVE SUMMARY OF THE EVALUATION

( Submitted to SACS for each TI evaluated with a copy to NACO)

Profileofthe evaluator(s):

| Nameofthe evaluators | Contact Details with phoneno. |
| --- | --- |
| - Mr. Romeo Myrchiang – Team Leader, | Ch. No. 30, Rngi Jynriew, Near Iaikyntiew College, Upper Nongthymmai, Shillong – 793014, Meghalaya Email: rameses2605@gmail.com Contact: +91 9436101106 / 9862034762 |
| - Mr. Eliakim Sorhie – External Evaluator | Electrical Colony, House No. ECB-14 Kohima – 797001, Nagaland Email: eliakim_sorhie@yahoo.co.in Contact: +91 8575735801 |
| - Mr. Sanjay Paul – Finance Evaluator | Office: C/o. Ajit K. Jain & Associates, Circular Road, Dimapur, 797112 Nagaland Email: spaul936@gmail.com Contact: +91 9862762587 |
| Officials from SACS/TSU (as facilitator) | Ms. Abonuo Khatso NSACS Kohima – 797001, Nagaland Email: abonuoangami1@gmail.com Contact: +91 9436011474 |

| Name of the NGO: | Shansham Organization _ Naginimora |
| --- | --- |
| Typology ofthe target population: | IDU & FSWs |
| Total population being covered against target: | 128 IDU against 128 IDUs; & 148 FSWs against 148 FSWs |
| Dates of Visit: | 24th & 25th February 2016 |
| Place of Visit: | Project Office (DIC) at Naginimora Field Visit for FGD: 2 Project Sites ( 1 for IDUs and 1 for FSWs). |

Overall Rating based programme delivery score:

| TotalScore Obtained(in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 41%-60% | C | Average | [42 %] Recommended for continuation with specific recommendation. |

Specific Recommendations:

- Change of Organization in leading and implementing the TI Project, with the appointment of a different PD and PM while retain the same project staffs. - All Project Staffs (PM, ANM, Accountant, ORWs & PEs) must be provided with appointment letters along with their roles and responsibilites which must be explained. - Project Director needs take active participation in the TI Project implementation and must ensure that the PD is in TI Project site at least a minimun of 2 to 3 days during the month to provide support, Monitoring and mentoring the Project staffs. - Minutes of monthly / weekly / DIC meetings needs to be properly documented and maintained, along with names, designation and signature of the respected persons. - Regular meetings with HRGs for service delivery needs to be upscale and intensified at the DIC level. - Re Orientation on Data Collection and outreach tools for Outreach Team (ORWs & PE), and authentication of data with the PE Dairy that is being used in the field. - Outreach & Micro planning and activities needs to be introduced and intensified with prioritization of site wise and HRG wise. - Condom andNeedle Syringes gap analysis needs to the implemented by the Project staff. - Risk and vulnerability assessment need to be updated and done periodically at the TI level. - Involvement of communities at all levels of the TI Project is a must and needs to be increased - Motivation and collectivization of HRG needs to be implemented and followed up at the TI Level - Movement register of all the TI staff needs to be maintained and recorded accordingly. - Organization / Project must ensure that all the Documents, Data Collection Tools are being maintian, updated and systematicall / chronologically stored; including previous years documents at the Project Office. - Bank Account must be at the area where the project is implemented, ie. - All the expenditure must be according to the approved Budget with supporting documents, and approve by PD. - Temporary Loan must be through bank transaction or A/c Payee, and the same returned via Bank Transaction, A/c Payee, and not by Cash. - Cash in hand should always be less than 5000. - Transaction for any amount above Rs 5000 should be done through cheque only. - TA must always have supporting voucher and must coordinate with the movement of the TI Staff, and also properly documented. - Books of account must be updated regularly. - BRS must be prepared month wise. - Expenditure for Every Budget head must have supporting documents and with proper supporting voucher. - Budget relocation of any budget heads must be with supporting approval from SACS or competant authority. - Regarding the payment of Honr. to Doctor, the same should be made by cheque only . In case of cash payment the acknowledgement should be in written by the particular doctor on his/her own commercial pad. - More training is required for accounts and record maintenance. - The Use of Tally must be implemented and practices by the Accountant.