# Nagaland State AIDS Control Society

Targeted Intervention- Evaluation Report

- 2016-

# Turning Point Organization (TPO)

Typology: IDUs

# Tizit, Mon District

Nagaland

Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eliakim Sorhie– External Evaluator

- Mr.Sanjay Paul– Finance Evaluator

- Ms. Abonuo Khatso – NSACS Observer

# Introduction

- Background of Project and Organisation

Turning Point Organization (TPO),with its headquarter at Mon Town, is a non governmental organization, registerd under the Society Act under the state of Nagaland and formed for the sole purpose of uplifting the lives of the rural population. The organization have been actively engaged in social development at the community level and on voluntary service. The organization have been atively involved in working on the issue of HIV and AIDS on the preventive aspects of transmission from parents to child, youth promotaional training progammes in skill upgradation and vocational trainings and other areas of promoting the socio economic upliftment of the community.

The organization is implementing TI project under NSACS at  Tizit, Mon District for IDUs and SPs, since 2009, and is in its 7th year of implementation.

- Name and address of the Organization: Turning Point Organization,P.O Box 22, Mon,– 789621, Nagaland

# Contact:+03869-251009/9436409612/8974976310

email:tpomon@yahoo.com , Chongying-konyak@yahoo.co.in

- Chief Functionary:Mr. Chongying Yinlunghu

- Year of establishment: 2000

- Year and month of project initiation:2009

- Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eliakim Sorhie– External Evaluator

- Mr. Sanjay Paul – Finance Evaluator

- Time frame: April 2014 – January 2016 [ 22 Months]

# Profile of TI

- Target Population Profile: IDU

- Typeof Project:  IDU

- Sizeof Target Group(s): 280 IDUs &160SPs [2014- 2015] ; 280 IDUs &170 SPs [2015 – 2016]

- Target Area:Tizit, Mon District

IDU SITES: Forest Colony, Medical, Monlam, Pantom, Industry, ADC, Pongma, Police, Shnaglam, Tingtan, Namsa Gate, Nangtan, Lapa, Shoalam Colony, Hongshai, Apnavally, Tekang, Ngaland Factory.

# I. Organizational support to the programme

The overall organizational support of “Turning Point Organization” towards the TI Project in Tizit, is supportive and cooperative towards the IDU community.  The organziation’s chief functionary and Project Director is very much commited and active to the cause and issues faced by the IDU community in the area.

However much commited to the cause of the target popualation, at the organization level, the Project Director is the only one involve with the TI Project. The Board / Organization members involvement in any of the the Project’s activities in the TI Project at Tizit is not visible in the Project. The TI Project’s activites is being managed and implemented by the PM, ANM, Accountant and Outreach Team based on their understanding and capacity, with little supervision or monitoring of the TI Project Director.

# II. Organizational Capacity

- Human resources: The Staffing pattern in the TI Project have been implemented as per the NACO guidelines and as per the Project proposal and Budget approved by NSACS. PM, Accountant, ANM and ORWs have been provided with appointment letter along with their roles and responsibilities of the organization as per the organization’s guidelines and also available in the project level; However, it is noticed that  a few of the project staff could not properly define their roles and responsibilities within the TI project.

PEs were also given appointment on a probation basis and on 3 months basis. The project staffs are cooperative and helpful towards each other, especially the  PEs and ORWs.

| Sl. No | Name | Designation | Date of Appointment. |
| --- | --- | --- | --- |
| 1. | Mr. Chongying Yinlunghu | Project Director |  |
| 2. | Mr. Wangyuh Konyak | Programme Manager | March 2015 |
| 3. | Mr. Sanjoy Singha | Accountant | 2009 |
| 4. | A.Angam | ANM | March 2015 |
| 5. | Mr. Nyempha Konyak | ORW -IDU | 2nd May 2014 |
| 6. | Mr. Ompha Konyak | ORW -IDU | 2010 |
| 7. | Mongyeang | ORW - FSW | March 2010 |
| 8. | Panglam | PE | 1st sep 2012 |
| 9. | A.Achak | PE | 15 feb 2015 |
| 10. | Pulei | PE | 10th july 2011 |
| 11. | Mongngam | PE | 4th july 2010 |
| 12. | Nokpoh | PE | 2nd sep 2012 |
| 13. | Senpha | PE | 16/feb/2016 |
| 14. | Amo | PE | 15/feb/2016 |
| 15. | Manto/Nokthak | PE | 3/5/2014 |
| 16. | Awang | PE | May 2014 |

- Capacity building:The TI staffs have been trained by NSACS, State Training and Resource Centre,Identified Learning Sites;  covering topics on Induction, Orientation, Harm Reduction, Data Collection Tools, Finance Management, Clinical management, SIMS, Refresher, Counselling, Outreach Trainings.

The various trainings organized have been attended by the PM, ANM, Accountant, Outreach Workers and Peed Educators accordingly. In house training by the TI Project have not been conducted by the Project.

- Infrastructure of the organization: The Project Office is equipped with a 3 roomed infrastructure which includes STI Clinic cum Counselling room, separate rooms for the Drop in Centrecum ORWs room, PM& Accountant room. The office locationis suitedadjacent to the main road and is easily accessible by the community for their needs and accessibilty to services provided by the TI Project.

4. Documentation and Reporting:The TI project staff’s are maintaining documents and procedures as per the NACO Guidelines to a certain limitation without proper checking and monitoring. Adherance to SACS protocol is being witness to a certain limitation; however feedbacks and suggestions by NSACS officials have not been followed or carried out properly by the TI project. The Project team mets every Monday of the week for reviews and reporting.

Data collection tools formatsForm A, Form B_1, Form C, and Form D of the Data Collection Tools, needs to be updated and properly maintained. Form B_1 needs proper authentication and verifcation by the ORWs in relation and comparing with the PE daily.

The Overall project planning, outreach as well as micro planning is not properly implemented or followed by the Outreach team to track HRGs for services provided by the Project such as ICTC Testing, STI Testing, Syphilis Testing etc..  Clinical service records and documents are being maintained the ANM.

TI project have introduce regular follow up mechanism, ORWs monitoring and supportive supervision systems iswitness and is being followed up by the PM.

CMIS and SOEs are being sent to NSACS on a regular manner indicating the monthly project performance

# II.ProgramDeliverables

# Outreach

- Line listing of the HRG by category: Site wise Line Listing and registration of all the HRG have been done and completed as per the Project proposal and as per the Targeted Project population coverage (ie. a target of 280 IDUs). The active HRGs are being covered and reached out with services provided by the project, such as Needle & Syringes and Condoms, ICTC referrals, STI treatment etc.

- Micro planningin placeand the same is reflected in Quality and documentation: Planning has been introduced by the TI project for service delivery ( N/S and condoms) which is being done by the outreach team; however the use and implementaton of proper micro plan is not reflected in the activities and documents of the PE &ORWs. Risk assessment and prioritization of HRGs have also not been done by the Outreach Team. Proper implementation and use of Micro Planning by the Outreach team needs improvement for outreach activities and service deliveries. Linkages between the Outreach team and the ANM for clinical services and follow up mechanism needs strengthening. The Outreach Team (ORWs &PEs) from time to time would requires orientation / re orientation on the data collection rolled out by the NACO as well as other related issues.

- Coverage of target population(sub-groupwise):As per the Targeted population of 280IDUS [2014-2015-2016], more than 80% of targeted population are being provided with services by the TI project on a regular basis or as and when needed by the HRGs.

4.  Outreach planning: Quality of Outreach planning and its implementation as well as documentation of the same is maintained andimplementedby the TI Project.Activities and tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization and proper planning.

Planning for outreach activities and other service delivery by the outreach team needs to be prioritized and implemented on a regular basis or montly basis.

Activities such as FGD, Hotspot Level meeting, Field Visits and other services provided by the TI Project are being done as per the project montly planed; however documentation of the same have not been documented properly.

5.   PE: HRG Ratio:The TI Project have a total of 10 PEs for IDUs looking after 19 Hotspot / sites under the TI Project.

6. Regular contacts:Regular contact of the HRGs is being maintained by the PEswho are providing N/S and Condoms to the HRGs which is <80% out of the active HRGs.

However, PEs are not being able to categorized or prioritized the HRGs under them but have been able to to make aware the HRGs on the Risk and Vulnerabilities of their behaviour, Harm Reduction, Abscess prevention etc. Linkages for clinical services and ICTC referrals or follow ups is being coordinated with the TI clinical ANM.

7. Documentation of the peer education: Peer Educator document’s which is the backbone of the TI Project are being maintained as per NACO’s data collection tool. However, the level of understanding of the PEs in terms of risk assessment, vulnerability and prioritization of the HRGs is still lacking among the Peer Educators. Also, the flow of distribution of commodities remains to be constant throughout the project period, which is reflected in the “Form B_1 – PE Weekly Planning and Activity Sheet”, which is mostly filled up during the weekly meetings, needs to be authenticated with the Peer Dairy.

PEs also maintains their own PE dairies, for their distribution of Commodities for their respective clients at the field level. However little information was available as the PEs dairy were not properly maintained and also the old dairies of the PEs were not maintained at the TI Project Office.

8.Quality of peer education: Interacting with the Peer Educators who came to the Project office during the Evaluation, their quality on peer education, knowledge and communication skills is not very clear to address the issues of STI, Risk Behaviour, Harm Reduction, Drugs related harmsand other related basic issues was being witnessed;

The Peer Educators are selected from respective areas and someare from the community background; there is a need to make Peer Educators aware of the objectives, goal and planning process towards risk behaviour among the target population.

Peer Educator’s skill and capacity needs to be enhance and capacitated with regular and effective orientation at the TI Project level, with proper accessment, mentoring and monitoring.

9. Supervision:The overall supervision and monitoring of TI Project is overlooked by the PM and which is being supported by the ANMand ORWs which is witnessed in the Project. Although documents on follow up are being maintained, proactive measure and assistance needs to be taken up to further enhance the outreachactivities by the Outreach Team for proper follow up on Risk Behaviour and reduction Counselling, ICTC, STI referrals and other services as well as behavioural change.  Organizational supervision needs to be strengthen by the Project Director who only visit the TI monthly.

# IV. Services

- Availability of STI services: The TI Project have a STI clinic managed by the ANM and is linked to one visiting Doctor, who is available on call; The clinic have adequate and supply of STI drugs and testing kits which is being supplied by NSACS and also purchased by the TI project as per the norms; The TI is linked to the ICTC and STI Clinic; Follow up mechanism is also in place which is reflecting in the number of referrals for HIV and Syphilis testing.

2. Quality of the services: The TI’s STI clinic is attached with the Counselling room which have limited privacy and is being maintained by the ANM. Clinical equipments are available in the STI Clinic, with adequate supply of medicines. The TI is also linked to a Government Clinic, where tests and linkages for syndromic cases are being treated, while abscess cases are being treated by the ANM and the Project clinic or field level.

3.  Quality of treatment in the service provisioning: The STI clinic have provided services and treatment to the HRGs with STI treatment, Abscess management, Counselling and linkages for ICTC testing; with 19 episodes of STI Counselling, and 1058 episodes of counselling;

4.  Documentation: The TI Clinic is maintaining registers related to services delivery maintained by the ANM which includes Network Clinic Register, Clinic Daily Summary Sheet, Medicine Stock Register, Referral Slips, Counselling Register, and RMC Register.The system of procurement of medicines is not witness in the project.

The Needle Syringes and Condom stock and distribution registers is maintained by the ORWs.

5.  Availability of Condoms and Needle and Syringes: The TI project is distributing free condomswhich are being acquired from SACS. Social marketing of condoms have been initiated, which is being done on a need based. The TI is maintaining stock in hand, while buffer stock for 3 months is not being maintained at the TI Project level. While needle and syringes are being purchased as per the budget allocated and on a montly or bi monthly basis, however buffer stock for 3 months are not being maintained by the project. The Needle Syringes and condoms are being distributed by the PEs and ORWs in the field level, while at the DIC level it is through the ANM.

Condom and N/S demand and gap analysis have not been done / implemented at the TI Project level.

6.   No. Of Condoms distributed: A total of 55,655 numbers of free condoms were distributed through the Outreach Team and ANM; during the period of April 2014 to January 2016;

7.  No. of  Needles /Syringes Distributed:A total of 63,243 number of free Needle /Syringes were distributed during the period of April 2014 to January 2016 through the Outreach Workers, Peer Educators, ANM and DIC with a returned of 40,732 number of Needle Syringes through the NSE programme which is 64%.

Waste Disposal Management is in place and disinfection of Needle / Syringes is being performed in the DIC or Project Office by the ANM with the support of Outreach Worker; while the final disposal is being done at the PHC, Tizit.

8. Information on linkages forICTC, DOT, ART, STI clinics:Linkages for STI testing and syndromic cases withthe Government Clinic, ICTC, mobile ICTChas been effective with 47% HRGs having undergone Syphilis testing; and 94% HRGshaving undergone HIV testing.

RNTCP referrals and awareness among the HRGs have not been detected by the TI Project, or detection HIV+ cases.

9. Referrals and followsup: Referral mechanism is being maintained by the TI and follow up mechanism has also been maintained and followed up by the ANM.

V. Community participation

- Collectivization activities: Collectivization or formation of groups has not been initiated by the TI Project.

2. Community participation in project activities: The overall community participation in the Project is lowwith limited of 2 PE being from the community background, they have not been able to involve the IDU community at large in various activities and events of the TI Project.Although the communities are taking part in the FGDs at the field level.

The organization, must relook and reflect on their program intervention and implementation to capacitate and mobilisethe IDU community for greater involvement and sustainability of the project. This must also be followed with proper documentation and reports.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc : The TI Project have established links with ICTC, Mobile ICTC, and STI clinic.

- Percentages of HRGs tested in ICTC: 94% of the registered / active HRGs have undergone HIV testing during the project period [ April 2014 – January 2016]

- Support system: The TI Project have support system only on clincal service delivery with the ICTC, Static government clinic, Mobile ICTC and STI centre;  The TI have developed a good rapport with different stakeholders and advocacy along with sensitization to the stakeholder is being done from time to time. The stakeholders have also reported of being invovled with the TI project at various levels;

VII. Financial systems and procedures

- Systems of planning:The organization/management is allowing the Project Office  to prepare the books of accounts every months as per the budget allotment and schedule provided by NSACS, without planning (either quarterly or yearly) which should have been based on activity wise as well as release of funds. Expenses are being made randomly without proper or system of planning.

The TI have spend almost the whole amount of funds released from NSACS. The Project also does not have any approval system endorsed by the NGO or management before incurring any expenses or expenditure.

2.  Systems of payments:Generally all the non salary payments, are being made by cash.  The Project is maintaining printed vouchres which are machine numbered and common name of the organization, but are being countersigned by the Accountant, PM and PD of the project, who approves the expenses. Most of the all the expenses are related with puchasing of foodstuffs or stationaries and supported by hand written /kachcha bills.

The TI has taken huge amount of loan during the year through cash and payment is also being made through cash and partly by cheque. Both Stock and assets registers are in place and updated; assets were not properly codified.

3.  Systems of procurement: There is no system for collecting any quatations before purchasing in bulk.  Stock & issue registers is being maintained but not tallied properly. There is no systems for quality checking of the product purchased.

- Systems of documentation: The system of documentation of accounting procedures by the project are maintaining of Cash Books, Ledger, Salary Register, Bank Book, Receipts and Payment Vouhcers, Stock register, attendance and leave register etc. BRS is not being prepard or maintained by the organization;Financial Audit Reports, SOEs are also maintained.

No minutes of financial planning or documents of approval for expenditure was available. Movement registers for Outreah Staff for payment of TA is not being maintained properly.

VIII. Competency of the project staff

VIII a. Program Manager: The Program Manager is a BA Graduate, have been working with the TI project since March 2015; The PM have been trained on Programme management and implementation, Data collection Tools, harm Reduction. Monthly CMIS is being prepared and sent ontime by the PM, as well as SOEs are being sent monthly to NSACS.

Although, being trained and capacitated with skill and knowledge, due to lack of supervision and mentoring the PM lacks in the performance and upscalling the TI Project. The PM will need more skills and trainings on project implemenation, outreach etc and aclose monitoring and supervision by the PD as well as SACS.

VIII b. ANM:The ANM have compelted her Diploma in Nursing and have been working in the project since March 2015 and have been trained been trained for Counselling, Harm Reduction and STI management. The ANM is efficient with ther roles and responsibiites and in dealing with the HRGs.

Record maintenance, updating of data and maintaining of registers at the Project clinic is being maintained by the ANM; Due to lack of supervision and monitoring from the Organizational and also at the NSACS level, the ANM’s capacity and performace could not be nurtured towards uplifting the projects services delivery.

VIIIc.ORW: The proejct’s ORWs have been with the project since 2010; ORWs in the TI Project have been trained under NSACS and STRC, Orchid on various outreach and data collection tools and Harm Reduction.

Their knowledge about the target population and on various indicators for their PEs, Hotspot analysis, outreach plan, importance of RMC, importance of ICTC testing and well as STI testing is clear, however this is not reflected in their outreach activities due to lack of proper monitoring and supervision. Outreach Team needs to proper implement the Outreach Planning as well as properly plan their activities accordingly.

Field level activities and PEs support is visible at the TI Project, with a visit of 4times a month;.

VIIId. Peer Educators:Peer educators have been trained by the learning sites  and have also been oriented at inhouse level by the project.

With many of the PEs interacted, their knowldege on hotspot or site prioritization and on prioritization of HRGs is not very clear; while theimportance of ICTC and STI testing, N/S exchange, condom demonstration skills and knowledge is clear.

Peer Educators knowledge and skills on report maintenance and documentation needs to be increased through capacity building and trainings.

Peer educator, usually meet at the DIC once a week for a weekly meeting and to discuss on issues faced at the field level.

VIII e. Accountant cum M&E: The project accountant have been with the project since the beginning of the project in 2009, and have been trained on accounting process, SIMSs and other related training on accouns management and documentations. However, due to lack of proper monitoring and supervision by the respective authorised persons, the accounting process is still an issue that is witness in the project.

IX. a. Outreach activity in Core TI project: Outreach activities in the TI level is still an area of concerns that needs to be relooked upon by the TI staffs with  proper planning  and implementation to be followed accordingly. Although a lot of activities are being carried out by the Outreach team in an planned manner, which have also reflected in the service uptake for clinical services and ICTC refferals and other service delivery.

The Outreach activites are not being documented properly, nor is it being done as per the sitewise or hotspot with prioritization.

X. Services: Overall service uptake in the Project and quality of service and service delivery of (Free Condom, N/S and N/SE) is very well accepted and satisfied by the HRGs met during the FGD. Linkage for STI to the clinic and ICTC referrals to the Mobile and Static ICTC is  also prefferred by the HRG.

XI. Community involvement:The HRGs involvement in the TI Project for commodities have been since the beginning of TI project; However the community’s participation in the TI Project’s events, activiites, programmes and uptake of service delivery is still lacking with minimal involvement of the communities at various levels of the TI Project.  The community have never been involved in the process ofplanning process, monitoring or advocacy level, of the TI Project.

Motivation, empowerment and collectivization is another area that the TI Project needs to impart to the HRGs, so as to enable them to be involved in a larger extent at all levels of the programme.

XII. Commodities: Hotspot Planning, Condom Demand and Gap Analysis risk and vulnerability factors has not been done or implemented in the TI Project. However the demand and distribution of condoms and N/Scalculation method is being done as per demand of the HRGs on a day to day basis and as and when required by the HRGs.

XIII. Enabling environment:Systematic plan and involvement of the community in advocacy, networking and linkages isnot witnessed in theProject. The concept of Advocacy is not well understood by the Project and is being done according to the need based.

The stakeholders met (Local leader) was able to speek openly and accpet the importance of N/S and Condoms. He have also worked closely with the TI Project and have addressed issues relating to the issue of Drug use and its affects at is level.

This needs to be strengthen and involvement of the HRGs in this aspect is utmost important, for the proper implementation and sustainability of the TI Project and mitigation with other linkages and services.

# Annexure C

# Confidential:				Reporting Form C

# EXECUTIVE SUMMARY OF THE EVALUATION

( Submitted to SACS for each TI evaluated with a copy to NACO)

# Profileofthe evaluator(s):

| Nameofthe evaluators | Contact Details with phoneno. |
| --- | --- |
| - Mr. Romeo Myrchiang – Team Leader, External Evaluator | Ch. No. 30, Rngi Jynriew, Near Iaikyntiew College, Upper Nongthymmai, Shillong – 793014, Meghalaya Email: rameses2605@gmail.com Contact: +91 9436101106 / 9862034762 |
| - Mr. Eliakim Sorhie – External Evaluator | Electrical Colony, House No. ECB-14 Kohima – 797001, Nagaland Email: eliakim_sorhie@yahoo.co.in Contact: +91 8575735801 |
| - Mr. Sanjay Paul – Finance Evaluator | Office: C/o. Ajit K. Jain & Associates, Circular Road, Dimapur, 797112 Nagaland Email: spaul936@gmail.com Contact: +91 9862762587 |
| Officials from SACS/TSU (as facilitator) | Ms. Abonuo Khatso NSACS Kohima – 797001, Nagaland Email: abonuoangami1@gmail.com Contact: +91 9436011474 |

| Nameofthe NGO: | Turning Point Organization (TPO) |
| --- | --- |
| Typology ofthe target population: | IDU |
| Total population being covered against target: | 280 IDU against 280 IDUs; |
| Dates of Visit: | 22nd & 23rd February 2016 |
| PlaceofVisit: | Project Office (DIC) at Tizit Field Visit for FGD: Police colony and 1 more spot.. |

Overall Rating based programme delivery score:

| TotalScore Obtained(in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 61%-80% | B | Good | [68 %] Recommended for continuation with specific recommendation for improvement. |

# Specific Recommendations:

- All Project Staffs (PM, ANM, Accountant, ORWs & PEs) must be provided with appointment letters along with their roles and responsibilites. - Project Director needs take active participation in the TI Project implementation and must ensure that PD is at least a minimun of 2 to 3 days during the month to provide support, Monitoring and mentoring the Project staffs. - Minutes of monthly / weekly / DIC meetings needs to be properly documented and maintained, along with names, designation and signature of the respected persons. - Regular meetings with HRGs for service delivery needs to be upscale and intensified at the DIC level. - Re Orientation on Data Collection and outreach tools for Outreach Team (ORWs & PE) - Outreach & Micro planning and activities needs to be introduced and intensified with prioritization of site wise and HRG wise. - Condom and Needle Syringes gap analysis needs to the implemented by the Project staff. - Risk and vulnerability assessment need to be updated and done periodically at the TI level. - Involvement of communities at all levels of the TI Project is a must and needs to be increased - Mentoring and monitoring process needs to be intensified by the PM and PD. - DIC management team, Collectivization and formation of support groups or SHGs needs to be implemented - Movement register of all the TI staff needs to be maintained and recorded accordingly. - Organization / Project must ensure that all the Documents, Data Collection Tools are being maintian, updated and systematicall / chronologically stored; including previous years documents at the Project Office. - All receipts and vouchers should be serialised and machine numbered. - All the expenditure must be according to the approved Budget with supporting documents. - Temporary Loan must be through bank transaction or A/c Payee, and the same returned via Bank Transaction, A/c Payee, and not by Cash. - Cash in hand should always be less than 5000. - Transaction for any amount above Rs 5000 should be done through cheque only. - TA must always have supporting voucher and must coordinate with the movement of the TI Staff, and also properly documented. - Books of account must be updated regularly. - BRS must be prepared month wise. - Expenditure for Every Budget head must have supporting documents and with proper supporting voucher. - Re allocation of Budget heads must be supported with proper authorization. - Budget heads suc as Crisis Response, Advocacy, Documentation etc. should not be supported by the bills for purchasing of foodstuffs. - More training is required for accounts and record maintenance. - The Use of Tally must be implemented and practices by the Accountant.