Nagaland State AIDS Control Society

Targeted Intervention- Evaluation Report

- 2016-

Youth Action for Social Service

Typology: IDUs

Phomching, Mon District

Nagaland

Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr.Eiliakim Sorhie– External Evaluator

- Mr.Sanjay Paul– Finance Evaluator

- Ms. Abonuo Khatso – NSACS Observer

Introduction

- Background of Project and Organisation

Youth Action for Socal Service (YASS) was formed in 1998 by a group of young people and with a zest and dedication of addressing the issues of the marginalized people living in Mon district. The organization was formally registered under the Societies Act – 1860, in the state of Nagaland on the 29th October 2002. The organization since its inception has been working for the development, upliftment and welfare of the tribal population of the Konya tribes in Nagaland.

The organization is operting in the district from its head office at Mon town and implementing the targeted intervention project at Phomching village (a distance of appx. 1 hours drive) and the neighboring villages from its Project Office at Phomching.

The targeted intervention project for IDUs has been implemeted by the Organization since 2009.

- Name and address of the Organization: Youth Action for Social Services (YASS), P.O. Mon, Mon District, Nagaland

- Chief Functionary: Mr. Along Tangsa Konyak ( Organization Chairman and Project Director of the Targeted Intervention project)

- Year of establishment: 2002

- Yearand month of projectinitiation:2009

- Evaluation team:

- Mr. Romeo Myrchiang – Team Leader

- Mr. Mr.Eiliakim Sorhie – External Evaluator

- Mr. Sanjay Paul – Finance Evaluator

- Time frame: April 2014 – January 2016 [ 22 Months]

ProfileofTI

- Target Population Profile: IDU

- Typeof Project:  IDU

- Sizeof Target Group (s): 249 IDUs [2014- 2015] ; 249 IDUs [2015 – 2016]

- Target Area:Phomching (Mon rural areas, and adjoining areas bordering Myanmar )

IDU SITES:Nyahnyu , Phomching , Longwa , Longshen Town , Tangnyu, Wetting , Longzang.

- Organizational support to the programme

The overall organizational support of YASS towards the TI project during the project year of 2014 – 2015 – 2016 seems negligible and was not witness in the project’s implementations or its activities, in terms of monitoring, supportive supervision and accountability. 

Although the Project Director seems to be involved in the monthly meetings of the Project, proper documentation of the same was not witness in the monthly meetting registers or any other reports or activities. The project’s activities are being managed and implemented by the TI staffs (PM, ORWs, Accountants, ANM and PEs) based on their understanding and capacity without the supervision of monitoring of the Project Director. 

The organizational involvement on accountability and responsibility is not witness as many of the TI project’s related documents were missing or not available at the project office during the evaluation, even after repeated request were made by the evaluation team and the program manager to the chief functionary for the documents.

| Oganization’s Executive Members |  |  |
| --- | --- | --- |
| Sl. No | Name | Designation |
| 1. | Mr. Along Tangsa | Chairman |
| 2. | Mr. Achum Konyak | Vice Chairman |
| 3. | Ms. Lily Konyak | Secretary |
| 4. | Mr. Wanjin Konyak | Executive Member |
| 5. | Mr. Kaipha Konyak | Executive Member |
| 6. | Mr. Honka Konyak | Corresponding Secretary |
| 7. | Mr. Leiong Konyak | Executive Member |
| 8. | Ms. Shelih Konyak | Executive Member |
| 9. | Mr. Ngipsha Konyak | Executive Member |
| 10. | Mr. Chingkam Konyak | Executive Member |

II.OrganizationalCapacity

- Human resources:The Staffing pattern in the TI Project have been implemented as per the NACO guidelines and as per the Project proposal and Budget approved by NSACS. Appointment letter of the PM, Accountant, ANM were not provided or given nor available at the project office. However ORWs appointment have been made by the PM for the project year of 2015 – 2015 on blank papers and not on the Organization’s Letter head. It is also witness that most of the project staffs, ORWs and PEs could not define their roles and responsibilities within the TI project.

Peer Educators have not been given any appointment nor any job description during the project period of 2014-2015-2016; their appointment are being done on verbal conversation basis.The project team are helpful and cooperative towards each other; however none of the projects staff or team are from the community or IDU background (neither the ORWs or the PEs).

| Sl. No | Name | Designation | Date of Appointment. |
| --- | --- | --- | --- |
| 1. | Mr. Along Tangsa Konyak | Project Director | Since the Project Inception in 2009 |
| 2. | Leiong Konyak | Programme Manager | 5th December 2012 |
| 3. | Hangpong Konyak | Accountant | 1st June 2015 |
| 4. | Ms. Moionhingkai Konyak | ANM | 3rd January 2014 |
| 5. | Mr. Bannyei Konyak (Aban) | ORW -IDU | Septemer 2014 |
| 6. | Ms. Thengli Konyak [Helen] | ORW - SPs | September 2014 |
| 7. | - Not Available - | Doctor [ Part Time] |  |
| 8. | Manyen | PE - IDU | September 2014 |
| 9. | Yelem | PE - IDU | June 2013 |
| 10. | Manlei | PE - IDU | April 2013 |
| 11. | Tonghe | PE - IDU | September 2014 |
| 12. | Chingnyei Konyak | PE –IDU | October 2010 [ Passed away on the 17 Feb 2016 ] |
| 13. | Minsheih | PE –IDU | July 2009 |
| 14. | Khampei | PE –IDU | September 2014 |
| 15. | Thoaton | PE - IDU | April 2013 |

- Capacity building: The TI project staffs have been trained by State Training and Resource Centre, Identified Learning Sites – Bethesda Youth Center& Care and Support Society covering topics on Orientation and refreshers and Harm Reduction during the project period of 2014 – 2015 – 2016.  The mentioned trainings have been attended by the ANM, ORWs and PEs of the project during the project years. 

In house, TI Project level trainings have not been organized by the project during the project years.

- Infrastructure of the organization: The Project Office is equipped with a 4 roomed infrastructure which includes STI Clinic, Counselling room, separate rooms for the Drop in Centre, PM& Accountant room and ORWs room. The project office is located near the village football ground and a little interior of the village and from the main road. In terms of accessing services and commodities by the community it may not be a feasible place, however the place offers privacy and space for the community members visiting the DIC and accessing the services provided by the TI project.

4. Documentation and Reporting:The TI Project is not maintaining documents and other procedures as per the NACO Guidelines. The project staff are not maintaining documents as per the projects requirement and implementation. Most of the documents during the project period of 2014- 2015 were not at the project office, while there are also documents that were not mainted or missing for the project year 2015-2016. There was No monitoring, checking or supervision done by the Program Manager or Project Director of the project. Adherance to SACS and Auditors reports and protocol was not complied or followed by the Organization or Project; Feedbacks and suggestions by NSACS officials, DPO mentioned in the visitors registeres have not been followed or carried out the TI project staff; Previous Evaluation feedbacks were also not followed by the organization.

Data collection tools formats:The project is not maintaining proper documentations of the Data collection tools as per the guidelines or as per the requirement of the project. Eg: Form A – HRG Registration Format is being duplicated for the same UID or person and is being done on yearly basis, and is being kept in a haphazzard and un organized manner, and many of the forms were missing, and not maintained in a serialize manner, registrations are from 2009 and 2010 only and only 3 Forms were of the 2013;  Master Registration Register is maintained by the project, however it has not been updated and the records available was till the UID 130; Form B_1:  Mismatch of data on cross checking and verification from the PEs and in comparing with the diaries they are maintaining (Authentication and verifcation have not been done by the project staff). Also most of the datas are written and maintained in Pencil with only the months written and not the year of the report; Form C: One ORW maintained the records from April 2014 – March 2015; while the other ORW maintained for the period of April 2014 – October 2014 and no further reports or documents were maintained after that. While other documents relating to the clinical aspects and services are being maintained by the ANM accordingly.

The overall project planning (Quarterly, Monthly, outreach as well as micro planning is not being implemented or followed by the outreach team to track individual HRGs for services delivery by the project for ICTC Testing, STI, Syphilis testing, Demand and gap analysis etc); A lot of mismatch between Movement registers and the dates of activities being conducted by the project. 

Project’s performance and review mechanism is not witness in the project, as well as monitoring an supervision is absent from the level of the Program Manager, Project Director and overall from the organiation.

CMIS and SOEs are being sent to NSACS on a regular manner indicating the monthly project performance in term of expesens; however the SOEs available were only from April 2015 – September 2015.

II.Program Deliverables

Outreach

- Line listing of the HRG by category: Sitewise Line Listing and registration of all the HRG have been done and completed as per the Project proposal and as per the Targeted Project population coverage (ie. a target of 249 IDUs). Line listing as per the information available for the PE site-wise line listing which does not match with the Master Registration Register and the Registration Forms. However, the HRGs as per the documents available were provided and reached with services under the TI Project for Needle & Syringes and Condoms, ICTC referrals, STI and Abscess treatment etc.

Project Site: Longwa, Longzang Village, Nyahyu village, Phomching, Longshen, Tangnyu, Wetting Village.

- Micro planning in place and the same is reflected in Quality and documentation: Proper planning have not been done by the TI project for service delivery of N/S and Condoms; however the outreach team deliver commodities and services to the key population as per the needs and requirement as well as demand of the communities. Mircro planning and implementation of activites is not reflected in the documents of the PEs and ORWs nor at the TI project level in the other activities with the key population. Risk assessment and prioritization of HRGs have also not been done by the TI project, neither being done by the Outreach Team. Linkages between the Outreach team and the ANM for clinical servicesand link with Mobile Clinic for ICTC Testing and STI Testing.

- Coverage of target population (sub-group wise): As per the Targeted population of 249 IDUs [2014-2015-2016], less than 70% of targeted population are being provided with services by the TI project on a regular basis or as and when needed by the HRGs.

4.  Outreach planning: Quality of Outreach planning as well as documentation is not implemented by the TI Project. Activities and tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization and proper planning.

Activities such as Advocacy, Outreach andClinical services and other services provided by the TI Project are being done in an unplanned and unsystematic way and on a need based. However, clinical services for ICTC and STIs are being conducted depending on the number visits the Mobile ICTC unit visits the project areas. Counselling as well as other activities were also conducted during the mobile ICTC days in the selected and specified area or village.

5.   PE: HRG Ratio: The TI Project have a total of 8 PEswho are looking after 7 project sites under the TI Project.

6. Regular contacts: Regular contact [ie 20 day / per month for the IDUs as per NACO guidelines] of the HRGs is not being maintained or carried out by the Outreach staffs (PEs) in actual; due to the vast area and distance coverage of the project added by the mobility and livelihood activities of the HRG; and regular contacts for IDUs are also being maintained by the PEs who are providing N/S and Condoms to the HRGs which is <70% out of the active HRGs.

PEs are not being able to categorized or prioritized risk and vulnerabilities of the HRGs under them; awareness regarding the harm reduction and STI related diseases as well as behavoiur change are still not clear among the HRGs; while linkages for clinical services and ICTC referrals or follow ups is being coordinated with the TI clinical ANM for Mobile ICTC services.

7. Documentation of the peer education: Peer Educator document’s (Form B_1) which is the backbone of the TI Project are being maintained as per NACO’s data collection tool, but not maintained properly and some of the data were not available at the project office. Peer Educator Dairy that are being maintained by the PEs at the Field level and used for the documentation and reporting of Form B_1 were also not available at the project office for verification or justification by the PEs. The level of understanding of the PEs in terms of risk assessment, vulnerability and prioritization of the HRGs is still lacking among the Peer Educators. Also, the flow of distribution of commodities (N/S and Condoms) remains to be constant throughout the project period, which is reflected in the “Form B_1 – PE Weekly Planning and Activity Sheet”, which is filled up by the PEs along with the ORWs during the reporting days of the week.

7. Quality of peer education: Interacting with the Peer Educators who were at the Project office during the Evaluation, their quality of education, knowledge and communication skills are not very clear to address the issues of HIV and AIDs, Drugs and injecting related harms, STI, Risk Behaviour, Harm Reductionand other related basic issues waswitnessed during the discussion.

Peer Educators in the project are selected from the general community and does not belong to the HRGs community or background; Peer Educators are not aware of the objectives, goal and planning process towards reducing risk behaviour neither among the target population nor on the importance of prioritization process.

Although emphasis on trainings have been provided and conducted by identified learning sites and State Resource and Training Centre,  most of the PEs seems to implement whatever the knowledge they learn from these trainings without proper supervision and monitoring system by the Program Manager or Project Director.

8. Supervision: The overall supervision and monitoring of TI Project is not witness in the Project from the level of the PM or the PD. Although at the field level the PM, Outreach staff and the ANM are implemting the activities and clinical services delivery through unplanned and based on the need based of the commuity. Although documents on follow up  ICTC, STI referrals are being maintained at the project level proper tracking and prioritization of the HRGs have not been done.

IV. Services

- Availability of STI services:The TI Project have a STI clinic managed by the project ANM without any doctor, and no information was available to verify the available of linkage with the project doctor; The clinic have supply of STI drugs and testing kits which is being supplied by NSACS and also purchased by the TI project as per the norms; The project is linked to the Mobile ICTC which visits the project sites twice a month, where all tests are being carried.

2. Quality of the services: The TI’s STI clinic cum counselling room does not have much privacy and is being maintained by the project ANM. Clinical equipments are available in the STI Clinic, with supply of medicines for the treatment of STI and Abscess cases.

3.  Quality of treatment in the service provisioning: The STI clinic have provided services and treatment to the HRGs with STI treatment, 4 cases of Abscess management, Counselling and linkages for ICTC testing; with 183 episodes of STI Counselling, and 705 episodes of counselling;

4.  Documentation: The TI Clinic is maintaining registers related to services deliveryand are maintained by the ANM which includes Network Clinic Register, Clinic Daily Summary Sheet, Medicine Stock Register, Referral Slips, Counselling Register. The system of procurement of medicines is not witness in the project.

5.  Availability of Condoms & Needle Syringes:The TI project is distributing free condoms which are being acquired from SACS or DAPCU. The TI is maintaing stock in hand, while buffer stock for 3 months is not being maintained at the TI Project level. Condoms are being distributed by the PEs and ORWs in the field level, while at the DIC level it is through the ANM or PM.

Condom demand and gap analysis have not been done / implemented at the TI Project level.

On the other hand the N/S stock register is mainainted and available only for the month of April 2015 to January 2016, with no proper purchasing mechanism and is being purchases at an interval of 2 to 3 months period, with no proper demand and gap analysis or for 3 months buffer stock.

6.   No. Of Condoms distributed: A total of 38,333 numbers of free condoms were distributed through the Outreach Team and ANM; during the period of April 2014 to January 2016; (As per the CMIS reports)

7.  No. of  Needles /Syringes Distributed: A total of 60,580 number of free Needle /Syringes were distributed during the period of April 2014 to January 2016 through the Outreach Workers, Peer Educators,  and DIC with a returned of 55,724 number of Needle Syringes through the NSE programme which is 91%. (As per the CMIS reports)

Waste Disposal Management at the TI level is not purely as per the NACO guidelines; PEs are collecting the N/S form the field in polythene bags and not in punctured proof box / jar; while disinfection of the N/S are not being done on a regular basis and only a few times were being disinfected which are then finally disposed off by burning in a pit dug outside and at the backyard of the DIC. (Pic Insert)

8. Information on linkages for ICTC, DOT, ART, STI clinics: Linkages for STI  and HIV testing with the mobile ICTC has been effective with 60% IDUs having undergone Syphilis testing; and 61% IDUs having undergone HIV testing.

RNTCP referrals and awareness among the HRGs have not been done by the TI Project; however it may also be noted that no cases were detected for TB or HIV+  during the Project period.

9. Referrals and follow up: Referral mechanism is being maintained by the TI and follow up mechanism has also been maintained and followed up by the ANM in coordination with the Outreach team and the Mobile ICTC clinic.

V. Community participation

- Collectivization activities: Collectivization or formation of groups has not been initiated by the TI Project.

2. Community participation in project activities: The overall community participation in the Project is very low. The outreach team (ORWs and PEs) of the projet itself are not from the community / IDU background; the project has not been able to involve the IDU community at large in various activities and events of the TI Project. Although the communities are taking part in the FGDs at the field level very few are involved and with no proper documentation.

VI. Linkages

- Assess thelinkages establishedwith thevarious services providers like STI,ICTC, TBclinics etc : The TI Project have established links with Mobile ICTC clinic.

- Percentages of HRGs tested in ICTC: 61% of the registered / active HRGs have undergone HIV testing during the project period [ April 2014 – January 2016] (As per CMIS report)

- Support system:The TI Project have support system only on clincal service delivery with the Mobile ICTC for HIV and STI testing; The project have only been able to develop rapport with only a few stakeholders and decision makers of the society, with few and unplanned advocacies being undertaken by the project. The stakeholders met have also reported of being indirectly invovled with the TI project at some level.

VII. Financial systems and procedures

- Systems of planning: The organization/management is allowing the Project Office  to prepare the books of accounts as per the budget allotment and schedule provided by NSACS, without planning (either quarterly or yearly) which should have been based on activity wise as well as release of funds eg. program cost, community based activity, servics related services etc, Expenses are being made randomly without proper or system of planning. However, this is being assessed only with the Ledger and Cash Book for the project period of April 2015 – September 2015 that was available at the Project office.

The TI have spend the whole amount of funds released from NSACS. The Project also does not have any approval system endorsed by the NGO or management before incurring any expenses or expenditure.

2.  Systems of payments: All payments, are being made by Cash as per the books of accounts (Ledger, Cash Book, Salary Register) available for the project period of April 2015 to September 2015, with no supporting documents of Vouchers, Bills, cash memo and other related actual payment receipt (APR) for supporting or verication for the project period of 2014-2015-2016.

The books of accounts – Ledger, Cash Book, Vouchers, Recipts and Bills, supporting documents etc for the year 2014 – 2015 were not available at the project office for verification.

3.  Systems of procurement: There is no system for collecting any quotations before purchasing in bulk.  Stock & issue registers for Needle and Syringes is being maintained but  cannot be verified with the actual purchases or receipts as the accounting documents were not available or produced by the organization.

- Systems of documentation: The organization is maintianing and had produced only the cash book, salary register and Ledger for the project year 2015 – 2016, with no other books of documents of accounts. 

The following documents were not available or maintained by the project or organization:

  - Cash Book [2014- 2015]

  - Ledger [2014 – 2015]

  - Bank Statement / Bank Pass Book [2014 – 2015-2016]

  - Organization Vouchers [2014 – 2015-2016]

  - Cash memos / bills [2014 – 2015-2016]

  - Salary register [2014 – 2015-2016]

  - Cheque Book

  - Bank Reconciliation Statement [2014 – 2015-2016]

VIII. Competency of the project staff

VIII a. Program Manager: The Program Manager is a B.A. Graduate and have been working with the TI project since December 2013, and is also one of the executive board members. The PM have received trainings on proposal development Programme management and implementation, Data collection Tools, Finance Management, harm Reduction, SIMS. Monthly CMIS is being prepared and sent ontime by the PM, as well as SOEs are being sent monthly to NSACS.

Although, being trained and capacitated with skill and knowledge, due to lack of supervision and mentoring the PM lacks in the performance and upscalling the TI Project; Monthly and quaterly planning as well as outreach plans for the TI on service delivery have not been done by the PM. Accountability and suportive supervision to the project staff is not satisfactory or visible at the poject outreach activities with few visits of 3 to 4 times a month in the field.

VIII b. Nurse / ANM: The project’s ANM is a BA Graudated and have completed her Diploma in Nursing and have been working in the project since March 2014 and have been trained been trained for Counselling, Harm Reduction, STI management. The ANM is efficient with her roles and responsibiites and in dealing with the HRGs.

Record maintenance, updating of data and maintaining of registers at the Project clinic is being maintained by the ANM; with a field visit of 1 to 2 times per month or as per the needs of the HRGs, while in most of the time she remains at the office. The ANM is clear on the concept of Harm Reduction, Abscess management, STI management, with basic counselling skills.

VIIIc.ORW: The project ORWs are not from the IDUs background have been with the project since May 2014; ORWs in the TI Project have been trained by the Learning sites and STRC, on induction, refresher and Harm Reduction.

Their knowledge about the target population and on various indicators for their PEs, Hotspot analysis, outreach plan, importance of ICTC testing and well as STI testing is not so clear. The ORWs are also not aware of the various drugs used by the HRGs or by the IDUs.No properOutreach Planwas visible at the project level.

Field level activities and PEs support is very limited at the TI Project, with a visit of 4 times a month; due to the vastness of the coverage area it is only possible to meet once or twice per PE per site per week .

VIIId. Peer Educators: Peer educators have been trained under STRC and the learning sites on orientation and refreshers as well as harm reduction. However in house training have not been conducted at the project level

With many of the PEs interacted, their knowldege on hotspot or site prioritization and on prioritization of HRGs is not very clear; while theimportance of ICTC and STI testing, condom demonstration skills and knowledge is clear.

Peer Educators knowledge and skills on report maintenance and documentation is not proper and cannot be authenticated as the reports are only maintained once a week at the project office, during the weekly meeting on every Friday of the week; Peer Dairy at the field level is also not maintained by the PEs.

VIII e. Accountant cum M&E:The project’s accountant is a B.A graduate and have joined the project on June 2015. The accountant have not received or being trained for accounts maintenance but have been trained for SIMS reporting. Many of the Books of Accounts are not maintined by the Accountant. The knowledge of the Accountant on the Data collection tools of the project is also limited.

IX. a. Outreach activity in Core TI project :Outreach activities in the TI level is still an area of concerns that have not been implemented by the project which is being reflected with the abscene of the Monthly and Outreach plans. The mismatch of activites and other relavent registers and reports available at the project office. Although activities are being carried out by the Outreach team in an unplanned manner, which have also reflected in the service uptake for clinical services and ICTC refferals.

The Outreach activites are not being documented properly, nor is it being done as per the sitewise or hotspot with prioritization. The outreach team are doing these activities only to achieve their targets and deliver the commodities to the HRGs without proper understanding and prioritization of the HRGs.

X. Services: Overall service uptake in the Project and quality of service and service delivery of (Free Condom, N/S and N/SE) is very well accepted and satisfied by the HRGs met during the FGD. Linkage for STI to the clinic and ICTC referrals to the Mobile  ICTC is  also prefferred by the HRG.

XI. Community involvement: The HRGs involvement in the TI Project for commodities have been since the beginning of TI project; However the community’s participation in the TI Project’s events, activiites, programmes and uptake of service delivery is still lacking with minimal involvement of the communities at various levels of the TI Project.  The community have never been involved in the process ofplanning process, monitoring or advocacy level, of the TI Project.

XII. Commodities:Hotspot Planning, Condom Demand and Gap Analysis risk and vulnerability factors has not been done or implemented in the TI Project. However the demand and distribution of condoms and N/Scalculation method is being done as per demand of the HRGs on a day to day basis and as and when required by the HRGs.

XIII. Enabling environment: Systematic plan and involvement of the community in advocacy, networking and linkages is not being implemented or visible at the TI Project. The concept of Advocacy is still not understood by the Project staff and is being conducted on a need based with no proper records of documents.

The stakeholders met (village chairman and Gaon Bura) were able to speek and accpet the importance of N/S and Condoms for the IDUs, however it is also shared by them that many of the younsters are into Opium inhaling or smoking and also spoke of the possibilities of having an OST centre.They also understood the need and importance of the prevention of HIV and AIDS and of staying safe.

Annexure C

Confidential:				Reporting Form C

EXECUTIVE SUMMARY OF THE EVALUATION

( Submitted to SACS for each TI evaluated with a copy to NACO)

Profileofthe evaluator(s):

| Nameofthe evaluators | Contact Details with phoneno. |
| --- | --- |
| - Mr. Romeo Myrchiang – Team Leader | Ch. No. 30, Rngi Jynriew, Near Iaikyntiew College, Upper Nongthymmai, Shillong – 793014, Meghalaya Email: rameses2605@gmail.com Contact: +91 9436101106 / 9862034762 |
| - Mr. Eliakim Sorhie– External Evaluator | Electrical Colony, House No. ECB-14 Kohima – 797001, Nagaland Email: eliakim_sorhie@yahoo.co.in Contact: +91 8575735801 |
| - Mr. Sanjay Paul – Finance Evaluator | Office: C/o. Ajit K. Jain & Associates, Circular Road, Dimapur, 797112 Nagaland Email: spaul936@gmail.com Contact: +91 9862762587 |
| Officials from SACS/TSU (as facilitator) | Ms. Abonuo Khatso NSACS Kohima – 797001, Nagaland Email: abonuoangami1@gmail.com Contact: +91 9436011474 |

| Nameofthe NGO: | Youth Action for Social Service (YASS) |
| --- | --- |
| Typology ofthe target population: | IDU |
| Total population being covered against target: | 249 IDU against 249 IDUs; |
| Dates of Visit: | 18th & 19th February 2016 |
| Placeof Visit: | Project Office (DIC) at Phomching Field Visit for FGD: DIC and Longwa spot. |

Overall Rating based programme delivery score:

| Total Score Obtained(in%) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 41%-60% | C | Average | [47.5 %] Recommended for Closure of the Project |