Nagaland State AIDS Control Society

Targeted Intervention - Evaluation Report

April 2014- January 2016

Yingli Mission Society

IDU

Longleng

Longleng District

Evaluation team:

- Mr. Kholi. A– Team Leader, External Evaluator

- Mr.Kevileme Visezuo – External Evaluator

- Mr. Raju Gupta– Finance Evaluator

Annexure: B

Reporting Format-B

Introduction

OBackground of Project and Organisation

Yingli Mission Society (YMS) a non-profit organization, registered under the Societies Registration Act 1860, No. RS/2145 Dated: 8-03-2002, is committed to work for the up-liftment of people in need of health, education, HIV and AIDs and other socio economic development. The organization since its inception have been working and supporting people, especially the disadvantaged group by extending care and support, linking them to treatment centres, caring for them in their home, counselling and rehabilitation.

The organization’s vision mission is to promote a society where sustainable opportunities are ensured for the poor and marginalized. The organization’s aims and objective is to build and evolve self-confidence and hope among the drop outs and youths, drug using community and people living with HIV and AIDS through creation of income generation activities, career guidance, and rehabilitation programmes etc.

The organization is implementing TI project under NSACS at Longleng and Tamlu for IDUs.

O Name and address of the Organization

Yingli Mission Society, P.O Box – 1, Lempong Junction, CTN Road, Longleng – 798625, Nagaland

| Telephone | : | 0369-236295 [O] 9436012551 [Secretary] |
| --- | --- | --- |
| E-mail | : | yinglimission@yahoo.co.in |

O Chief Functionary				:Mr. Thepmei

O Year of establishment			:2002

O Year and month of project initiation	: 2005

O Evaluation team:

- Kholi. A (External Evaluator)

- Kevileme Visezuo(External Evaluator)

- Raju Gupta (External Finance Evaluator)

O Time frame:

Date of evaluation: 	1st- 2nd February 2016

Assessment Period: 	April 2014- January 2016 [22 months]

Profile of TI

O Target Population Profile:Injecting Drug User (IDU)

O Type of Project:Core Group (IDU)

O Size of Target Group(s)

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 300 | 300 |
| Achievement | 300 | 300 (114 IDU & 86 OST) |

O Target Area:

| Sl. No. | Name of the Coverage area | Old Target | New Target |
| --- | --- | --- | --- |
| 1 | Medical ward | 17 | 0 |
| 2 | Nyengching ward | 14 | 0 |
| 3 | Shaulih ward | 13 | 0 |
| 4 | Agri ward | 14 | 0 |
| 5 | PPC ward | 15 | 0 |
| 6 | High school ward | 13 | 0 |
| 7 | Shayong ward | 12 | 0 |
| 8 | Shamkang ward | 14 | 0 |
| 9 | Leinyak ward | 12 | 0 |
| 10 | Bahok ward | 14 | 0 |
| 11 | Mole ward | 15 | 0 |
| 12 | Orangkong village | 15 | 0 |
| 13 | Alayang village | 15 | 0 |
| 14 | Yaong village | 14 | 0 |
| 15 | Yachem village | 14 | 0 |
| 16 | Hukphang village | 14 | 0 |
| 17 | Namching village | 12 | 0 |
| 18 | Phumnyu village | 13 | 0 |
| 19 | Pongo village | 17 | 0 |
| 20 | Yongphang village | 20 | 0 |
| 21 | Sakshi | 18 | 0 |
| Total |  | 300 | 0 |

I. Organizational support to the programme

The overall organizational support of “Yingli Mission Society” towards the TI Project in Tamlu is supportive and cooperative towards the IDU community.

Although committed to the cause of the target population the overall organizational support to the project in Tamlu, is not available; The Board / Organization members involvement in any of the Project’s activities in the TI Project at Tamlu is not visible in the Project. The TI Project’s activities is being managed and implemented by the PM, Nurse, Accountant and Outreach Team based on their understanding and capacity, without the supervision or monitoring of the TI Project Director.

| Organization’s Board of Members |  |  |
| --- | --- | --- |
| Sl. No | Name | Designation |
| 1. | ThemjenPhom | Chairman |
| 2. | Lima Mannen | Secretary |
| 3. | Aliba | Member |
| 4. | Mr. Nuklu | Member |
| 5. | Smti. Merenchila | Member |
| 6. | Asangla | Member |
| 7. | Dr.Meren | Member |

II. Organizational Capacity

1. Human resources:

- The Staffing patterns in the TI Project have been implemented as per the NACO guidelines and as per the Project Proposal and Budget approved by NSACS.

- PM, Accountant, Nurse and ORWs has been provided with appointment letter. Signature of staffs are not indicated in appointment letter

- The roles and responsibilities of the project staff is available at the TI project;

- PEs are not given any appointment letters nor provided with any roles or responsibilities in the TI project. They are appointed through verbal conversations only. The project staffs are cooperative and helpful towards each other, especially the PEs and ORWs who are also from the community.

- PD is involved in the project and attends monthly meetings. However, his signature in some meetings are missing and not matching in some case. PD attended a total of 15 meetings but his feedback and inputs are not reflected in records.

| Sl. No | Name | Designation | Date of Appointment. |
| --- | --- | --- | --- |
| 1. | Mr. TemjenPhom | Project Director | Since the beginning of the TI Project [ 2009] |
| 2. | Senti | Programme Manager | 1st August 2013 |
|  | Chuje | Programme Manager | 20th January 2016 |
| 3. | Yamen | Accountant cum M&E | 1st January 2014 |
| 4. | AshomPhom | Nurse (ANM) | 1st January 2013 |
| 5. | Manik | ORW | 1st April 2013 |
| 6. | Teong | ORW | 1sst August 2015 |
| 7. |  | Doctor [ Part Time] | No records available |
| 1 | Bauong | PE | 1st April 2013 |
| 2 | L. Chingmei | PE | 1st April 2010 |
| 3 | N. Bendang | PE | 1st April 2007 |
| 4 | Talong | PE | 1st April 2012 |
| 5 | Chongpang | PE | 1st April 2011 |
| 6 | Moanukshi | PE | 1st August 2014 |
| 7 | C. Cingmei | PE | 1st April 2008 |
| 8 | Anung | PE | 1st April 2012 |
| 9 | Chaupa | PE | 1st April 2011 |
| 10 | Chaupen | PE | 1st April 2013 |
| 11 | Chingshimong | PE | 1st April 2010 |
| 12 | Ashi | PE | 1st April 2014 |
| 13 | Chongngo | PE | 1st July 2015 |

- Post of one PE internally adjusted for Spouses of HRGs.

2. Capacity building:

List of training details-

| Name | Designation | Training attended |
| --- | --- | --- |
| Chuje | Programme Manager | Accounting & Refresher |
| Yamen | Accountant | MIS & Accounting |
| AshomPhom | Nurse | Induction |
| Manik | ORW | Refresher |
| Teong | ORW | Refresher |
| 12 PEs | PEs | Not all were trained. In-house orientation given. |

3. Infrastructure of the organization:

- The TI DIC has 3 rooms (Project Director’s room, one room has been portioned into PM cum Accountant cum STI/ Counselling cum ORW’s working room and one recreation room.

- 2 rooms are allotted for OST clients and the TI has a kitchen attached with the OST client’s room.

- Basic office furniture’s are in place.

- Computer, laptops, TV and lockers in place.DVD Player not functioning.

- Static STI clinic set up and in place.

- Basic clinical equipment’s missing.Weighing machines, N/S Destroyer and Sterilizer not working.

- Waste disposal mechanism not maintained.

- STI medicines Kit 1 & 6, disinfectants and gloves are available.

- Board games (carom) available for recreation.

- Documentation and Reporting:

- All 17 formats for data collection in use.

- PE’s submit their reports to their respective ORW on a weekly basis.

- Review meeting done on a weekly and monthly basis and actions are taken as per the gaps and achievements for each staffs and PEs.

- SIMS and SOEs are submitted to NSACS in the first week of succeeding month.

- Sharing of project reports and technical inputs takes place during the quarterly, half-yearly and annual review meeting organized by NSACS.

- Electronic database and management reporting systems exist for tracking clients, programme outcomes and financial information.

- Feedback and compliances to audit observations were not followed.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 300 | 300 |
| Achievement | 300 | 300 (114 IDUs & 186 on OST) |
| Newly registered | 12 | 0 |

2. Micro planning in place and the same is reflected in Quality and documentation.

- Outreach plan and micro plan not in place at project or hot spot level.  Weekly plan available/ maintained for delivery of project services.

- Micro planning and outreach plans are done on a weekly and monthly basisandimplemented in outreach activities by ORWs and PEs.

5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- March 2015: | April 2015 - Jan. 2016 |
| --- | --- | --- |
| Target | 300 | 300 |
| Achievement | 300 | 300 |
| Nos. of New HRGs | 12 | 0 |
| Nos. of active HRGs | 294 | 246 |

- Active HRGs were provided with project services on a regular basis.

6. Outreach planning

- Work plan for PE done on a weekly basis.

- Monthly plan for outreach in place.

- Tracking of HRGs for service delivery by the outreach staff is done on a need based and randomly without prioritization and proper planning.

- Coordination meeting between Nurse, ORWs and PEs are done on a weekly basis and actions are taken based on gaps or achievements.

7. PE: HRG ratio:

- Ratio of PE to HRG is 1:25 as per contract agreement. Target is 300 IDUs and 12 PEs are on board.

8. Regular contacts

- On an average, 53% of total registered HRGs were regularly contacted 20 days every month and provided project services.

- PEs reported that some sites were never visited by ORW during last one year.

9. Documentation of the peer education

- Peer field dairies and Form B in use by PEs to capture their field activities. ORW assists them in data entries in Form B.

10. Quality of peer education- messages, skills and reflection in the community

- Hotspot level meetings are conducted to increase the knowledge level among the community members. Community members have basic knowledge of HIV, safe injecting practices, and proper and consistent usage of condom.

- Community members are also aware of services available at the TI DIC and other health care service providers.

11. Supervision- mechanism, process, follow-up in action taken etc

Field-mentoring and supervision: Each ORW has 5-6 peer educators for IDUs and undertakes a mentoring role. An average of 5-6 field visits are conducted by ORWs (average of once in a week). During these visits the ORW supervises the hotspots level meeting, one-to-one/group sessions conducted by PEs with HRGs, providing new information and monitor field level performance.

Meeting-based supervision: Every week ORW and PEs meets for reporting and planning. During these meeting ORW assist PEs in documentation of field activities, review performance of the previous week and plan for the succeeding week

Overall supervision of outreach plan and field activity is done by Program Manager.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- Static STI has been established and managed by a full time Nurse.

- Part time Doctor never visited clinic during assessment period.

- The clinic has adequate infrastructure and testing kits in place and has provision for handling STI cases.

- All STI medicines are not in place: only Kit 1 & 6 available at clinic.

- 12 Syphilis reactive cases observed and all were provided treatment.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- Separate room for STI Clinic established at TI DIC.

- Minimum clinical equipment’s and furniture in place.

- Network Clinic Formats in place and updated.

- Stock out of STI medicines observed. Only Kit-I and 6 available.

- Buffer stock of commodities and medicines not maintained..

- Colour coded Waste Disposal bins not in place.

3. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- TI’s STI clinic has a separate room which is partitioned into counselling room cum observation room. Privacy is being maintained.

- Minimum/ basic clinical equipment’s are available in the STI Clinic, with shortage of STI medicines Kits.

- Referral support is available and all HIV testing is referred to District Hospital.

- Mechanism of follow -up on ICTC, RMC and STIs are done by nurse as perORWs and PEs weekly report.

- 95.66% of the HRGs were provided counselling.

- 27% of the active HRGs were given RMC.

- 292 out of 300 line listed HRGs tested once in the last one year (97.33%).

- 14% of line listed HRGs underwent syphilis testing. 29% of registered 50% HRGs tested twice.

- A total of 292 underwent HIV testing at least once during the last one year (97.33%).

- 39.5% of line listed HRGs underwent HIV testing twice.

- None tested HIV positive. Linkage has been created with ART Centre.

4. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- Network Clinic Formats/ Registers used by TI NGO.

- Standard Referral slips in use and properly tracked.

- Stock registers of condomand medicines are maintained.

- TI NGO procures STI medicines Kits and Syphilis testing kits from NACO/SACS. Indent Register not maintained for requisitioning STI medicines from NSACS.

5. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Free condoms are distributed by PE’s and staffs of TI DIC. No secondary distribution outlets have been created.

- Social Condom Marketing (SCM) was initiated to cater to the needs of the community members.

- Community members reported that they get free condoms as and when they demand.  No shortage has been reported during the assessment period.

6.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

| Distribution of Commodity | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| Free Condom | 27708 | 27132 |
| Social Marketing of condom | 252 | Records not available during evaluation. |

7. No. of Needles / Syringes distributed through outreach / DIC.

|  | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| N/S distributed | 35928 | 31968 |
| Used N/S returned | 21156 | 18300 |

8. Information on linkages for ICTC, DOT, ART, STI clinics.

- Referral linkage with District Hospital, Longleng has been established for ICTC, DOT and ART.

9. Referrals and follows up

- Only 27% of the active HRGs were given RMC.

- 14% of line listed HRGs underwent syphilis testing twice. 29% of registered 50% HRGs tested twice. 12 reactive cases detected and provided treatment.

- 39.5% of line listed HRGs underwent HIV testing twice. None tested positive.

- All HIV and syphilis testing are referred to ICTC, District Hospital. Follow up actions are initiated by the Nurse during weekly and monthly review meetings.

V. Community participation

1. Collectivization activities:

- Crisis Management Team (CMT) has been established with HRG representation. A total of 6 crises were reported and was addressed by the CMT. Records are maintained in standard formats.

- One DIC Committee formed with 12 HRGs who are on OST. No records of their activities were maintained.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members involved in the project as PEs and ORWs. Activities include outreach, commodity distribution, referrals and conduct of FGD.

- All activities documented in their respective field diaries and formats.

- Community Events and Health Camps were held but records were not available for physical verification.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- Referral linkage with District Hospital, Longleng has been established for ICTC, DOT and ART.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

- 100% of the total registered HRGs were referred for HIV testing out of which only 11.83% have undergone HIV testing twice.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- The TI Project has created support system on clinical service delivery with the ICTC and RNTCP Centre in District Hospital, Longleng and with ART centre, IMDH, Mokokchung.

- Linkages and advocacy initiative with other stakeholders was in place and a total of ten [n=10] advocacies were conducted with Village leaders, Military Personnel’s, Traders Union leader, Underground cadres, Religious body, Family members of HRGs and with General community.

VII. Financial systems and procedures

1. Systems of planning:

- All planning is done by Governing Body and final approval is given by Project Director. More than 60% of the budget has been utilised against the fund released. Expenditures are made as per approved budget heads.

- NGO did not take adequate measures to conform to audit recommendations.

2. Systems of payments:

- Systems of getting approval from PD are practised before any monetary transaction.Payments are made with proper bills and vouchers but majority of bills are ‘katcha’.

- Cash transaction above NACO’s directive observed.

- Cash in hand sometimes exceeds the limit of ₹ 5000/-

3. Systems of procurement-

- Purchase of drugs is done as per GMP guide line.

- No quotation is found, as the procurement is centralized from Kohima.

4. Systems of documentation-

- Separate Bank account is maintained for the TI Project at Longleng Town.

- Audit report is in place.

- Vouchers are printed and machine numbered, but ledger is not maintained for vouchers.

- Cash book is updated on a daily basis.

- SOE is submitted in time.

- Mismatch found in physical and financial reporting on purchase of N/S.

- Assets purchased by NGO could not be traced from assets register for physical verification. No proper codification in place.

VIII. Competency of the project staff

VIII a. Project Manager

- Program Manager was recently appointed (21st January, 2016).

- Had been working with MSM community in another TI as ORW (6 months) and as Counsellor for one year.

- Has attended training on Refreshers and Accounting since joining the present TI.

- Is aware of her roles and responsibilities but is new to IDU intervention programs.

- Program Manager has basic knowledge on TI components, Risk and Vulnerability Assessment and Data Collection Tools. Has a fair knowledge on micro planning but has not yet initiated/ implemented.

- The capacity, skill and knowledge of the Program Manager in planning, program management and financial managementis limited (Training required).

VIII b. Counsellor/ ANM

- Nurse is an ANM and has been working at TI Project since January 2014.

- Nurse has attended training onSTI/ RTI, Induction Training and Refreshers training.

- Has not been trained on Counselling.

- Not able to clearly explain risk assessment and risk reduction processes.

- Is able to give basic counselling on HIV and STI.

- All registers and clinic formats maintained and updated.

- Conducts 2-3 field visits monthly or as per needs from the community member.

VIII c. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

- Two ORWs on board. One has graduated from PE and one was appointed in August 2014 as a result of turnover.

- Both the ORW has been provided Refreshers Training.

- Monitoring of PEs is done by the ORW and key performance indicators are closely checked. Supportive supervision is done based on needs and ORWs conducts FGD meetings at the hotspots.

- Is not very clear about micro plan and all outreach planning is done in consultation with their respective PEs or as per need based on a weekly basis.

- Mentoring and message on rapport building, condom demonstration and safe sex practise are imparted.

- Has limited understanding on hotspot analysis and demand-gap analysis.

- ORWs have basic knowledge of STI symptoms.

- Limited field visits by ORWs. Movement register indicates only 1-2 field visits each covering 3-4 days in a month. Some PE reported that their ORW has never met them at his hotspot/ site in two years.

VIII d. Peer educators

- PE’s are able to explain the prioritization of hotspots.

- Explain the importance of RMC and ICTC testing. RMC as to ensure regular medical check-ups and testing as to monitor to prevent the transmission of HIV.

- Exhibited condom demonstration skills with correct message on condom use.

- Knowledge about referrals points for HRGs.

- N=6 PEs has not been trained. In-house orientation was provided to them by project staffs.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- Project services are given to HRGs based on commodity distribution, referrals for RMC and HIV/ Syphilis testing. Outreach activities have not been prioritised in a planned manner: it has been set to achieve specific targets (commodity distribution and referral targets).

- Individual HRGs are tracked for ICTC and syphilis testing.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- Overall uptake of Project servicesand quality of service delivery (Free Condom & N/S) was well accepted by the HRGs.

- Above 80 % of the participants expressed satisfaction and were comfortable to approach the nurse for treatment and counselling.

XI. Community involvement

- Two [n=2] ORWs are from the HRG background. They are also involved during project planning and development of project proposal.

- Advocacies were conducted as per needs of the community. Supporting documents are maintained.

- A total of ten [n=10] advocacies were conducted to address issues of community members.

XII. Commodities

- Planning for meeting the demand of condom and N/S is done at the project level on a quarterly, monthly and weekly basis.

- Demand analysis done based on distribution of previous month or quarter.

- Frequency of injecting drugs (daily/ weekly/ occasionally), and numbers of sexual act are also taken into consideration.

XIII. Enabling environment

- Linkages and advocacy initiative with other stakeholders was in place and a total of ten [n=10] advocacies were conducted with Village leaders, Military Personnel’s, Traders Union leader, Underground cadres, Religious body, Family members of HRGs and with General community.

- Systematic plan and involvement of the community in advocacy, networking and linkages is not witness. However, a Crisis Management Team has been set up and includemembers from Women Group leaders, Legal advisor, Town Council member and other public leader.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

- Insurances for project staffs were paid in cash.

- A ‘Personal Benefit Fund’ has been created for the staffs: 25% is deducted from salary and deposited into an account which is refundable. 15% interest is added by the Organisation when contract of staffs is over/ until staffs has resigned.

Confidential                                      Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Kholi. A | +91 9862797996 |
| Kevileme Visezuo | +91 9774978143 |
| Raju Gupta | +91 7085169800 |
| Officials from SACS/TSU (as facilitator) Ms.Imtisenla | +91 9856534957 |

| Name of the NGO: | Yingli Mission Society, Longleng. |
| --- | --- |
| Typology of target population | CoreGroup (IDU) |
| Total population being covered against target: | April 2014- March 2015:; April 2015 - Jan. 2016. Target; 300; 300. Achievement; 300; 300. |
| Dates of Visit: | 1st March- 2nd March, 2016 |
| Place of Visit: | Project Office (DIC) of Yingli Mission Society, Longleng |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 60.3% | B | Good | Recommended for continuation |

Specific Recommendations:

Organizational capacity: - Signatures in contract/ appointment/ renewal letter to be ensured. - Program Manager newly appointed on 21st January 2016 and needs to be capacitated on overall program management,performance indicators, financial management, harm reduction, etc. - Nurse need to be capacitated on counselling skills. - ORWs need to be capacitated on hotspot analysis and demand gap analysis. - Ensure that all PEs who had not attended training at Learning Sites be forwarded for next batch [n=6 PEs has not been trained]. - Project Director should ensure his presence during every monthly staffs review meetings to monitor progress of project activities. - All fixed assets need to be codified and accordingly tally with asset register. - DVD player needs to be replaced. - Basic clinical equipment’s must be in place. Weighing machines, N/S Destroyer and Sterilizer should be replaced. - Waste disposal mechanism as per guidelines should be maintained/ observed. - Buffer stock of commodities and medicines should be in place for at least 3 months requirement. - TI NGO should ensure that contracted Part time Doctorvisit clinic regularly. Financial management: - TI NGO should ensure that all cash payment more than ₹ 5000/- is done in cheque. - Minimize mismatch between physical and financial reporting. E.g. Mismatch found in purchase and physical stock of N/S. - Records of all expenses incurred/ made should be properly documented and filed. - Adequate measures should be taken by TI NGO to audit observations and recommendations. - Three quotations required for purchase of commodities to ensure quality and minimise expenses. - TI NGO should try to ensure that cash in hand is less than ₹ 5000/- - Insurance Policy through proper channel for all project staffs should be ensured. Program Delivery: - Outreach activities in the TI level needs to be re-evaluated and Micro plans for all hotspots/ sites should be in place. Risk and vulnerability assessment needs to be updated periodically and should be prioritised. - ORW should conduct a minimum of 4-5 days field visit weekly and should ensure that at least all hotspots are covered every month and conduct at least 2 FGDs monthly. - Scale up on referrals for HIV and Syphilis testing required - Proper documentation needs to be put in place for all field activities. - Establish systematic plan and involvement of the community in advocacy, networking and linkages.

Name of the Evaluators				Signature

| Kholi. A |  |
| --- | --- |
| Kevileme Visezuo |  |
| Raju Gupta |  |