Nagaland State AIDS Control Society

Targeted Intervention - Evaluation Report

April 2014- January 2016

Yingli Mission Society

IDU

Tamlu

Longleng District

Evaluation team:

- Mr. Kholi. A– Team Leader, External Evaluator

- Mr.Kevileme Visezuo – External Evaluator

- Mr. Raju Gupta– Finance Evaluator

Annexure: B

Reporting Format-B

Introduction

O Background of Project and Organisation

Yingli Mission Society (YMS) a non-profit organization, registered under the Societies Registration Act 1860, No. RS/2145 Dated: 8-03-2002, is committed to work for the up-liftment of people in need of health, education, HIV and AIDs and other socio economic development. The organization since its inception have been working and supporting people, especially the disadvantaged group by extending care and support, linking them to treatment centres, caring for them in their home, counselling and rehabilitation.

The organization’s vision mission is to promote a society where sustainable opportunities are ensured for the poor and marginalized. The organization’s aims and objective is to build and evolve self-confidence and hope among the drop outs and youths, drug using community and people living with HIV and AIDS through creation of income generation activities, career guidance, and rehabilitation programmes etc.

The organization is implementing TI project under NSACS at Longleng and Tamlu for IDUs.

O Name and address of the Organization

Yingli Mission Society, P.O Box – 1,

Lempong Junction, CTN Road,

Longleng – 798625, Nagaland

| Telephone | : | 0369-236295 [O] 9436012551 [Secretary] |
| --- | --- | --- |
| E-mail | : | yinglimission@yahoo.co.in |

O Chief Functionary				: Mr. Thepmei

O Year of establishment			: 2002

O Year and month of project initiation	: 2005

O Evaluation team:

- Kholi. A (External Evaluator)

- Kevileme Visezuo (External Evaluator)

- Raju Gupta (External Finance Evaluator)

OTime frame:

Date of evaluation: 	4th March – 5th March, 2016

Assessment Period: 	April 2014- January 2016 [22 months]

Profile of TI

O Target Population Profile:Injecting Drug Users (IDUs)

O Type of Project:Core Group (IDUs)

O Size of Target Group(s)

|  | April 2014- March 2015: | April 2015- Jan. 2016: |
| --- | --- | --- |
| Target | 300 | 300 |
| Achievement | 300 | 300 |

OTarget Area:

| Sl. No. | Name of the Coverage area | Old Target | New Target |
| --- | --- | --- | --- |
| 1 | Highschool colony | 15 | 1 |
| 2 | Medical colony | 14 | 1 |
| 3 | Church colony | 16 | 1 |
| 4 | NST colony | 13 | 1 |
| 5 | New colony | 16 | 1 |
| 6 | Tamlu Village | 15 | 1 |
| 7 | Tamlu k | 14 | 1 |
| 8 | Kangching | 17 | 1 |
| 9 | NetnyuChing | 16 | 1 |
| 10 | B.Namsang | 15 | 1 |
| 11 | Anaikhai | 11 | 1 |
| 12 | Shetap | 19 | 1 |
| 13 | Yonglok | 15 | 1 |
| 14 | Shemnyuching | 17 | 1 |
| 15 | Ngetchongching | 16 | 1 |
| 16 | Nemha | 19 | 1 |
| 17 | Aboiji | 17 | 1 |
| 18 | Kongshong | 17 | 1 |
| 1 | Total | 282 | 18 |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

- The project aims to contribute to the reduction of HIV&AIDS incidence among 300 injecting drugs users and 60 their sexual partners in 1 town and 13 villages in Tamlu Block under Longleng District.

The NGO will be focusing on: strengthening outreach services through effective planning, implementation, supervision and documentation; provisioning of quality clinic services; increasing the involvement of HRG in the project through establishment of support and Core Committees; capacity building of project staff and PEs; and strengthening monitoring system within the project.

II. Organizational Capacity

1. Human resources:

| STAFF STATUS: YINGLI MISSIN SOCIETY, TAMLU DIC (2014-2015) |  |  |  |  |
| --- | --- | --- | --- | --- |
| SL.NO | NAME | DESIGNATION | EDUCATIONAL QUALIFICATION | DATE OF JOINING |
| 1 | M.KONI.PHOM | PROGRAM MANAGER | BA | Aug-11 |
| 2 | PURTOSHI | ACTT CUM M&E | B. COM | Apr-14 |
| 3 | MOJE | NURSE | ANM | Aug-11 |
| 4 | BANGOM | ORW | 10 PASSED | Apr-07 |
| 5 | PONGE | ORW | PU PASSED | Apr-06 |
| TAMLU DIC 2015-2016 |  |  |  |  |
| SL.NO | NAME | DESIGNATION | EDUCATIONAL QUALIFICATION | DATE OF JOINING |
| 1 | M.KONI.PHOM | PROGRAM MANAGER | BA | Aug-11 |
| 2 | PURTOSHI | ACTT CUM M&E | B.COM | Apr-14 |
| 3 | MOJE | NURSE | ANM | Aug-11 |
| 4 | BANGOM | ORW | 10 PASSED | Apr-07 |
| 5 | PONGE | ORW | PU PASSED | Apr-06 |

|  | PE STATUS YINGLI MISSIN SOCIETY |  |  |  |
| --- | --- | --- | --- | --- |
| Sl. No. | NAME | DESIGNATION | EDUCATIONAL QUALIFICATION | DATE OF JOINING |
| 1 | ONGVAI | PE | 8 PASSED | Apr-09 |
| 2 | CHINGSHAH | PE | 10 PASSED | Nov-11 |
| 3 | JAMES | PE | PU PASSED | May-15 |
| 4 | JOHAN | PE | 8 PASSED | Nov-11 |
| 5 | MOA | PE | PU PASSED | Jun-15 |
| 6 | LIPOK | PE | 10 PASSED | Jun-14 |
| 7 | KONOAK | PE | 10 PASSED | Apr-15 |
| 8 | BAUNYEM | PE | PU PASSED | May-15 |
| 9 | PHANGAU | PE | 8 PASSED | Nov-11 |
| 10 | PONGJEI | PE | 10 PASSED | Sep-14 |
| 11 | CHANGANG | PE | 8 PASSED | Apr-15 |
| 12 | MEIBA | PE | 8 PASSED | Apr-15 |
| 13 | ELA | PE | 10 PASSED | Jan-14 |

| April 2015- Jan 2016 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | NAME | DESIGNATION | EDUCATIONAL QUALIFICATION | DATE OF JOINING |
| 1 | ONGVAI | PE | 8 PASSED | Apr-09 |
| 2 | CHINGSHAH | PE | 10 PASSED | Nov-11 |
| 3 | JAMES | PE | PU PASSED | May-15 |
| 4 | JOHAN | PE | 8 PASSED | Nov-11 |
| 5 | MOA | PE | PU PASSED | Jun-15 |
| 6 | LIPOK | PE | 10 PASSED | Jun-14 |
| 7 | KONOAK | PE | 10 PASSED | Apr-15 |
| 8 | BAUNYEM | PE | PU PASSED | May-15 |
| 9 | PHANGAU | PE | 8 PASSED | Nov-11 |
| 10 | PONGJEI | PE | 10 PASSED | Sep-14 |
| 11 | CHANGANG | PE | 8 PASSED | Apr-15 |
| 12 | MEIBA | PE | 8 PASSED | Apr-15 |
| 13 | ELA | PE | 10 PASSED | Jan-14 |

2. Capacity building:

| TRAINING REGISTER 2014-2015 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name Of The Staff Attended The Training | Designation Of The Staff Trained | Induction/Refresher/New Skills | For Which The Training Has Been Initiated | Training By (SACS/TSU/STRC/NGO |
| M.KONI.PHOM | PM | OST Training at Kohima | Opioid Substitution Treatment With Buprenorphine | SACS |
|  |  | Refresher | Program Management | STRC |
| L.MOJE.PHOM | Nurse | OST Training at Kohima | Opioid Substitution Treatment With Buprenorphine | SACS |
|  |  | Induction | Harm Reduction | NEGRIHMS SHILLONG |
| PURTOSHI | M&E CUM ACCTT | Refresher | Finance & MIS | STRC |
| PONGE | ORW | Refresher Training at Mokokchung | Refresher Training | SACS |
| MOA | PE | INDUCTION | INDUCTION | CSS |
| LIPOK | PE | INDUCTION | INDUCTION | CSS |
| CHINGMEI | PEER EDUCATOR | REFRESHER | HARM REDUCTION | CSS |
| BONGJEI | PE | REFRESHER | HARM REDUCTION | CSS |

| TRAINING REGISTER 2015-2016 |  |  |  |  |
| --- | --- | --- | --- | --- |
| NAME OF THE STAFF ATTENDED THE TRAINING | DESIGNATION OF THE STAFF TRAINED | INDUCTION/REFRESHER/NEW SKILLS | FOR WHICH THE TRAINING HAS BEEN INITIATED | TRAINING BY(SACS/TSU/STRC/NGO |
| CHINGSHAH | PE | REFRESHER | HARM REDUCTION | CSS |
| JOHAN | PE | REFRESHER | HARM REDUCTION | CSS |
| BONGJEI | PE | REFRESHER | HARM REDUCTION | CSS |
| ONGVAI | PE | REFRESHER | HARM REDUCTION | CSS |
| BANGOM | PE | REFRESHER | HARM REDUCTION | CSS |
| PONGE | PE | REFRESHER | HARM REDUCTION | CSS |
| MOA OZUKUM | PE | REFRESHER | HARM REDUCTION | CSS |
| LIPOK | PE | REFRESHER | HARM REDUCTION | CSS |
| PHANGAU | PE | REFRESHER | HARM REDUCTION | CSS |
| JAMES | PE | REFRESHER | HARM REDUCTION | CSS |
| BAUYEM | PE | REFRESHER | HARM REDUCTION | CSS |
| KONOAK | PE | REFRESHER | HARM REDUCTION | CSS |

- One ORW yet to be trained. In-house orientation has been given by project staffs.

3. Infrastructure of the organization:

- Office set-up: The TI Project Office has two rooms. Basic office furniture’s and steel lockers available.

Accountant is based at TI project site.

- Recreational items: TV and DVD in working condition. Board game available.

- Laptop and digital camera in working order. Printer and desktop monitor not functioning.

- All 17 formats in place and used by staffs and PEs.

- HRG Master Register and Line Listing available at project level.

- STI Clinic established at project office:

- Basic clinical instruments and observation bed in place.

- Audio visual privacy could not be maintained in clinic due to set-up of rooms. Accountant is sharing room with counselling room.

- Availability of STI Kits: Only Kit 1 & Kit 6.

- Syphilis testing kits available.

- N/S destroyer in place but sterilizer not functional.

- Abscess prevention and management materials available.

- Gloves, cottons and bandages available.

- Colour coded Waste Disposal Bins not maintained.

- Disinfection of used N/S not done before final disposal.

- Waste disposal pits constructed but not as per guideline.

- General medicines are also available.

- Network Clinic Format and Referral Slips available and in place.

- Contracted Doctor hardly visits TI Clinic. TI project is availing the service of another local Doctor who visits clinic twice in a month and support the project. Constructive feedbacks/ suggestions are also given by the Doctor to project staffs to scale up their good work.

- Documentation and Reporting:

- All 17 formats for data collection in use.

- SIMS and SOEs are submitted to NSACS in the first week of succeeding month.

- PE’s submit their reports to their respective ORW on a weekly basis.

- Review meeting done on a weekly and monthly basis and actions are taken as per the gaps and achievements for each staffs and PEs.

- Action plans are developed for each staffs and PEs after every review meetings.

- Mismatch of entries in data tool collection formats observed from PE- ORW.

- Electronic database and management reporting systems exist for tracking clients, programme outcomes and financial information.

- Feedback and compliances to audit observations were not followed.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

|  | April 2014- Mar. 2015: | April 2015 – Jan. 2016 |
| --- | --- | --- |
| Target | 300 | 300 |
| Achievement | 300 | 300 |

2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counselling.

Not applicable

3. Registration of truckers from 2 service sources i.e. STI clinics and counseling.

Not applicable

4. Micro planning in place and the same is reflected in Quality and documentation.

Micro planning and outreach plans available at project level and commodity requirements for individual HRGs are projected. Quarterly plans are done for Program Manager, ORWs and PEs. This is followed up by monthly plans for commodity distribution and referrals. Weekly plans are in place to follow-up on the same.

Review of outreach is done on a monthly and weekly basis during weekly and monthly meetings. However, ORWs are not able to conduct field visits as planned. ORWs conducts only 2- 3 field visitin a month.

5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

|  | April 2014- Mar. 2015: | April 2015 – Jan. 2016 |
| --- | --- | --- |
| Target | 300 | 300 |
| Achievement | 300 | 300 |
| Newly registered | 30 | 18 |
| Active HRGs | 282 | 300 |
| HRGs on OST | 31 | 17 |
| Drop-out |  | 9 |
| Regular Contact | None could be contacted 20 days in every month for delivery of any project services because service is not required by HRGs as risk behaviour is low. |  |

6. Outreach planning – quality, documentation and reflection in implementation

- Micro planning and outreach plans available at project level and commodity requirements for individual HRGs are projected. Quarterly plans are done for Program Manager, ORWs and PEs. This is followed up by monthly plans for commodity distribution and referrals. Weekly plans are in place to follow-up on the same.

- Review of outreach is done on a monthly and weekly basis during weekly and monthly meetings. However, ORWs are not able to conduct field visits accordingto plan. ORWs conducts only 2- 3 field visit in a month for the purpose of conducting Group Meetings with HRGs.

- Review meetings are documented. Details of last meeting’s review are followed-up and actions taken are highlighted.

7. PE: HRG ratio:

- Ratio of PE to HRG is 1:25 for IDU as per contract agreements

- 12 PEs on board against a target of 300 IDUs.

8. Regular contacts

- None could be contacted 20 days in every month for delivery of any project services because service is not required by HRGs as risk behaviour is low.

- Needfor commodities on a daily basis are not required. Moreover distribution of commodities could not be achieved because most of the HRGs are farmers and daily wage labourers, who go to the field/ jungleand return back after 4-7 days.

9. Documentation of the peer education

- Peer field dairies and Form B in use by PEs to capture their field activities. IEC and BCC materials are also used for imparting awareness on HIV, safe practise and OST program.

10. Quality of peer education- messages, skills and reflection in the community

- Hotspot level meetings are conduced 2-4 times in a month to increase the knowledge level of the community members. IEC and BCC materials are also used for imparting awareness on HIV, safe practise and OST program.

- Community members have basic knowledge of HIV, proper condom usage and safe injecting practices. They are happy with the project for linking them up with various health care service providers.

11. Supervision- mechanism, process, follow-up in action taken etc

- Field-mentoring and supervision: Each ORW has 6 peer educators and undertakes a mentoring role. An average, 2 field visits are conducted by ORWs. During these visits the ORW supervises the hotspots level meeting, one-to-one/group sessions conducted by PEs with HRGs, providing new information and monitor field level performance.

- Meeting-based supervision: Every week ORW and PEs meets for reporting and planning. During these meeting ORW assist PEs in documentation of field activities, review performance of the previous week and plan for the succeeding week

- Overall supervision of outreach plan and field activity is done by Program Manager.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

- Static STI has been established and managed by a full time Nurse.

- Part time Doctor hardly visit clinic during assessment period. TI Project is availing the service of another local Doctor who visits clinic twice in a month and support the project activities. Constructive feedbacks/ suggestions are also given by the Doctor to project staffs to scale up their good work.

- The clinic has adequate infrastructure and testing kits in place and has provision for handling STI cases. 8 reactive cases of Syphilis witnessed and all were provided treatment.

- Only Kit 1 & 6 available at clinic for STI.

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- STI Clinic established at project office:

- Basic clinical instruments and observation bed in place.

- Audio visual privacy could not be maintained in clinic due to set-up of rooms. Accountant is sharing room with counselling room.

- Availability of STI Kits: Only Kit 1 & Kit 6.

- Syphilis testing kits available.

- N/S destroyer in place but sterilizer not functional.

- Abscess prevention and management materials available.

- Gloves, cottons and bandages available.

- Colour coded Waste Disposal Bins not maintained.

- Disinfection of used N/S not done before final disposal.

- Waste disposal pits constructed but not as per guideline.

- General medicines are also available.

- Network Clinic Format and Referral Slips available and in place.

- Contracted Doctor hardly visits TI Clinic. TI project is availing the service of another local Doctor who visits clinic twice in a month and support the project. Constructive feedbacks/ suggestions are also given by the Doctor to project staffs to scale up their good work.

- In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

Not applicable

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres..

- Nursehas been trained on Syndromic Case Management and basic Counselling skills.

- Syndromic case Management chart in place at the clinic and Nurse follows standard protocols.

- Referral support is available and all HIV testing is referred to PHC.

- Follow up on ICTC and Syphilis/ VDRL are done by Nurse based on ORWs and PEs reports.

- Linkages have been established at IMDH, Mokokchung for ART.

- Linkages also established with RNTCP at PHC for DOT.

- Abscess management service available and management provided both at project clinic and at the field level. Abscess prevention kits available at project STI clinic.

5. Documentation-

- TI NGO procures STI medicines Kits and Syphilis testing kits from NACO/SACS. Indent Register is maintained for requisitioning STI medicines from NSACS.

- Network Clinic Formats/ Registers used by TI NGO.

- Standard Referral slips in use and properly tracked.

- Stock registers of condom and medicines are maintained.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Free condoms are distributed by PE’s, ORWs and from TI DIC.

- No instance of shortage reported.

- Condom Social Marketing has also been initiated to meet the demand of the community members.

- Community members reported that they get free condoms as and when they demand.  No shortage has been reported during the assessment period.

7.No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

| Distribution of Commodity | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| Free Condom | - 25488 piece | - 20987 |
| Social Marketing of condom | - Actual nos. of branded condoms sold could not be ascertained from the system of record keeping available at the TI project. Only numbers issued to PEs and ORW recorded. Total numbers sold also could not be worked out because different brands are sold at different rate. |  |

- A total of 46475 condoms were distributed against projected requirement of 46968 during the assessment period.

8. No. of Needles / Syringes distributed through outreach / DIC.

|  | April 2014- March 2015: | April 2015- Jan. 2016 |
| --- | --- | --- |
| Projected requirement | 47568 | 36120 |
| N/S distributed | 46500 | 31390 |
| Used N/S returned | 29650 | 22835 |

- A total of 77890 N/S were distributed against projected requirement of 83688 during the assessment period.

- A total of 52485 used N/S were returned against a distribution of 77890.

9. Information on linkages for ICTC, DOT, ART, STI clinics.

- Referral linkage with PHC, Tamlu has been established for ICTC and DOT and ART.

- Linkages established at ART Centre IMDH, Mokokchung for ART.

- STI Clinic established at TI Project Office managed by a full time Nurse. Contracted Doctor hardly visits TI Clinic. TI project is availing the service of another local Doctor who visits clinic twice in a month and support the project. Constructive feedbacks/ suggestions are also given by the Doctor to project staffs to scale up their good work.

10. Referrals and follows up

- 100% of the registered HRG underwent Syphilis testing at least once during the last one year.

- On an average, 51 out of 300 HRGs tested twice for syphilis.

- 100% of the registered HRG underwent HIV testing at least once during the last one year.

- On an average, 93% of line listed HRGs were referred and only 25% tested twice for HIV.

V. Community participation

1. Collectivization activities:

- Crisis Management Team established with 12 community members’ representation.

- DIC Committee formed with 12 community members. The Committee is formally registered and was formed to assist in project activities and to create awareness on harm reduction among peers.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community members involved in the project as PEs and ORWs. Activities include outreach, commodity distribution, referrals and conduct of FGD.

- All activities documented in their respective diaries and formats.

- Five Important Dates were observed at the project level however numbers of community members who participated in these events were not recorded.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- Static STI Clinic established at TI DIC and managed by a full time Nurse. The Nurse is assisted by a local Doctor who visit clinic twice in a month..

- Referral linkage with PHC, Tamlu has been established for ICTC, OST and DOT. However Doctors and Counsellors are not regular.

- Linkages established at ART Centre IMDH, Mokokchung for ART.

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

- On an average, 51 out of 300 HRGs tested twice for syphilis.

- On an average, 93% of line listed HRGs were referred and only 25% tested twice for HIV.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- Support system has been established with the administration, Dobashis, Church community, colony/ ward leaders, Women Group, NGOs and student’s organizations. Some of the stakeholders are also on OST program.

- Advocacies with various key stakeholders had been done since the inception of the project in 2005. TI NGO is widely visible and accepted by the general community.

- The TI Project has also created support system on clinical service delivery with the ICTC and RNTCP Centre in PHC, Tamlu and with ART centre, IMDH, Mokokchung.

VII. Financial systems and procedures

1. Systems of planning:

- All the Planning & decision making is done by the Director, accountant and executive Members of the Organization. Planning is also done according to the prescribed system endorsed by SACS & NACO.

- Budget Utilization is more than 60% against the released fund and all expenditures are within approved budget in all budget head.

- NGO has not taken adequate measures to comply to audit observations.

2. Systems of payments-

- The NGO is practising a system of getting approval from PD before any transaction/ payments.

- All payments are made with proper bills and vouchers, but majority of bills are ‘katcha’.

- Cash payments beyond ₹ 5000/- was not observed.

- Cash in hand sometimes exceeds the limit of ₹ 5000/-

3. Systems of procurement-

- Purchase of drugs is done as per GMP guide line.

- System of taking Quotations for procurement of assets and commodities not adhered to. All procurement is centralized from Kohima.

4. Systems of documentation-

- No banking facility available in project site. Separate bank A/c is maintained at Longleng Town.

- Vouchers are printed and machine numbered, but ledger is not maintained for vouchers.

- Cash book is updated on a daily basis.

- SOE is submitted in time.

- Mismatch found in physical and financial reporting. Audit report is in place.

- Assets register is maintained but all fixed assets are marked only and not properly codified.

VIII. Competency of the project staff

VIII a. Project Manager

- Program Manager has been working in TI project since 2001 and had attended various trainings conducted by NSACS and TSU.

- Is competent and is familiar with the proposal, quarterly planning and program performance indicators. Conducts Weekly & Monthly review meetings and prepares Weekly & Monthly Plan for the Project staffs.

- Has basic knowledge on financial management and is skilled in computerization and management of data.

- Not very familiar with risk assessment.

VIII b. Counsellor

- Nurse is an ANM and has been working at TI Project since 2011 and has attended trainings on OST, Induction and Refresher.

- Possess basic counselling skills and management of Symptomatic STI.

- Is able to explain risk assessment and risk reduction processes.

- Is able to give basic counselling on HIV and STI.

- Has adequate knowledge about local drug use scenario.

- All registers and clinic formats maintained and updated.

- Conducts field visit as per needs from the community member: blood withdrawal and abscess management in the field.

VIII c. ORW

- Monitoring of PEs is done by the ORW and key performance indicators are closely checked. Outreach planning is done in consultation with their respective PEs or as per need based.

- One ORW has been working in TI project since 2006. Second ORW has graduated from PE.

- Both ORWs lacks clarity on hotspot analysis but has basic knowledge of STI symptoms.

- Supportive supervision is done based on needs and ORWs conducts FGD meetings at the hotspots. On an average, they conduct only 2-3 field visits in a month and were not able to meet respective PEs at their hotspot/ sites level monthly.

- Capacity building on rapport building, condom demonstration, safer injecting practise, abstinence, OSTand overdose prevention are imparted.

VIII d. Peer educators in IDU TI

- Prioritisation is done as per demand for commodities by HRGs and referral for HIV testing.

- Possesses fair condom demonstration skills and have basic knowledge on common symptomatic STI.

- Have a fair knowledge about various health care service provider and centres.

IX. a. Outreach activity in Core TI project

- Services are given to HRGs based on commodity distribution, referrals and HIV and Syphilis testing.

- Micro plans in place for each hotspots and prioritisation of outreach is done based on demand for commodity and uptake for referrals services. Individual HRGs are tracked for ICTC and syphilis testing. Micro plans are updated on a quarterly basis.

- On an average, ORWs conduct only 2-3 field visits in a month and were not able to meet respective PEs at their hotspot/ sites level monthly.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- Overall uptake of Project services and quality of service delivery (Free Condom & N/S) was well accepted by the HRGs.

- Above 80 % of the participants expressed satisfaction and were comfortable to approach the nurse for treatment and counselling.

- 281 HRGs were counselled at the DIC and field level.

- On an average, 51 out of 300 HRGs tested twice for syphilis.

- On an average, 93% of HRGs were referred and only 25% tested twice.

- A total of 46475 condoms were distributed against projected requirement of 46968 during the assessment period.

- All line listed HRGs were provided N/S and a total of 77890 N/S were distributed against projected requirement of 83688 during the assessment period.

- A total of 52485 used N/S were returned against a distribution of 77890 during the assessment period.

- Abscess management service available at all time both at the Clinic and in the hotspot level. A total of 10 abscess dressings were provided at clinic and 3 in the field during the assessment period.

XI. Community involvement

- Two [n=2] ORWs on board and both are from the HRG background. They are also involved during project planning and development of project proposal.

- Advocacies are conducted once in a monthas per plan and documented.

- A total of 22 advocacies were conducted to address issues of community members.

XII. Commodities

- Planning for meeting the demand of condom and N/S done at the project level on a quarterly, monthly and weekly basis.

- Demand analysis done based on distribution during the previous month or quarter. Frequency of injecting drugs (daily/ weekly/ occasionally), and numbers of sexual act are also taken into consideration for meeting the demands of the community members.

XIII. Enabling environment

- Linkages and advocacy initiative with other stakeholders has been established and advocacies are conducted once in a month as per plan and documented. A total of 22 advocacies were conducted to address issues of community members.

- Community Members expressed happiness with the project for sensitising the public about the issues of HRGs and creating linkages to various service providers.

- Good networking with key stakeholders established.

Confidential                                      Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to DAC)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Kholi. A | +91 9862797996 |
| Kevileme Visezuo | +91 9774978143 |
| Raju Gupta | +91 7085169800 |
| Officials from SACS/TSU (as facilitator) Ms. Imtisenla | +91 9856534957 |

| Name of the NGO: | Yingli Mission Society, Tamlu. |
| --- | --- |
| Typology of target population | Core Group (IDU) |
| Total population being covered against target: | April 2014- March 2015:; April 2015 - Jan. 2016. Target; 300; 300. Achievement; 300; 300. |
| Dates of Visit: | 2th March- 5th March, 2016 |
| Place of Visit: | Project Office (DIC) of Yingli Mission Society, Tamlu |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 72.8% | B | Good | Recommended for continuation |

Specific Recommendations:

Organizational capacity: - TI NGO to include signature of staffs in contract/ appointment/ contract renewal letters. - TI NGO should ensure that contracted part time Doctor regularly visit TI clinic. - Audio visual privacy should be ensured/ maintained in STI clinic. (Accountant is currently sharing same room with counselling room). - All fixed needs to be properly codified and marked. - TI NGO should ensure that printer and desktop monitor is repaired. - Sterilizer should be replaced. - TI NGO should ensure that STI Kits 2, 3, 4, 5 & 7are in place and buffer stock of STI medicines are maintained for 3 months: Only Kit 1 & Kit 6 are available currently. - Nurse should ensure that all used N/S are disinfected before final disposal. - Colour coded Waste Disposal Bins should be in place. - Waste disposal pits should be constructed as per NACO guideline. - Reorient all project staffs on key performance indicators. Financial management: - Adequate measures to should be taken to comply to audit observation and recommendations. - Cash transaction above ₹.5000/- should be minimized. - Cash in hand should be less than ₹ 5000/ as per NACO’s directive. - System of taking Quotations for procurement of assets and commodities should be practised. - No banking facility available in project site. However, TI NGO should open an Account at the nearest bank to cut cost in time and money for transportation. - Maintain a separate ledger for vouchers. - Minimize mismatch in physical and financial reporting. Program Delivery: - ORWs should ensure that each PEs has micro plansof their respective hot-spot(s). - ORWs should ensure that they conduct at least 4-5 days field visit every week. - Hot spot level meeting needs to be scaled up and meeting minutes should reflect topics discussed and numbers of HRGs who participated. - ORW needs to ensure that their respective PEs is met at the hotspot level every month. - Ratio of PE to HRG is 1:25 for IDU as per contract agreements. Therefore, PEs should ensure that each HRG’s under him/ her is regularly contacted every month and provided project services. - Scale up twice testing for HIV and follow up on referrals. - Numbers of HRG participant in events should be recorded in event register. - Encourage formation of support groups/ CBO for empowering HRGs.

Name of the Evaluators				Signature

| Kholi. A |  |
| --- | --- |
| Kevileme Visezuo |  |
| Raju Gupta |  |