Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

| Background of Project and Organisation: | SCOHD Society is a CBO network in Tamil Nadu and Puducherry where a group of community members took initiative to address the problems related to the sexual health and human rights of sexual minorities i.e., Gay, Lesbian, Bisexual, Transgender population. SCHOD was founded in 1996 for the welfare of the MSM and TG community, Supported by NAZ Foundation started the MSM project at Pudhucherry, other supporters were TNVHA, APAC-VHS , TI in Cuddalore district supported by TANSACS , in Pudhucherry by PACS, Pechan Project in Cuddalore |
| --- | --- |
| Name and address of the Organization: | Sahodaran Community Oriented Health Development (SCOHD) Society, No. 73, First Floor, Ellaiamman Kovil Street, Pudhucherry – 605 001 |
| Chief Functionary: | K. Sheethal, President |
| Year of establishment: | 2003 |
| Year and month of project initiation: | April 2014 to March 2016 |
| Evaluation team : | External Evaluators 1. Maria Benno 2. Vijay Anand 3.Vedam & Co. SACS/TSU representative 1. Balamurugan, AD - M&E , PACS |
| Time frame: | 1st to 3rd Februrary 2016 |

Profile of TI

(Information to be captured)

| Target Population Profile: FSW / MSM / IDU / TG/TRUCKERS / MIGRANTS | MSM TI |
| --- | --- |
| Type of Project: Core/ Core Composite / Bridge population | Core group |
| Size of Target Group(s) | Target 1200 Registered -1200 Drop Out- 46 Ongoing-1154 |
| Sub-Groups and their Size | Kothi= 706, DD= 373 & TG=75 |
| Target Area | Pudhucherry Municipality, Ozhuvarkarai Municipality, Villiyanur Commune, Bahur Commune,Thirubhuvanai Commune and Nettapakkam Commune |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

Based on interaction with 3 board members i.e. Secretary, Treasurer and a committee member it is evident that they are aware of the project done for MSM. They support very few community members indirectly, apart from knowing about the project periodically during their board meeting, they are not involved directly in the project activities. Annual general meeting is documented as once in three months. No project level advocacy meetings are done.

II. Organizational Capacity

1. Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

- All staff in place and issued appointment order and verifiable, there is no appointment order for Dr. Sathish Kumar for the period 6th January 2015 to March 2015. Dr. Sathish Kumar's name is entered in the attendance register since July 2014 and signed and salary issued. - 5 staff turnover witnessed (2 ORWs, 1 Accountant and 2 Doctors ). The position of PM and M&E the staff have been swapped - All ORWs are from the community - Monitoring and concentrated involvement of the Project Director is lacking in the TI Intervention - The Project Manager is promoted from among the ORW and from the community, hence PM lacks acceptance by the staff team especially other community staff. In certain documentation lacks uniformity. - Office bearers has strong commitment in building the capacity of staff and PEs but lack vision in reaching all the registered community members.

2. Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

Staff have attended trainings conducted by STRC. Training file available. 3 Trainings conducted for PE

3. Infrastructure of the organization

- Infrastructure of the organization is adequate - Name board available - TI Clinic lacks adequate ventilation, lighting and privacy. The TI Clinic does not follow the universal works precaution or medically accepted practice in sterilizing proctoscope. It was shared by the TI counsellor that the proctoscope are placed in a covered basin and placed on a gas stove and heated, the same is also used to prepare beverages for the staff - It was also shared that the autoclave was not in a working condition, however it was not available during physical verification at the time of evaluation

4. Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

- Formats and registers are maintained and available, however lacks uniformity - Mismatches observed from referrals slips to registers in terms of RMC, PT and ICTC - STI , RMC, and PT register not maintained it is reported only from the referral slips and Consolidated service delivery format and mostly not updated - Only 70% of the newly registered HRGs undergone PT. Not verifiable from referral slips and register maintained by the counsellor, it is observed in some cases the new HRG provided PT recorded as RMC in register maintained by counsellor and CSD format maintained by the ORWs - The Consolidated service delivery format does not reflect referrals for counselling services. During interactions in the filed HRGs though are familiar with the term counseling not able to explain the nature of the service and name the counsellor - Stereo type recording observed in the staff review meeting minutes - Committee registers have only meetings recorded but committees are not active and HRGs lack knowledge about these committees during interactions in the field. - One event has been documented with 144 HRGs as participants - Counselling sessions form is mostly incomplete and stereotype documentation observed - The issue of medicine in some cases does not match with that of the Treatment register maintained by the medical officer in the TI clinic - It is observed that all NACO formats not followed - In majority of the documents and registers the PM’s signature not observed and monitoring by PM not observed - The PD’s direct involvement also not observed

III. Program Deliverables

Outreach

| Indicators | Observations |
| --- | --- |
| 1. Line listing of the HRG by category | Computerized Master register at the TI level. Last registration of HRG on 03.01.2016. Format A completed and available. |
| 2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling. | NA |
| 3. Registration of truckers from 2 service sources i.e. STI clinics and counseling. | NA |
| 4. Micro planning in place and the same is reflected in Quality and documentation. | Updated hotspot analysis available for hotspots. ATP available, however tracking of HRGs for RMC, ICTC, PT for new HRGs not observed from available documents as mismatches observed from referral slips to registers. |
| 5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs | Target = 1200 / Regular contact is 798 (Average of last three months) 69% |
| 6. Outreach planning – quality, documentation and reflection in implementation | Updated hotspot analysis available for hotspots and verifiable however Form B is maintained by ORWs, Except for a few PE others lack knowledge about Form B. Prioritization of HRG is not done by ORWs based on risk and vulnerability data. The project team lacks conceptual clarity on the TI programme, in reporting of the actual data for the services uptake, in rendering quality outreach messages, and also do risk - vulnerability assessment along with condom demand on quarterly basis. |
| 7. PE: HRG ratio, PE:migrants/truckers | 1:60 ratio of PE to HRG observed |
| 8. Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members | Though regular contact is 69% tracking for services - RMC, PT for new identification and counselling had been very low in the assessment period |
| 9. Documentation of the peer education | - Form B is maintained by ORWs, Except for a few PE others lack knowledge about Form B. Prioritization of HRG is not done by ORWs based on risk and vulnerability data. - PE are part of the weekly review meetings and verifiable from review meeting register |
| 10. Quality of peer education- messages, skills and reflection in the community | The PEs lack understanding about the committees they are part of, and information about basics of HIV, STI. Lack condom demonstration skills not known and not properly documented. PEs is documenting only the services provided but the quality of their work is not documented. 45% PE attended the FGD at the time of evaluation |
| 11. Supervision- mechanism, process, follow-up in action taken etc | - All the PE have been met at the hotspot and provided support by the ORW four times in a month. Inferred from interactions with ORWs and PE - The current PM is promoted from ORW and lacks supervisory skills and conceptual understanding of the TI components and related documentation |

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

Referrals are made to government facilities for STI services, namely- odiyansalai PHC, JIPMER, Nettapakkam PHC, Thavalakuppam PHC, Villiyanur PHC, Thiruhuvanai PHC, Mannadipet PHC, Mahathma Gandhi Medical College, Indra Gandhi Medical College GH and Government Hospital and the TI clinic. TI Medical Officer lacks training on SCM and NACO guidelines in treatment protocol and clinic maintenance. Observed from interaction with Medical officer, STI Control Programme- Urban Primary Health Center, Odiansalai and STI Counsellor –Indira Gandhi Medical College and Hospital, services are adequate

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

TI Medical Officer lacks training on SCM and NACO guidelines in treatment protocol and clinic maintenance

3. In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

NA

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

TI Medical Officer lacks training on SCM and NACO guidelines in treatment protocol and clinic maintenance. Follow up mechanism by the TI counsellor not observed, there is an understanding that the work of the TI team is over with referrals made to the STI facilities and reporting the numbers.

5. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- Those HRGs accessing services for STI, RMC, ART and ICTC services at the government facilities are not counselled by the TI counsellor. - HIV positive line list available with the counsellor however follow up and positive living counselling not done by the TI Counsellor - Follow up of Syphilis reactive clients and STI diagnosed clients not observed at the TI level - It was shared by the TI counsellor that they give away the STI Clinic network form to the HRGs attending at the TI Clinic and the carbon copy retained. At the time of evaluation it was observed that the STI Clinic network form was used as rough sheet / one side paper , as data extracted by ORW was written on it and submitted - Mismatches observed from referrals slips to registers in terms of RMC, PT and ICTC - STI , RMC, and PT register not maintained it is reported only from the referral slips and Consolidated service delivery format and mostly not updated - Only 70% of the newly registered HRGs undergone PT. Not verifiable from referral slips and register maintained by the counsellor, it is observed in some cases the new HRG provided PT recorded as RMC in register maintained by counsellor and CSD format maintained by the ORWs - The Consolidated service delivery format does not reflect referrals for counselling services. During interactions in the field HRGs though are familiar with the term counseling not able to explain the nature of the service and name the counsellor - The issue of medicine in some cases does not match with that of the Treatment register maintained by the medical officer in the TI clinic - It is observed that all NACO formats not followed - In majority of the documents and registers the PM’s signature not observed and monitoring by PM not observed

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Condom demand is 203720 condom distribution is 238314. It is observed 17% over distribution of condom. It is also observed during field visit that HRGs lack condom demonstration skills - No stock out during assessment period - 342 condom distributed through social marketing initiated since December 2015 as shared by the M&E, verifiable in FGDs with HRGs in the field. The data shared by the M&E (342 sold) does not match with that given by the ORWs (550 sold). The account for the cash through CSM not observed

7. No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

Condom distribution through Hand to hand = 197733 & Through Outlets = 40581. As per ORW data 618 condom sold through social marketing and 342 condom distributed through social marketing initiated since December 2015, quality of data management

8. No. of Needles / Syringes distributed through outreach / DIC.

NA

9. Information on linkages for ICTC, DOT, ART, STI clinics.

Linkages for ICTC, DOT, ART, STI clinics adequate, and the TI team has rapport with service providers

10. Referrals and follows up

- 75% of HRGs had undergone RMC twice in the last one year as per data, however not verifiable in majority of the cases from the referral slips and visit to the referral centers - Follow up on newly identified HRGs for PT not verifiable from referral slips and register maintained by the counsellor, it is observed in some cases the new HRG provided PT recorded as RMC in register maintained by counsellor and CSD format maintained by the ORWs - 70% of newly registered HRGs availed PT 30% yet to avail PT - Out of referred for ICTC and Syphilis 1319 have accessed services (87%) there is gap of 13%

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- Average of 7-8 HRGs are documented as members of the committees (STI, DIC, Condom, Financial, Crisis, Programme Management) - It is also observed from records that the President is member of all committees and few HRGs are members in more than one committee. - During field interactions with the HRGs it is observed that majority of them are not aware of their membership in the CBO and subscription to be paid, however as per the CBO records at present there are 680 members

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Being a CBO the staff are mostly from the community and they are involved in the TI.

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages for STI/ICTC/TB established with government facilities

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

Out of referred for ICTC 1319 have accessed services (87%) there is gap of 13%

3. Support system developed with various stakeholders and involvement of various stakeholders in the project.

Interaction with stakeholders namely Medical Practitioner, NGO representatives, PA to politician, representative from journalist forum, PRO of TG Clinic, held. It is observed that this is the first time they have come together as a group and discussing on economic generation activities for the HRGs. They have been engaging with the PD at a one to one level.

Performance

| Indicator | Target | Achievement | Percentage (%) |
| --- | --- | --- | --- |
| Coverage | 1200 | 1200 | 100 |
| Unique contact | 1200 | 986 | 85 |
| Regular contact | 968 | 798 (Average of last three months) | 69 |
| STI clinic attendance | 4800 | 2974 | 62% |
| ICTC testing | 2400 | 1517 | 63% |
| Syphilis Screening | 2400 | 1517 | 63% |
| Condom demand / Supply | 203720 | 238314 | 17 (over distribution) |
| Number of PLHA/ linked to ART | 2 | Both linked to ART | 100 |

VII. Financial systems and procedures

1. Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

A letter sent to the CBO by PSACS is available but there is no signed agreement between both the parties viz. PSACS and CBO. . We are advised by the CBO that NACOSACS guidelines are being followed.

2. Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

Vouchers are available for all expenses incurred. But the voucher forms used are one-side papers. This is not in order as vouchers constitute important documentary evidence. At present only the Project Head approves the vouchers. There is a need to ensure that other functionaries like Project Manager and Accountant also authenticate the vouchers prior to the Project Head finally approving them. It is also necessary for the vouchers to carry Programme name. Programme documents in general are in agreement with the Accounting records. We are not able to feel satisfied that books and records are kept up to date on a day to day basis as the present incumbent working as Accountant was the Project Manager earlier. He is seen actively involved in attending to all matters of running the CBO along with the present incumbent working as Project Manager System of extending advances for incurring expenses, if any available, has not come to our notice. .

3. Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

Gel (Lubricants) were procured but the system of obtaining competitive quotations is not followed for acquiring lubricants.

4. Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

CBO President and Treasurer are the joint signatories who operate the Savings Bank account exclusively maintained for the project. It is maintained with Bank of Baroda, Puducherry. Bank reconciliation statements are being prepared.

VIII. Competency of the project staff

VIII a. Project Manager Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

Programme Manager completed Masters in Tamil Literature and has 5 years of experience in the TI and since 8 months promoted from the position of ORW and from the community. Conducts weekly staff review meetings, however lacks conceptual clarity about programme performance indicators and supervisory & monitoring skills

VIII b. ANM/Counselor Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

Counsellor is from the community, has done a course in Operation Theatre Assistance, and 7 years experience as TI counsellor. However lacks clarity on risk assessment, risk reduction, maintenance and updating of data and registers. Lacks follow up on STI diagnosed clients and HRGs living with HIV

VIII c. ANM/Counselor in IDU TI Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments. For ANM, adequate abscess management skills.

NA

VIII d. ORW Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

All ORWs are from the community. They lack knowledge on various indicators for their PEs, outreach plan . Updated hotspot analysis available, lack field level action based on review meetings and lack uniformity in documentation

VIII e. Peer educators Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

PEs lack understanding of the importance of RMC and ICTC testing only by coercing HRGs are been referred or escort to ICTC/STI centers and also they lack understanding about prioritizing hotspots, and HRGs based on risk and vulnerability and their condom demonstration skills was not up to the mark which is clearly evident in the field among HRGs. Availability of demo model not observed among the PEs

VIII f. Peer educators in IDU TI Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

NA

VIII g. Peer Educators in Migrant Projects Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritise the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

NA

VIII h. Peer Educators in Truckers Project Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

NA

VIII i. M&E officer Whether the M&E officer ( FSW and MSM/TG TIs with more than 800 population and all migrant Tis are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

The present M&E is with the CBO since 2003, in the TI since 2011 as PM and from April 2015 works as M&E officer. Done Diploma in Electronic communication. The data given for same category differs in some of the cases, system generated data does not match with the data extracted from base records of the ORWs and lacks analytical skills in providing information about gaps in outreach, service uptake and validation of the data before reporting on to the MTR/SIMS

IX. a. Outreach activity in Core TI project Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

It is observed from the interaction with the ORWs that quarterly hotspot analysis is done and documented. Outreach activities reflect uptake of services, however in few cases gaps seen. ATP available and due list to track HRGs for service uptake. CSD is mostly incomplete

IX. b. Outreach activity in Truckers and Migrant Project Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

NA

X. Services Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

Overall service uptake as reported in the project is just satisfactory. Quality of services and service delivery is adequate at the government facilities. Quality of services and service delivery and clinic maintenance at the TI clinic is inadequate.

XI. Community involvement How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

Average of 7-8 HRGs are documented as members of the committees (STI, DIC, Condom, Financial, Crisis, Programme Management). It is also observed from records that the President is member of all committees and few HRGs are members in more than one committee. During field interactions with the HRGs it is observed that majority of them are not aware of their membership in the CBO and subscription to be paid, however as per the CBO records at present there are 680 members

XII. Commodities Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

Condom demand analysis is done quarterly, however it is observed that excess of condom is being distributed over the actual demand

XIII. Enabling environment Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

Advocacy meetings not planned and conducted during the assessment period. Some stakeholders have been engaged with the PD one a one on one basis not come together as a group and discussed issues pertaining to HRGs

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

TI has facilitated HRGs in getting ration card=53, voter ID=52, aadhar card=40, old age pension=6, TG pension=14, Job placement=5, bank accounts=23, SHG=5

XV. Best Practices if any

NA

Annexure C

Confidential                                  Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Maria Benno | 9444066739 |
| Vijay Anand | 9944466857 |
| Raghuram. V Vedam & Co | 8489008370 |
| Officials from SACS (as observers) Balamurugan | 9443623973 |

| Name of the NGO: | Sahodaran Community Oriented Health Development (SCOHD) Society |
| --- | --- |
| Typology of the target population: | Core- MSM |
| Total population being covered against target: | Target 1200 Registered -1200 Drop Out- 46 Ongoing-1154 |
| Dates of Visit: | 1st to 3rd February 2016 |
| Place of Visit: | Pudhucherry Region |

Overall Rating:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for continuation with closer monitoring from SACS |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

Organization Capacity: - The Project Holder to be more actively involved and engaged in the effective implementation of the TI with increased percentage of time in programme monitoring - The PM to be oriented on overall TI concept and capacity built on roles and responsibilities, and supervisory skills - Revisit the recruitment of PE positions and minimize PE turnover - The CBO office bearers to have more visioning of the TI programme, in giving directions and guidelines in TI project implementation, uniformity in documentation and uptake of services - Streamline and strengthen all documentation and ensure all NACO formats are followed by all staff Out Reach: - Enhance quality of overall documentation of all formats and registers. - Staff review meetings not to limit to weekly reporting also to discuss field issues and other aspects pertaining to effective implementation of TI - Follow up with newly identified HRGs for PT - Outreach and micro plan to be effectively used in increasing the regular contact and scale up on HRGs accessing services - Outreach team to prioritize and focus on those HRGs more at risk and vulnerable - To strengthen the quality of peer education and to have more clarity on TI concept. Clinic Services: - TI to ensure the TI Clinic doctor to be trained on Syndromic Case Management - Counselor to follow all NACO formats and update all documents and ensure confidentiality of all documents - Follow up on all HRGs referred to government facilities not limiting to only getting the referral slips signed and sealed - Follow up all STI diagnosed clients ,ensure complete treatment, partner treatment and partner counselling - To ensure data correlation from referral slips to formats and registers - Counsellor might have burnout issues and needs to be addressed by the Project Director as the counsellor is in the same position for many years - TI clinic doctor and counsellor to be oriented on clinic maintenance and sterilization of equipments used at the clinic - Only the TI clinic doctor to prescribe medicine - Counsellor to ensure follow up counselling for all HIV positive HRGs at the TI and refer to TI clinic doctor periodically to treat OIs Commodities: - Condom demand analysis to be done more effectively as excess of condom is being distributed over demand and the TI to effectively track condom distribution till the PE level and document - TI to ensure lubricants are distributed as per demand analysis gap of 30% observed - Strategically locate condom outlets in all hotspots Enabling Environment: - TI project to have clarity on the functions of the various committees, ensure periodic meetings are conducted with increased HRG representation in the committee as members - The CBO management to look into avenues in tapping the resources of the stake holders, periodic stakeholders meetings be conducted - TI project team to gather issues from HRGs through hotspot/DIC level meetings, plan and conduct advocacy meetings Recommendation to SACS: - Closer monitoring from SACS - Organize for training on SCM for the TI clinic doctor with periodic mentoring/supervisory visits and orientation on clinic maintenance for counsellor & doctor Recommendation to TSU: - Closer handholding in strengthening documentation - As project staff lack understanding and clarity on the role of advocacy in the project. The project team to be helped by TSU to develop understanding and a strategy for advocacy

Name of the evaluators				Signature

| Maria Benno |  |
| --- | --- |
| Vijay Anand |  |
| Raghuram. V Vedam & Co. |  |